## Slide 1: wP5: HiRadMat@SPS – Status report
EUCARD Steering Committee Meeting
INFN-Frascati, November 4-5, 2009
Outline
HiRadMat – overview/reminder
Project : status – work plan
Web pages - Open access
Summary
I. Efthymiopoulos – CERN

## Slide 2: The HiRadMat Facility
Study the impact of intense pulsed beams on materials
  Thermal management (heating)
    material damage even below melting point
    material vaporization (extreme conditions), cavitation
  Radiation damage to materials – change of properties
  Thermal shock - beam induced pressure waves
Test bed, important for the design validation of LHC near-beam components before installation in the machine
Requires LHC-type beam from pilot to 288 nominal bunches
Foreseen clients : LHC collimators, protection devices, machine components, material studies (bulk, superconductors), high-power targetry, irradiation tests of electronics
What is it?

## Slide 3: The HiRadMat Facility
Examples
High-intensity beam on a solid target
MERIT experiment: High-intensity beam on a liquid Hg-target
High Energy Density Plasma formation, proton “Tunneling Effect”
LHC collimator: Displacement analysis – 500kW load case for 10s
Loss rate 4x1011 p/s (Beam Lifetime 12min)

## Slide 4: The HiRadMat Facility
Primary beam layout
SPS
TI 2
T9 target area / TNC
TT60
Beam
End of common part
with TI 2 transfer line
50 m
C. Hessler, 26/01/09
Beam
TT66 line (new)

## Slide 5: The HiRadMat Facility
Beam in shared mode during SPS operations
Primary proton/ion beam parameters
Parameter | Unit | Value (proton beam) | Value (lead ion beam)
Beam energy | GeV | 450 | 36.9×103 (177.4 GeV/n)
Bunch intensity | particles | 5×109 to 1.15(1.75)×1011 | 5×109 to 4.1×1010
Bunch length | cm | 11.2 | 11.2
Number of bunches | - | 1 – 288 | 1 – 592
Bunch spacing | ns | 25 | ≥ 25
Pulse energy | MJ | 2.4 | 28×10-3
Pulse length | ms | 7.2 | 7.2
Peak power | GW | 340 | 2.3
Normalized emittance (1s) | mm | 3.5 | 1.4
sx × sy at exp. (baseline) | mm2 | 1.0 | 1.0
sx × sy at exp. (request) | mm2 | 0.25 – 4.0 | 0.25 – 4.0
Integrated beam intensity (protons) |  | 1016 protons/year 10 experiments × 1015 protons(max)/exp ~30100 extractions/exp | 

## Slide 6: The HiRadMat Facility
Irradiation area layout: TT66 line & TNC tunnel
Test area
~10 m long. space upstream the T9 target
[1.5,3.0] m lateral space
Possibility for fast installation of experiments
Cool-down space downstream the TNC tunnel
If requested, areas for test of electronics or component irradiation can be prepared

## Slide 7: The HiRadMat Facility
Parameter | Value
Experiments per year | 10
Maximum intensity per experiment | 1×1015 protons <30 full intensity pulses
Waiting time after experiment for de-installation | ≥ 2 weeks
Access during experiment (except urgent interventions) | no
Control of experiment and data taking | remote
Maximum intensity per year | 1×1016 protons
Parameter | Value
Installed experiments | 1
Material exposed to beam | C, CFC, Cu, W, hBN, Al, Be, …, advanced composite materials
Volume of exposed material | ≤ 16,800 cm3
Equipment size Length (flange-to-flange) Width Height below beam line Height above beam line | ≤ 7.0 m ≤ 1.0 m 1.1 m ≤ 0.8 m
Weight | ≤ 4,000 kg
Handling zone (L × W × H) | 15  2.0  2.2 m3
Equipment support | comes with experiment – quick installation interface required
Cool-down space | see equipment size
Crane support | mobile cranes sufficient
Handling | prepare fast handling and remote installation with crane
Design parameters for the experimental area
Specification document
Additional requirements for the exp. area will depend on the type of equipment and test planned
Safety and RP constraints should come in addition

## Slide 8: The HiRadMat Project
The facility was originally proposed by R. Assmann in 2006 and included as part of the new initiatives program of CERN. A working group, coordinated by R. Assmann, did a conceptual design. The results were presented to A&T sector management in February 2009, and a summary specification document is under publication.
The creation of the HiRadMat facility was included and recommended in the summary Memo from the CERN Irradiation Facilities WG (Lucie Linssen/PH – chair)
The HiRadMat Project was approved in summer’09 and included in the CERN MTP for 6MCHF
  Project leader : Ilias Efthymiopoulos (EN/MEF)
  Target dates : First beam in the facility by June 2011 then two months of commissioning, first users by Q4 2011
HiRadMat is also included in the EUCARD/FP7 project as Transnational Access
  http://eucard.web.cern.ch/EuCARD/activities/access/
  Funds available to support EU users for the exploitation of the facility – within limits!
Overview - reminder

## Slide 9: The HiRadMat Project
Project structure
HiRadMat Facility Project
Project Leader : I. Efthymiopoulos
Deputy PL : S. Evrard
Project Team
User Selection Panel
Operation
Primary beam WG
M. Meddahi, C. Hessler
WANF Dismantling WG
S. Evrard, Hel. Vincke
Irradiation area WG
A. Pardons, S. Evrard
Beam Commissioning
M. Meddahi
Operation & Maintenance
CCC, M. Lazzaroni (superintendent)
User support Team
EN/MEF
A & T Sector Mgmt
SPS & LHC Physics coordinators & scientific committees
IEFC Committee
Safety:, L. Bruno, GS, E. Paulat
RP issues: Y. Algoet, L. Ulrici
Planning : H. Gaillard, N. Gilbert
Integration : M. Lazzaroni
External collaborators : SLAC team
Users : invited/informed (R. Assmann, B. Goddard, R. Schmidt, J. Blanco-Sancho…)

## Slide 10: The HiRadMat Facility
Ongoing work to finalize the functional specifications for the facility.
  First contact to (known) users for Beam Request Survey
WGs starting their work : prepare work packages and contact various groups for resources and budget estimates
  Project review January 19-20, 2010
  A doctoral student funded by EUCARD will start on April’10 – focus on RP issues for the design and operation of the faclity
Schedule guidelines:
  Access in BA7/TCC6 is limited due to LHC operation. Try to profit the most from the foreseen LHC technical stops (~3 days/month)  flexibility !!!
  Plan :
    dismantling from WANF equipment completed in 2009/2010  access limitations
    installation of new TT66 beam line and irradiation area in TNC in 2010/2011 shutdown  competition with other shutdown works in the injectors after the 20month operation
Status
Very challenging!

## Slide 11: The HiRadMat Facility
Tentative schedule
Preliminary &
Very challenging !!!

## Slide 12: EUCARD/WP5 – HiRadMat Facility @SPS
Web pages for project and open access available
  http://cern.ch/hiradmat - http://eucard.web.cern.ch/EuCARD/activities/access/
  Article in CERN Courier in 2010 to advertize the facility? – other ideas?
Status

## Slide 13: EUCARD/WP5 – HiRadMat Facility @SPS
First contact with the users
  Known colleagues (~35) from CERN and outside labs
    LHC equipment: obstacles, vacuum, beam instrumentation, electronics
    Target R&D : isolde, neutrino beams
    Material R&D
  Asked to fill BeamRequestSurvey form as feedback for the design specifications of the facility  stakeholders
Doctoral student funded by WP5 selected
  Will start on April’10 with FLUKA simulations for RP characterization and access conditions for the facility
  Most likely his Ph.D will be submitted at EPFL (Prof. L.Rivkin)
Status

## Slide 14: EUCARD/WP5 – HiRadMat Facility @SPS
The HiRadMat project is getting into shape
  Excellent team and WG coordinators
  Project review last week of January 2010
  Q4 2011 as target date for user access remains, but the schedule is very challenging – we’ll do our best to make it!
    Leaves ~7(11) weeks in 2011 + full 2012 run for users/open access
WP5/Transnational Access EUCARD web pages done
  First official announcement to users for Beam Request Survey  8 replies so far, more to come…
  Next step: finalize user selection procedures and related documentation
Summary
Thank you!