## Detector TDR Computing Support
WBS |  |  | Item | Required Man-months (2 years) |  |  |  | Manpower sources
|  |  |  | Phy | Eng | Tecn | Comp Prof | Phys | In1 | In2 | In3 | Miss | Eng | In1 | In2 | In3 | Miss | Tecn | In1 | In2 | In3 | Miss | ComProf | In1 | In2 | In3 | Miss
X |  |  | Computing support for the Project TDR
X | 1 |  | Management (Morandin)
X | 1 | 1 | computing coordination | 3 |  |  |  | 3 | Padova |  |  | 0 | [14 empty] | 0
X | 1 | 2 | operation management | [8 empty] | 0 | [14 empty] | 0
X | 1 | 3 | offline coordination | 6 |  |  |  | 6 |  |  |  | 0 | [14 empty] | 0
X | 2 |  | Fast-full coordination
X | 2 | 1 | full simulation background into fast simulation |  |  |  | 3 |  |  |  |  | 0 | [14 empty] | 3
X | 2 | 2 | compare the fast and full simulations |  |  |  | 3 |  |  |  |  | 0 | [14 empty] | 3
X | 2 |  | Fast simulation (Rama)
X | 2 | 1 | Coordination | [8 empty] | 0 | [14 empty] | 0
X | 2 | 2 | Core development | [8 empty] | 0 | [14 empty] | 0
X | 2 | 3 | Sub-detector simulation code dev. & maint. | [8 empty] | 0
X | 3 |  | Geant4 simulation (Bianchi, Paoloni)
X | 3 | 1 | Coordination | [8 empty] | 0 | [14 empty] | 0
X | 3 | 2 | Core dev. & maint. |  |  |  | 12 |  |  |  |  | 0 | [14 empty] | 12
X | 3 | 3 | Sub-detector simulation code dev. & maint. | [8 empty] | 0 | [14 empty] | 0
X | 4 |  | Operation (Stroili)
X | 4 | 1 | Validation and quality assurance | [8 empty] | 0 | [14 empty] | 0
X | 4 | 2 | Periodic build and release distribution | [8 empty] | 0 | [14 empty] | 0
X | 4 | 3 | Simulation production | [8 empty] | 0 | [14 empty] | 0
X | 5 |  | Offline infrastructure (Brown)
X | 5 | 1 | Subversion rep. managemet |  |  |  | 6 |  |  |  |  | 0 | [14 empty] | 6
X | 5 | 2 | Package management |  |  |  | 6 |  |  |  |  | 0 | [14 empty] | 6
X | 5 | 3 | Software release tools dev. & maint. |  |  |  | 6 |  |  |  |  | 0 | [14 empty] | 6
X | 5 | 4 | Databases | [8 empty] | 0 | [14 empty] | 0
X | 5 | 5 | Development of infrastructure packages | 12 | [7 empty] | 12 | [14 empty] | 0
X | 5 | 6 | BaBar code migration | 12 | [7 empty] | 12 | [14 empty] | 0
X | 6 |  | Distributed computing (Fella, Luppi)
X | 6 | 1 | GRID production |  |  |  | 6 |  |  |  |  | 0 | [14 empty] | 6
X | 6 | 2 | Data distribution and bookkeeping |  |  |  | 6 |  |  |  |  | 0 | [14 empty] | 6
X | 7 |  | Administative tools and central AAI (Gianoli, Murtas)
X | 7 | 1 | Collaboration DB dev. & manag. |  |  |  | 4 |  |  |  |  | 0 | [14 empty] | 4
X | 7 | 2 | AAI system (LDAP) dev. & maint. |  |  |  | 4 |  |  |  |  | 0 | [14 empty] | 4
X | 7 | 3 | User support / documentation |  |  |  | 2 |  |  |  |  | 0 | [14 empty] | 2
X | 8 |  | Collaborative tools (Gianoli, Murtas)
X | 8 | 1 | Web site |  |  |  | 6 |  |  |  |  | 0 | [14 empty] | 6
X | 8 | 2 | Tools configuration and maintenance |  |  |  | 3 |  |  |  |  | 0 | [14 empty] | 3
X | 8 | 3 | Tools developement |  |  |  | 3 |  |  |  |  | 0 | [14 empty] | 3
X | 8 | 4 | Tools AAI integration |  |  |  | 3 |  |  |  |  | 0 | [14 empty] | 3
|  |  | TOTAL | 33 | 0 | 0 | 73 | 9 | 0 | 0 | 0 | 24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 73
Software development support
Collaborative and administration tools support
Offline infrastructure support
Simulation Support
Data bookkeeping, distributed computing
|  |  |  | Phys |  | Physicist
|  |  |  | Eng |  | Engineer
|  |  |  | Tecn |  | Technician
|  |  |  | Comp Prof |  | Computing Professional
|  |  |  | In1,2,3 |  | Institutions contributing
|  |  |  | Miss |  | Missing Manpower
All numbers in man-months, with the hypothesis of two years for TDR preparation (2009-2010)

## Comp prof for TDR Computing Support
Activity | Manpower | Detailed tasks | Prerequisites
Software development support | 1 FTE | develop and support Subversion server scripts that implement the SuperB code repository policy | High school diploma in Computer science; Univ. degree in Computer science or equivalent preferable; experience with scripting languages and programming; knowledge of Linux operating system
develop and support tools (scripts) to support SuperB packages (package creation, tagging, migration, comparison, ...)
develop and support tools (scripts) for the development and distribution of SuperB software releases
develop and support tools for evaluating and managing SuperB software dependencies
develop and support tools for building SuperB software release binaries
Collaborative and administration tools support | 1 FTE | design and implement the SuperB user DB at LNF with associated user interfaces and complete the design of the LDAP DB to be used as the base for the AA services; | High school diploma in Computer science; Univ. degree in Computer science or equivalent preferable; basic experience with relational DB, LDAPdirectory services; experience with script and OO programming
develop the tool to produce and update a LDAP directory service
install and configure additional collaborative tools (e.g.: Hypernews system)
complete the integration of the collaborative tools with the AA system (Sympa, Joomla, Indico...)
configure Sympa to manage dynamic mailing list and sender's lists
migrate to LNF the basic collaborative tools
provide user support including training and documentation
provide steady state maintenance
Offline infrastructure support | 1 FTE | facilitate the migration of selected BaBar offline software packages to SuperB offline software standards and new infrastructure packages | Univ. degree in Physics; experience with Object Oriented programming in C++; experience with software development at a recent HEP experiment; experience with BaBar software is preferable
work with physicists to define SuperB requirements on infrastructure software packages
evaluate existing (non-BaBar) infrastructure software packages for use in SuperB. This involves characterizing the performance, maintainability, interface, and design of these packages in the context of the SuperB requirements.
test prototypes of infrastructure software packages for use in SuperB
Simulation Support | 1 FTE | support the integration of full simulation background information into the fast simulation | Univ. degree in Physics Basic experience in Object Oriented programming in c++ Some experience with Geant4 toolkit is preferable
development of core functionalities of full simulation
support the integration of the sub-detector simulation code into the full simulation.
development software to compare the fast and full simulation descriptions of the SuperB detector
development software to validate and monitor the performance of the full and fast SuperB simulations
Data bookkeeping, distributed computing | 1 FTE | design and develop a distributed framework for analysis and simulation job submission and data storage | Univ. degree in Computer Science or equivalent; experience with Linux operating system and DBMS; knowledge of Grid computing preferable
design and develop a data bookkeeping system
setup and maintain a Grid site
setup and maintain the Grid infrastructure for the SuperB experiment
verify the compatibility of the experiment offline software with the Grid infrastructure