## Sheet1
Scientific
Keep track | Number | Title | WP | Lead | Type | DissLev | Due Date
1 | 1.1 | Report on analysis strategies and interconnections | 1 | CEA | R | CO | M18
2 | 1.2 | Report on novel approaches for event selection and statistical analysis | 1 | CEA | R | CO | M24
3 | 1.3 | Presentation of new results on double higgs production | 1 | CEA | R | PU | M43
4 | 1.4 | Presentation of new results on HZZ couplings | 1 | CEA | R | PU | M43
5 | 1.5 | Presentation of new results on ttH production | 1 | CEA | R | PU | M43
6 | 1.6 | Presentation of new results on new physics in dibosons | 1 | CEA | R | PU | M43
7 | 2.1 | Presentation on implementation of state equation in 3d code | 2 | UCL | R | PU | M18
8 | 2.2 | Report on extraction of damping timescale with numerical simulations | 2 | UCL | R | CO | M36
9 | 2.3 | Presentation on implementation of analytic gravitational-wave templates | 2 | UCL | R | PU | M18
10 | 2.4 | Report on template searches on real data | 2 | UCL | R | CO | M40
11 | 2.5 | Report on 3D-spin wavelet and Bayesian code | 2 | UCL | R | CO | M12
12 | 2.6 | Simulations with 3D-spin wavelet and Bayesian code | 2 | UCL | R | CO | M24
13 | 2.7 | Testing code and predicting forecast made | 2 | UCL | R | PU | M30
14 | 2.8 | publication on 3D-spin wavelet and Bayesian code application to first EUCLID data | 2 | UCL | R | PU | M40
15 | 2.9 | Report on development of cross-correlation and 3D mapping codes | 2 | UCL | R | CO | M12
16 | 2.10 | Publication on Simulation with cross-correlation and 3D mapping codes | 2 | UCL | R | PU | M24
17 | 2.11 | Publication on testing code and predicting forecast made for 3D and corr-correlation | 2 | UCL | R | PU | M30
18 | 2.12 | Application of cross-correlation and 3D mapping codes to first EUCLID data | 2 | UCL | R | CO | M40
19 | 3.1 | Report on data managing structure and identify critical points | 3 | AUTH | R | CO | M13
20 | 3.2 | Report on ESR projects to proceed with optimization | 3 | AUTH | R | CO | M23
21 | 3.3 | Report on implementation and performance of optimized projects | 3 | AUTH | R | CO | M30
22 | 3.4 | Report on cross-fertilization academy/non-academy for data management | 3 | AUTH | R | CO | M35
23 | 4.1 | Report on data analysis structure and identify critical points | 3 | AUTH | R | CO | M13
24 | 4.2 | Report on ESR projects to proceed with optimization | 3 | AUTH | R | CO | M23
25 | 4.3 | Report on implementation and performance of optimized projects | 3 | AUTH | R | CO | M30
26 | 4.4 | Report on cross-fertilization academy/non-academy for data analysis | 3 | AUTH | R | CO | M35
Managment
Keep track | Number | Title | WP | Lead | Type | DissLev | Due Date
1 | 5.1 | Report on network schools with ESR feedback | 5 | UNILE | R | Co | M24
2 | 5.2 | Report on effectiveness of secondment plan | 5 | UNILE | R | Co | M30
3 | 5.3 | Report on SW Carpentry full cycle with feedback from ESRs | 5 | UNILE | R | Co | M40
4 | 5.4 | Training Material available on website | 5 | UNILE | ADM | PU | M48
5 | 6.1 | Dissemination and activity plan | 6 | UNIPI | ADM | PU | M4
6 | 6.2 | First documentary on the project public | 6 | UNIPI | ADM | PU | M14
7 | 6.3 | Second documentary on the project public | 6 | UNIPI | ADM | PU | M24
8 | 6.4 | Third documentary on the project public | 6 | UNIPI | ADM | PU | M36
9 | 6.5 | Annual reports on dissemination and outreach activities at annual meetings | 6 | UNIPI | ADM | PU | M18
10 | 6.6 | Annual reports on dissemination and outreach activities at annual meetings | 6 | UNIPI | ADM | PU | M30
11 | 6.7 | Annual reports on dissemination and outreach activities at annual meetings | 6 | UNIPI | ADM | PU | M41
12 | 6.8 | Scientific publication report from project WP1-WP2 | 6 | UNIPI | ADM | PU | M48
13 | 6.9 | Dissemination and outreach material on website | 6 | UNIPI | ADM | PU | M48
14 | 6.10 | Scientific conference report | 6 | UNIPI | ADM | PU | M48
15 | 7.1 | Project website up and running with ESR application and registration system | 7 | UNIPI | ADM | PU | M1
16 | 7.2 | Kick-off meeting in Pisa | 7 | UNIPI | ADM | Co | M1
17 | 7.3 | Recruitment report with information on recruited ESR | 7 | UNIPI | ADM | PU | M5
18 | 7.4 | EJDAs signed | 7 | UNIPI | ADM | PU | M3
19 | 7.5 | Declaration of conformity | 7 | UNIPI | ADM | PU | M6
20 | 7.6 | CDP ready | 7 | UNIPI | ADM | Co | M9
21 | 7.7 | Report on PhD thesis status | 7 | UNIPI | ADM | Co | M40
22 | 7.8 | Final project with all activties and results obtained | 7 | UNIPI | ADM | PU | M48
WP | Start | End
1 | 9 | 48
2 | 9 | 48
3 | 9 | 48
4 | 9 | 48
5 | 7 | 48
6 | 9 | 48
7 | 1 | 48

## Sheet2
Scientific
Keep track | Number | Title | WP | Lead | Type | DissLev | Due Date
7 | 2.1 | Report on implementation of state equation in 3d code | 2 | UCL | R | CO | M12
9 | 2.3 | Report on implementation of analytic gravitational-wave templates | 2 | UCL | R | CO | M12
11 | 2.5 | Report on 3D-spin wavelet and Bayesian code | 2 | UCL | R | CO | M12
15 | 2.9 | Report on development of cross-correlation and 3D mapping codes | 2 | UCL | R | CO | M12
19 | 3.1 | Report on data managing structure and identify critical points | 3 | AUTH | R | CO | M13
23 | 4.1 | Report on data analysis structure and identify critical points | 3 | AUTH | R | CO | M13
1 | 1.1 | Report on analysis strategies and interconnections | 1 | CEA | R | CO | M18
20 | 3.2 | Report on ESR projects to proceed with optimization | 3 | AUTH | R | CO | M23
24 | 4.2 | Report on ESR projects to proceed with optimization | 3 | AUTH | R | CO | M23
2 | 1.2 | Report on novel approaches for event selection and statistical analysis | 1 | CEA | R | CO | M24
8 | 2.2 | Report on extraction of damping timescale with numerical simulations | 2 | UCL | R | CO | M24
10 | 2.4 | Report on template searches on real data | 2 | UCL | R | CO | M24
12 | 2.6 | Simulations with 3D-spin wavelet and Bayesian code | 2 | UCL | R | CO | M24
16 | 2.10 | Simulation with cross-correlation and 3D mapping codes | 2 | UCL | R | CO | M24
13 | 2.7 | Testing code and predicting forecast made | 2 | UCL | R | CO | M30
17 | 2.11 | Testing code and predicting forecast made for 3D and corr-correlation | 2 | UCL | R | CO | M30
21 | 3.3 | Report on implementation and performance of optimized projects | 3 | AUTH | R | CO | M30
25 | 4.3 | Report on implementation and performance of optimized projects | 3 | AUTH | R | CO | M30
22 | 3.4 | Report on cross-fertilization academy/non-academy for data management | 3 | AUTH | R | CO | M35
26 | 4.4 | Report on cross-fertilization academy/non-academy for data analysis | 3 | AUTH | R | CO | M35
14 | 2.8 | D-spin wavelet and Bayesian code application to first EUCLID data | 2 | UCL | R | CO | M40
18 | 2.12 | Application of cross-correlation and 3D mapping codes to first EUCLID data | 2 | UCL | R | CO | M40
3 | 1.3 | Presentation of new results on double higgs production | 1 | CEA | R | PU | M43
4 | 1.4 | Presentation of new results on HZZ couplings | 1 | CEA | R | PU | M43
5 | 1.5 | Presentation of new results on ttH production | 1 | CEA | R | PU | M43
6 | 1.6 | Presentation of new results on new physics in dibosons | 1 | CEA | R | PU | M43
Managment
Keep track | Number | Title | WP | Lead | Type | DissLev | Due Date
15 | 7.1 | Project website up and running with ESR application and registration system | 7 | UNIPI | ADM | PU | M1
16 | 7.2 | Kick-off meeting in Pisa | 7 | UNIPI | ADM | Co | M1
18 | 7.4 | EJDAs signed | 7 | UNIPI | ADM | PU | M3
5 | 6.1 | Dissemination and activity plan | 6 | UNIPI | ADM | PU | M4
17 | 7.3 | Recruitment report with information on recruited ESR | 7 | UNIPI | ADM | PU | M5
19 | 7.5 | Declaration of conformity | 7 | UNIPI | ADM | PU | M6
20 | 7.6 | CDP ready | 7 | UNIPI | ADM | Co | M9
2 | 5.2 | Report on effectiveness of secondment plan | 5 | UNILE | R | Co | M30
10 | 6.6 | Annual reports on dissemination and outreach activities at annual meetings | 6 | UNIPI | ADM | PU | M30
8 | 6.4 | Third documentary on the project public | 6 | UNIPI | ADM | PU | M36
3 | 5.3 | Report on SW Carpentry full cycle with feedback from ESRs | 5 | UNILE | R | Co | M40
21 | 7.7 | Report on PhD thesis status | 7 | UNIPI | ADM | Co | M40
11 | 6.7 | Annual reports on dissemination and outreach activities at annual meetings | 6 | UNIPI | ADM | PU | M41
4 | 5.4 | Training Material available on website | 5 | UNILE | ADM | PU | M48
12 | 6.8 | Scientific publication report from project WP1-WP2 | 6 | UNIPI | ADM | PU | M48
13 | 6.9 | Dissemination and outreach material on website | 6 | UNIPI | ADM | PU | M48
14 | 6.10 | Scientific conference report | 6 | UNIPI | ADM | PU | M48
22 | 7.8 | Final project with all activties and results obtained | 7 | UNIPI | ADM | PU | M48