## Slide 1: The Belle II Silicon Vertex Detector
Christoph Schwanda
Institute of High Energy Physics
Austrian Academy of Sciences
10th Belle PAC, February 9, 2016, KEK, Japan

## Slide 2: Components of the Belle II SVD
Ladders
End rings
Carbon fiber (CF) cone
End flange
PXD (independent sub-detector inside SVD)
Outer CF shell
Beam pipe

## Slide 3: SVD ladders
L6 Ladder (Kavli IPMU)
L5 Ladder
(HEPHY)
L4 Ladder (TIFR)
L3 Ladder (Melbourne)
FWD module
BWD module
Origami +z
Origami ce
Origami -z
BWD
FWD
Cooling pipe
Cooling pipe
Cooling pipe
BWD module (Pisa)
FWD module
(Pisa)
Layer | Ladders (spares) | DSSDs / ladder
6 | 16 (4) | 5
5 | 12 (3) | 4
4 | 10 (2) | 3
3 | 7 (2) | 2
47 FW/BW + spares (4)

## Slide 4: Ladder Anatomy (L6 ladder)
PF1
PB2
PB1
PA1
PA2
DSSD
PF2
Rib
AIREX
Origami hybrid
Origami hybrid
Flexible circuit to transmit detector signals to the ladder ends
APV25
Readout ASIC of the strips
FlexPA (PA/PF/PB)
Flexible circuit to transmit detector signals to the APV25
APV25
AIREX
Thermal insulator between the DSSD and APV25
PA0
Flexible circuit glued on the Origami hybrid to transmit n-side detector signals to the APV25
PA0
DSSDs
2 small rectangular (L3)
2-4 large rectangular (L4-6)
1 trapezoidal (L4-6)

## Slide 5: What happened since the focused VXD review in October 2015?
The Melbourne group (L3) was qualified to start ladder production (end of Oct 2015)
The TIFR and Kavli IPMU groups were qualified to assemble their final prototype (class B) ladders (Jan 2016)
Keratherm issue and its mitigation (Oct-Dec 2015)
PXD-SVD L3 clearance issue and its mitigation (Oct-Dec 2015)
Origami flex blister issue (since Nov 2015)

## Slide 6: Keratherm on FW/BW hybrids
BW module
FW module
Keratherm strip between APV25 chips and APV guard to establish thermal contact

## Slide 7: Keratherm issue
In Oct. 2015 a liquid was observed on the forward APV25 chips of L4.905 (class B-) and later also found on other ladders
The liquid is silicone oil, squeezed out of the Keratherm foil as it is compressed by more than 30% of its thickness (“bleeding”)
After consultation with the manufacturer we considered replacing the Softtherm 86/125 foil (red) by low bleeding Softtherm 86/235 (yellow)
Hybrid PCB
APV guard
Side edge of APV chip
Fluid at the edge of Keratherm

## Slide 8: Leakage after ~1 month and >10 Mrad irradiation
Softtherm 86/125 (red): Full surfaces of FR4 blocks moistened with oil
Softtherm 86/235 (yellow): Surfaces of FR4 blocks only partially moistened with oil

## Slide 9: Summary of the Keratherm R&D
Irradiation test
  Samples of the old and new material were gamma irradiated at Takasaki Advanced Radiation Research Institute, JAEA (60Co source, >10 Mrad)
Bleeding test
  Bleeding of silicone oil was studied on irradiated samples for different gap widths
  Although also the new material leaks, it is significantly less
Thermal test
  Keratherm thermal conductivity was studied in FW/BW modules, both before and after irradiation
  Thermal properties of both materials are similar
  No significant change due to irradiation
  We decided to use the yellow Softtherm 86/235 for FW and BW end mounts
FW / BW module
Temperature probe
Al block
Ice water (~ 0°C)
Probes are placed on surfaces of end mount and APV guard
Thermal test setup

## Slide 10: PXD-SVD L3 clearance issue
Clearance between PXD and the new C35 capacitor in L3 is only 467µm in the CAD model (without solder thickness)
Clearance between PXD and the APV25 bonding pads is 995µm
PXD volume Ø66.2mm
New capacitor without solder (~300µm higher)
BW situation

## Slide 11: Modification on BWD bridge in L3
Increase this area (1mm)
OLD
NEW
We decided to mitigate the clearance issue by shifting L3 by 1 mm outwards by modifying the L3 bridges

## Slide 12: Modification on FWD bridge in L3
Increase this area (1mm)
OLD
NEW
Reduce material
Increase the chamfer in this area
Radius is shifted to the left
Chamfer is bigger and shifted to the right
A number of modifications are necessary on the FWD bridges to avoid L4 inference issues after the 1 mm shift

## Slide 13: Summary of the L3 modification studies
The L3 radius is increased by 1 mm to mitigate the clearance issue with the PXD volume
This increase is achieved by modifying the design of the L3 bridges – the end rings are unchanged
The SVD mechanics group has developed a new L3 bridge design that avoids interference problems with L4 in FW emerging after the shift
The Melbourne group (L3 assembly) has analyzed the impact of the new bridge design on every assembly step and made small modifications to the assembly procedure
The SVD software group has assessed the impact of the 1 mm shift on tracking performance, PXD ROI finding and alignment performance

## Slide 14: PA0 & Origami: the history
Aug 2014: crack problem found in PA0 flex that bring signals from sensor strips to APV25 chips on ORIGAMI flex circuits
  Full reproduction of ORIGAMI+PA0 needed
  ORIGAMI reproduced by the company end of 2014, PA0 crack problem need still to be solved
Oct 2014: PA task force in place
  Several months of investigations, optimization of the process and new design of the PA0
  Specifications documents for PA0 production & ORIGAMI assembly written
  Detailed QA procedure implemented: several electrical tests and visual inspection during production of PA0 & assembly of the ORIGAMI
Aug 2015: PA0 pre-prod. (batch0) successfully produced & assembled on 12 ORIGAMI, no cracks on PA0 and full test on a L5 class B ladder
  PA0 mass production started in Aug-Sep 2015: tested & no cracks
Oct 2015: ORIGAMI assembly started, divided in 3 batches with delivery expected in Dec 2015, Feb 2016, Mar 2016

## Slide 15: Origami flex blister issue
End of Nov 2015: large blisters appear on 5 out of 5 OCE circuits during the reflow step of batch1 mass production
Potential to destroy all origami circuits, mass production is halted for investigation of the issue
Bubbles are most likely due to humidity absorbed by the circuits (long storage at soldering company in non-humidity controlled environment)
Moisture expands in the oven due to high temperature (230 °C) during reflow

## Slide 16: Possible solutions
Components on origami are placed and soldered by hand
10 circuits/week (compared to 11.5 for reflow)
Manual soldering
Hybrid option
Circuits are dried by pre-baking at 120 °C for 17 hours
Dry reflow is performed to select good pieces
Perform another pre-baking at the day of reflow
Reflow soldering of components, except connectors
Manual soldering of connectors
Reproduction of failed circuits

## Slide 17: Possible solutions
Pros:
Effective
Schedule predictable and faster than the hybrid plan (10 circuits/week)
Cons:
Costs 50% higher than the original plan
Costs could be higher than in the hybrid option depending on the failure rate
Manual soldering
Hybrid option
Pros:
Possibly cheaper in case of low failure rate of the pre-baking cure
Cons:
Failure rate not precisely know, could be 40%
Pre-baking could cause pad oxidation leading to bonding/soldering problems
Schedule depends on failure rate, lower than manual soldering

## Slide 18: Recovery strategy
Short term
  A few pieces (8 O+Z and 6 O-Z) have already survived standard reflow @ Saiden
  5 OCE have been populated by hand soldering @ Saiden
  15 circuits (5 OCE, 5 O+Z, 5 O-Z) have been successfully pre-baked and will be equipped by vapor-phase soldering @ HEPHY
  Complete these circuits and distribute them in an optimized way to assembly sites in time to maintain production
  This allows to operate from mid March to end of June 2016
Long term
  Perform the necessary R&D to choose one solution (manual soldering or hybrid option)
  Determine failure rate with long pre-baking+reflow & perform tests on pad oxidation
  Complete this R&D by end of March 2016

## Slide 19: SVD ladder assembly

## Slide 20
Today

## Slide 21: Pisa (FW/BW)
Production status
15 class A FW sub-assemblies and 23 class A BW sub-assemblies have been completed out of 47 each
Brass pins
Before shimming
After shimming on PF1 chuck
Shimming on PF1 chuck
Shimming on brass pins
Traced back to non-planarity of the PA:
  Original shimming on brass pins used to compensate this effect
  Better cure found with a 50 um shim applied on the PF1 chuck
Resume SFW production after the Feb 2016 B2GM
P-side glue failure
  PF1 was found lifted up on 2 SFWs

## Slide 22: Pisa schedule
Today’s status

## Slide 23: Melbourne (L3)
Qualification review for class A production was held Oct-29, 2015
  Follow-up issue: no glue under bias pads or PA may peel off from detector
  Cured by a modification of the moveable parts of the gluing jig, to allow for a correct glue thickness and spread all over the pad line
The impact of the L3 bridge design change on the assembly procedure was studied and minor modifications were implemented
L3 production will start after the L3 bridges are re-manufactured and the assembly procedure is confirmed on a mechanical dummy

## Slide 24: Melbourne schedule
To finish in May…

## Slide 25: TIFR (L4)
L4.906 ladder (assembled in Oct 2015): One reference point on the FW sensor was shifted by ~400 mm
Traced back to stress generated on the sensor during clamping of the FW hybrid board
Can be cured by a shim placed in the slant jig
Started the assembly of the final prototype (class B)
Qqualification for class A production to beheld starting of March
shim
clamp

## Slide 26: TIFR schedule
1st half shell completed: Oct 2016
Production completed: May 2017

## Slide 27: HEPHY (L5)
Site qualified for ladder production in Aug 2015
Sep – Dec 2015: class C ladder for ladder mount test, Keratherm R&D
First class A ladder (L5.002) started Jan 14, 2016 and completed Feb 1, 2016 (12 working days)
Mechanical survey ongoing, electrical test will be done mid of Februrary
L5.002: OS5 gluing
L5.002: CO2 clip gluing – 2016-01-29
Completed L5.002, still on assembly base – 2016-02-01

## Slide 28: HEPHY schedule
1st half shell completed: Aug 2016
Production completed: Mar 2017

## Slide 29: Kavli IPMU (L6)
To address issues identified in the Sep 2015 class C prototype, the group decided to assemble a “class D” ladder
In addition, a focused review (lead by H. Tajima) was held on Dec-9, 2015 and the list of items to investigate was extended
Study items in the class-D ladder
  PA1/PA2 gluing and wrapping
  High electrical noise around the rib region
  FW DSSD lift-up (similar to L4)
  Common DB use
  Documentation

## Slide 30: PA1/PA2 gluing and wrapping
Gluing parameters were tuned to reduce the amount of glue as requested by reviewers, glue spreads successfully under the wire bonding pads

## Slide 31: Kavli IPMU (L6)
The class-D assembly was completed on Jan 15, 2016
Outstanding issue in this ladder
  Reference points on one side of the ladder are systematically lower by 100-200 μm than nominal
  The gap between sensors and ribs will be monitored in the next assembly
The final prototype assembly (class B) has started last week

## Slide 32: Kavli IPMU schedule
1st half shell completed: Jan 2017
Production completed: Sep 2017

## Slide 33: Mechanics and commissioning

## Slide 34: SVD design revision 2.4 ® 2.5
Includes
  Modification of the L3 bridges, to shift L3 by 1 mm
  Fix of a few clearance problems in rev. 2.4
  Modification FW L4 endmount to improve L3 cable routing
L4 end mount
L3 cables (100 wires)
OLD
NEW
R=3mm

## Slide 35: Refurbishment of open CO2 cooling system
Schedule
  December 2015: disassemble current box, order new parts (done)
  January 2016: make new box (done)
  February 2016: install devices (ongoing)
  March 2016: re-write software and test
  End of March 2016: Shipping to KEK

## Slide 36: CO2 cooling pipe bending tool
Bending radius
(much smaller then result due to springback)
Support for the bent pipe
For pipe fixation and length control

## Slide 37: L6 cooling pipe attachment with cradle tool (Jan-29, 2016)

## Slide 38
L6 cooling pipe attachment with cradle tool (Jan-29, 2016)

## Slide 39: L6 cooling pipe attachment with cradle tool (Jan-29, 2016)
Support arms are to be prepared to confirm realistic movement for the next step
Similar tool/pipe needs to be prepared for L5 and L4

## Slide 40: Schedule for ladder mount
Feb – Jun 2016: Production of missing prototype tools and jigs
24th B2GM (Jun 2016):
  Prototype tools/jigs to discuss feedback to final jigs are prepared
  Jun 17, 2016 (Fri): Review of ladder mount procedure with the prototype tools/jigs
Jun – Oct 2016: Production of final tools and jigs
25th B2GM (Oct 2016):
  Final tools/jigs are prepared
  Review of ladder mount procedure with the final tools/jigs as the final feedback
Oct 2016 – Feb 2017: Repeat a number of practices
  Address all issues in the ladder mount procedure and finalize it
26th B2GM (Feb 2017):
  Get approval of the finalized procedure from SVD group by showing demonstration of a whole steps
  Afterwards start ladder mount
End of ladder mount: Oct 2017
Unfortunately, we are ‘one B2GM’ behind the schedule presented at the Oct 2015 BPAC review

## Slide 41: Electronics

## Slide 42: SVD readout system

## Slide 43: FADC redesign
V2 (current version)
  2 systems available (one at HEPHY, one at KEK)
  Each one capable of reading more than one full ladder
  Used in CERN test beams
V3 (redesign)
  Main changes: elimination of daughter boards, direct connection between Stratix FPGA and VME bus
  Jul – Aug 2015: V3 schematics at HEPHY
  Sep – Dec 2015: conversion P-cad ® Mentor done by company
  Feb 2016: manufacturing of two prototype PCBs, firmware migration to V3
  Feb/Mar 2016: testing and debugging of V3 at HEPHY
  Apr 2016: test of V3 at the DESY test beam

## Slide 44: Improving noise hardness of the FADC system
Increasing C35 capacitor from 10 ® 100 nF
  Presented at the Oct 2015 VXD review
  C35 now changed on all hybrid boards, new C35 will be used in origami assembly
LV power lines
  Separate +10V LV power lines for p- and n-sides have been identified as a potential source of common mode noise
  Combining the lines up to the DOCKs would require a change in FADC, DOCK PCBs and PS patch panels
  The proposal is to implement this in FADC V4

## Slide 45: Updated FADC schedule
May – Sep 2016: Development of V4 hardware (FADC, junction board) and remaining firmware
Oct – Dec 2016: Production of V4 and junction board prototypes
Jan/Feb 2017: Final test of V4 at HEPHY
Mar – May 2017: “mass production” (58 boards) of V4 including optical and electric testing at the company, in system test at HEPHY

## Slide 46: SVD schedule

## Slide 47: Ladder production schedule
End of L6 production: Sep. 2017
End of FW/BW production: Jul 2016

## Slide 48: Integration schedule
Start of ladder mount: Feb 2017
SVD ready: Dec 2017
VXD integration: from Dec 2017

## Slide 49: SVD milestones
 | Feb 2016 BPAC (Oct 2015 BPAC)
Completion origami+PA0 mass production | 1) (Mar 2016)
All assembly sites qualified | Mar 2016 (Jan 2016)
First class A ladder | Jan 2016 (Nov 2015)
Start of ladder mount | Feb 2017 (Oct 2016)
SVD ready | Dec 2017 (Sep 2017)
Start of VXD integration | Dec 2017 (Nov 2017)
Start of VXD installation | Jun 2018 (Apr 2018)
1) Depends on the option to be chosen for the origami mass production

## Slide 50: Schedule risk
Critical path defined by
  L6 production
  VXD integration and installation
Very little contingency in the present schedule
  No contingency in the L6 schedule
  2 months SVD only commissioning very tight
  3 months VXD commissioning very tight
Any further delay accumulated in L6 production must be absorbed in the VXD integration/installation phase

## Slide 51: L6 schedule risk and mitigation stragegy
L6 critical schedule is determined by several elements
  Delay in the availability of components and start of assembly
  Marginality of manpower at IPMU
    Especially in terms of long-term availability of expert manpower
  Complexity and length of the L6 ladder assembly procedures
All aspects need to be addressed to mitigate the risk
  Great technical progress at IPMU, light at the end of the tunnel for the origamis.
    Reassess at the end the class B production (end of Feb)
  So far weak counter measures have been realized
    Need a stronger reaction from IPMUhire 2 HW postdocs
    Organize longer working hours and weekend/vacation activity
    Explore the possibility of a wide mobilization of the collaboration to provide manpower at IPMU
  Only little optimization of the procedures is foreseeable
    Explore the possibility of setting up a second production line

## Slide 52: Second L6 assembly line
In December 2015 Pisa was asked to explore the possibility to setup a second L6 assembly line
  A preliminary schedule for setting up the line is the following:
    Jig production, site qualification, prototypes (6-8 months): Oct 2016
    Class C/B production: November-December 2016
    Final qualification: End of 2016
  Several issues need to be resolved and understood
    funding and support from INFN
    preparation of the jigs and qualification of the site
    availability of class C sensors for prototyping
    compatibility with the FW/BW assembly and manpower in Pisa
Another possibility is to setup a second line at IPMU in the L4 assembly area once L4 is finished
  Need acceleration of L4 effort (injection of manpower required)
  Need full support from IPMU for jig reproduction
We ask BPAC for guidance in how to proceed to most effectively reduce the schedule risks for the overall SVD production

## Slide 53: Summary
Ladder assembly
  The Pisa, HEPHY and Melbourne sites are in production mode, TIFR and Kavli IPMU are almost there
  Need to make a transition into production mode
L6
  Great progress following the December review, very dim light at the end of tunnel
  However, we need to restore contingency in the L6 schedule as it poses a serious risk to the overall schedule ® BPAC input
Origami mass production
  Stopped due to blister formation in reflow step
  Mitigation plan exists – impact on the overall schedule is limited
Mechanics and commissioning
  We have seen nice progress in the development of the ladder mount procedure but unfortunately a milestone has been missed, resulting in ~3 months delay
Electronics
  FADC redesign is on schedule, V3 is will tested in the DESY April 2016 testbeam

## Slide 54: backup

## Slide 55: Keratherm foils
Manufacturer:
  Kerafol, Germany
Product family:
  Softtherm
  Thermoplastic elastomere
  Contains silicone oil
Originally foreseen material:
  Softtherm 86/125
  0.5mm thickness
  Color: red
Replacement candidate:
  Softtherm 86/235
  0.5mm thickness
  Color: yellow

## Slide 56: Temperatures before and after irradiation
 |  | Softtherm 86/235 (yellow, new) |  |  |  | 
 |  | end mount | apv guard | cooling | Δt | Δt
 |  | p | n | block | p | n
FW | normal | 13,3 °C | 20,4 °C | 6,1 °C | 7,2 °C | 14,3 °C
 | irradiated | 12,4 °C | 19,9 °C | 4,7 °C | 7,7 °C | 15,2 °C
BW | normal | 9,3 °C | 19,2 °C | 3,5 °C | 5,8 °C | 15,7 °C
 | irradiated | 7,4 °C | 18,2 °C | 4,2 °C | 3,3 °C | 14,0 °C
 |  | Softtherm 86/125 (red, old) |  |  |  | 
 |  | end mount | apv guard | cooling | Δt | Δt
 |  | p | n | block | p | n
FW | normal | 11,9 °C | 19,0 °C | 3,9 °C | 8,0 °C | 15,1 °C
 | irradiated | 8,7 °C | 17,2 °C | 4,1 °C | 4,6 °C | 13,1 °C
BW | normal | 10,7 °C | 19,7 °C | 4,9 °C | 5,8 °C | 14,8 °C
 | irradiated | 7,9 °C | 18,5 °C | 3,6 °C | 4,3 °C | 14,9 °C
Thermal properties of both materials are similar
No significant change due to irradiation
Ice water
APV guard (p)
Cooling block
APV guard (n)
Softtherm 86/235, BW, irradiated
Δt n
Δt p

## Slide 57: Measurement of softness
    Put 2 strips of Softtherm on granite table, placed Al plate on top
    Measured height of plate with CMM
    Put weight on aluminum plate (~2kg) and measured height of plate again
    Height difference shows the compression of the Softtherm
Deformation = Height difference | Softtherm 86/125 red, old type | Softtherm 86/235 yellow, new type
unirradiated sample | 71µm | 35µm
Irradiated sample | 6µm | 14µm
Old red Softtherm 86/125:
  Highly compressible at beginning but get much harder due to irradiation.
New yellow Softtherm 86/235:
  Less compressible, but stay more compressible after irradiation.

## Slide 58: Hybrid soldering (reflow+hand) option
Procedure at Saiden
  Prebaking + dry reflow (120 ℃ for 17 hours)
    Not at once, divided in some batches (for example 30 * 4)
    Bonding pads masked
  Kept in the desiccator
  Masking work
  Kept in the desiccator
  Second prebaking (120 ℃ 17 hours)
  Solder paste printing
  Reflow
  Visual inspection at KEK for blisters
  Hand soldering of connectors