## Slide 1: ALICE ITS Upgrade Status and Plans
Federico Ronchetti, INFN-LNF
ALICE ITS Meeting 27/09/2016
ITS News
Ongoing activities
2016 planning

## Slide 2: ITS Activities @ LNF Until EOY

## Slide 3: ALPIDE4 Tests on Preseries
5 chips 100krad work fine but as for ALPIDE3 threshold start to decrease (20%) proposal: relax threshold and irradiate again until 1 MRad is accumulated (how long does it take?)
2 chips up to 340 kRad: analog supply current down by x2 thresholds saturate at lower level:
  takes 1 year to go back try accelerated annealing by heating on some chips SEU x-section for periphery memory (same value found at PSI)
next week heavy ion test

## Slide 4: ALPIDE4 Tests on Preseries

## Slide 5: ALPIDE4 Tests on Preseries
ALPIDE pre-series chips
2+2 chips for HI tests
5 chips tested at 100 kRad
2 chips 350 kRad
10 available for testing: 21 total
ALIPDE production 3 weeks delay PPR, postponed 1 month -> 24th of October - end of October availability of modules is on critical path need to produce ALPIDE4 HICs (next weeks)
IB
1 alu-FPC available friday - monday
get batch with 4 FPC next week
OB
2 dummy modules produced, found some issues swissPCB
2 modules with working chips tue - wed

## Slide 6
Stave
Inner Detector Barrel
End wheel
End wheel
IB Service Half Barrel
Stave
2 Middle Layers
2 Outer Layers
Outer Detector Barrel
MFT
ITS OB
ITS IB
Cage
Inner Barrel
Outer Barrel
OB Service Half Barrel
EDR 3 May 2016
EDR 20 July 2016
EDR 20 July 2016
Service Barrels and Cage
3 Inner Layers
PRR Dec 2016
PRR Nov 2016
PRR Nov 2016
EDR Nov 2016
PRR Feb 2017
Detector / Service Barrel Mechanics EDR/PRR

## Slide 7: ITS Activities @ LNF Until EOY
Stave mechanical assembly (ED/DP/AR) Federico, Marco T, Pavel, Marco I, Massimo (2016) rest of the team entter training beginning of 2017
FPC-FPC welding tests Aldo, Luciano, Daniele, Alessandro …
Glass Dummy production Luciano, Daniele, Alessandro ….
Dummy alignment and gluing tests Emiliano, Alessandro, Daniele + selected operators from step 1
Stave mechanical assembly Emiliano, Alessandro, Daniele + selected operators from step 1
In parallel: preparation of the procedure documents (Daniele/Stefano)
Tentative

## Slide 8: Training on handling bar
Assembled stave
Stave Mechanical Assembly

## Slide 9: FPC-FPC Welding Tests

## Slide 10: FPC-FPC Welding Tests

## Slide 11: Module Dummy Tests

## Slide 12: Module Dummy Tests
+
+
+
+
Strategy is to use the glass dummy both for alignment and gluing tests

## Slide 13: Milestones
week | S Dry Assembly | Dummy HIC | S Assembly w/ DHIC | Note
39 | Federico, Marco (Dry) | Glass tiles at LNF | N/A | 
40 | Marco T, Marco I | Find Plexi base with marks | N/A | No Federico (CERN)
41 | Marco I, Marco T | Produce glass dummy prototype | N/A | No Daniele (CERN)
42 | Massimo, Marco I | Produce glass dummies | N/A | 
43 | Massimo, Marco T |  | N/A | No Daniele, Alessandro
44 |  | Align dummies | N/A | 
45 |  |  | N/A | No Federico, Valeria (AW)
46 | Federico, Pavel | Gluing tests | N/A | 
47 | Federico, Pavel |  | N/A | Validation with Torino
48 |  |  | Operators TBD | No Marco T (Test Beam)
49 |  |  |  | 
50 | 1 Stave assembled with glass dummies |  |  | 
51 | contingency |  |  | 
52 |  |  |  |