## DCH
WBS | Item | Required Man-months (2 years) |  |  |  | Manpower sources
|  | Phy | Eng | Tecn | Comp Prof | Phys | In1 | In2 | In3 | Miss | Eng | In1 | In2 | In3 | Miss | Tecn | In1 | In2 | In3 | Miss | ComProf | In1 | In2 | In3 | Miss
1 | DCH (TDR)
1.1 | External geometry optimization | 4
1.1.1 | Radius of inner cylinder | 1
1.1.2 | Length of DCH | 1
1.1.3 | Offset of DCH center | 1
1.1.4 | Shape of DCH end-plates | 1
1.2 | Cell geometry optimization (w/ or w/o cluster counting)
1.2.1 | Full simulation bkg occupancy vs. x/y/z | 3
1.2.1.1 | Tools (including validation, e.g. with BABAR) | ?
1.2.1.2 | Actual DCH studies | 3
1.2.2 | Performance studies (FAST simu) | 8.5
1.2.2.1 | Setup dE/dx in FastSim | 1.5
1.2.2.2 | Benchmark channels: momentum & dE/dx resolution | 5
1.2.2.2.1 | Setup tools | 2.5
1.2.2.2.2 | Actual DCH studies | 2.5
1.2.2.3 | stereo vs. stereo+axial | 1
1.2.2.4 | optimization of stereo angle | 0.5
1.2.2.5 | optimization of B field? | 0.5
1.2.3 | Garfield/Magboltz studies | 4
1.2.3.1 | spatial resolution vs. mixture | 2
1.2.3.2 | dE/dx resolution vs. mixture | 2
1.2.4 | Tests with prototypes
1.2.4.1 | Prototype construction |  | 2 | 2.5
1.2.4.1.1 | Design |  | 1
1.2.4.1.2 | Mechanics |  |  | 1
1.2.4.1.3 | Stringing |  |  | 0.5
1.2.4.1.4 | Electronics |  | 1 | 1
1.2.4.1.5 | DAQ | 0.5
1.2.4.2 | Laboratory tests | 29
1.2.4.2.1 | Measurement of gas mixture properties | 2
1.2.4.2.2 | Analysis software tools | 3
1.2.4.2.3 | Aging test | 3
1.2.4.2.4 | Cosmic Test | 12
1.2.4.2.4.1 | Laboratory operation | 6
1.2.4.2.4.2 | Data analysis | 6
1.2.4.2.5 | Test Beam | 9
1.2.4.2.5.1 | Set-up and operation | 3
1.2.4.2.5.2 | Data analysis | 6
1.3 | Mechanical structure |  | 12
1.3.1 | Structure design
1.3.2 | Mechanical Integration
1.4 | Electronics (w/ or w/o cluster counting) |  | 36
1.4.1 | Architecture
1.4.2 | HV distribution
1.4.3 | Front-End
1.4.4 | Trigger
1.4.5 | DAQ
1.5 | Gas System
1.5.1 | Design
|  | Phys |  | Physicist
|  | Eng |  | Engineer
|  | Tecn |  | Technician
|  | Comp Prof |  | Computing Professional
|  | In1,2,3 |  | Institutions contributing
|  | Miss |  | Missing Manpower
All numbers in man-months, under the hypothesis of two years for TDR preparation (2009-2010)
Note on C4: fnc: Uncertainty: this group of tasks requires interaction with other subdetectors and some tools from the DGWG
Note on C12: fnc: - Large uncertainty: depends on number of iterations needed with Background Group. - This estimate is made only considering occupancy studies: a more sophisticated analysis, involving the time structure of background hits, requires more work.
Note on C21: fnc: To be better quantified By Gocha et al.
Note on C32: fnc: To be better quantified by Mike et al.
Note on C35: fnc: Time needed to analyise cosmic ray data, assumed ~ continuous data taking in 2009-2010
Note on C36: fnc: Laboratory operations: data acquisition, check/adjustement of runnig conditions, bookkeeping, etc. Assume ~ continuous cosmic ray data taking in 2009-2010
Note on C37: fnc: Time needed to analyise cosmic ray data, assumed ~ continuous data taking in 2009-2010
Note on C38: fnc: Assuming 3 beam tests of ~7-10 days between 2009 and 2010
Note on D41: fnc: My guess. Still need to talk to the mechanical Engineer at LNF
Note on D44: fnc: Estimate does not include R&D for cluster counting, probably 12mm more