## Slide 1: Towards Pixel TDR
P. Morettini

## Slide 2: Which detector we want to build?
LTF recommendations on module placement strategy are almost ready.
For the inner layers inclined is the preferred solution. For outer layers, no big difference between the two options in terms of performance.
In the next two months, we will have to define a preliminary design of the local support, implementing LTF indications, to use in the TDR.
Around this design we will develop a coherent view of module connections, integration, services and data transmission.
The responsibilities of the different institutes, the cost, the schedule and the production strategy will be defined around this design.
LTF
recommendation
Discussion in the engineering and sim community
Initial design of the local supports in the TDR

## Slide 3: How many modules?
Fully inclined | 
Layer 0 | 936 FE
Layer 1 | 2016 FE
Layer 2 | 3200 FE
Layer 3 | 4752 FE
Layer 4 | 6264 FE
Rings | 
Layer 0 | 3264 FE
Layer 1 | 5472 FE
Layer 2 | 6144 FE
Layer 3 | 7680 FE
Extended barrel | 
Layer 0 | 1920 FE
Layer 1 | 3840 FE
Layer 2 | 4608 FE
Layer 3 | 6336 FE
Layer 4 | 7776 FE
Still not clear how many points are needed for high-eta tracking. Should be able to reduce the number of rings.
Total | 22560 FE
Total | 24480 FE
Total | 17168 FE
14-16 m2 of silicon
7/8 times the existing detector

## Slide 4: A possible layout
This is a sketch of a possible Pixel layout, with hypothetical number of modules and cost.
Inner section
Barrel
Endcap 1
Endcap 2
L4
L2/L3
#FE
7718 (21.5%)
Core value
8.4 M (19.1%)
#FE
7718 (21.5%)
Core value
8.4 M (19.1%)
#FE
6216 (17.3%)
Core value
9.1 M (20.7%)
#FE
6264 (17.5%)
Core value
7.2 M (16.3%)
#FE
7952 (22.2%)
Core value
9.8 M (22.2%)
UK
US
+
Italy/Spain
Germany, Switzerland, France
Italy
+
Japan

## Slide 5: Decision path
Local support and services optimization
LTF
recommendation
Discussion in the engineering and sim community
Initial design of the local supports in the TDR
ATLAS FE chip
design
Module design optimization
Module pre-production
Specification reviews
(FE, sensor, mod, readout, services)
Sensor & BB
market survey
Readout and
services design
CMOS demonstrators
evaluation
CMOS project
Definition
(technology, goals)
2018
2019
CMOS module
development
Decision
TDR
2017
Preliminary design reviews
Specifications reviews

## Slide 6: Reviews calendar
Topic | Spec review | PDR | FDR | PRR | Comments
Local supports | Q4 2016 | Q2 2017 | Q1 2019 | Q1 2020 | Preliminary design in the TDR
Sensor | Q4 2016 | Q2 2017 | Q2 2018 | Q4 2019 | Preliminary design in the TDR
FE chip | Q4 2016 | Q3 2017 | Q1 2018 | Q4 18-Q3 19 | Preliminary design in the TDR
CMOS | Q4 2016 | Q4 2017 | Q3 2018 | < Q2 2020 | Conceptual design in the TDR
Bump bonding | Q1 2017 | Q2 2017 | Q4 2018 | Q4 2019 | 
Module | Q1 2017 | Q2 2017 | Q4 2018 | Q4 19-Q3 20 | Preliminary design in the TDR
Power distribution | Q1 2017 | Q3 2017 | Q1 2019 | Q1 2020 | Preliminary design in the TDR
Data transmission | Q1 2017 | Q3 2017 | Q1 2019 | Q1 2020 | Preliminary design in the TDR
Specification are the key to keep the TDR coherent around a well defined detector concept.
Reviews circled in red are strictly correlated and should be done together. This means 3 reviews in Q1 2017.
Some of the PDRs could in fact go after the TDR to reduce the load next year, even if we want a conceptual design of all the component ready for the TDR.

## Slide 7: Important questions to answer ~now
Maximum dose: 3000 or 4000 fb-1?
  This is a key parameter, that defines local support design and sensor technology. We could design the inner section for 2000 fb-1 (assuming one replacement) and the rest for 3000 fb-1 with a safety margin of 1.5.
Data rates: updated values from Step 1.6 sim.
  The first section of data transmission is on copper and it is challenging, as we aim for 5 Gb/s over 5-6 meters. Ad-hoc design of transmitter (FE chip) and receiver (opto-converter) is needed.
CMOS: still several options open.
  Must converge by April to a single proposal, providing a clear indication of possible benefits for ITk. The most interesting solution at the moment seems to be a 5th layer made with monolithic CMOS (advantages in cost and production simplification).
Schedule: must provide a detailed schedule by March AUW.
  Need to define the production model (how many module production and module loading centers, where). Must understand the integration sequence, to exploit the overlap between production and integration to increase the time we have to produce modules (24-30 months).

## Slide 8: Production schedule

## Slide 9: Cost estimates
Layout | # mod | Surface | Layer 0-1 | Layer 2-3 | Layer 4 | Rings | Total
Base (Scoping Document) | 9780 | 14.14 | 7.4 | 11.5 | 8.9 | 14.1 | 43.1
Extended | 12240 | 17.88 | 7.4 | 12.4 | 8.3 | 25.2 | 54,4
Fully Inclined | 12486 | 15.10 | 4.9 | 9.8 | 7.2 | 25.2 | 48.3
Estimates based on Step 1.5 layouts. For the real detector, we assume we can save ~5M by reducing the number of space points in the very forward region.
More savings are expected in bump-bonding and sensors.
Our present indication is in he range 40-45 M.
We expect to produce an updated estimate in April, for a candidate TDR layout and with updates sensors, bump-bonding and services costs.

## Slide 10: Contributions to the TDR
RD53A chip will be submitted in April ( June). Back in June ( August). We should be ready to assemble and test 3D modules with RD53A. This implies work in several domains:
  Sensors production/testing.
  Readout fw/sw (look at short term solutions and contribute to long term test systems for production).
  Module interconnections, support cards.
  Test beams, irradiations.
Bump-bonding qualification (Selex  Leonardo).
  Test 12 inch indium bump deposition on test wafers.
  Qualify Leonardo as a possible bump-bonding vendor.
Participate to end-caps local support development.
  Several possibilities: flex design, carbon structure, thermal and mechanical performance validation (simulation and samples), PP1 area design, power distribution and control.
  There could be a synergy with other (stave based) system tests planned at CERN and elsewhere.
  Possible cooperation with CAEN on serial power.