## Slide 1: Update on the SVD construction
Ladders
End rings
Carbon fiber (CF) cone
End flange
PXD (independent sub-detector inside SVD)
Outer CF shell
Beam pipe
S. Bettarini on behalf of the SVD-Group
7th Belle II Italian Coll. Meeting, 05/05/2017 Trieste

## Slide 2: Outline
Layer 4,5,6 Ladder production status
  FW modules: (PF1) peel-off issue
Layer3 cooling improvement
SVD Ladder mount:
  Cooling-pipes mounting
  Fibers insertions (see LL)
A look at the activities in 2018:
  Commissioning; Integration SVD/PXD; Cosmics run

## Slide 3: SVD ladders
L6 Ladder (Kavli IPMU)
L5 Ladder
(HEPHY)
L4 Ladder (TIFR)
L3 Ladder (Melbourne)
FWD module
BWD module
Origami +z
Origami ce
Origami -z
BWD
FWD
Cooling pipe
Cooling pipe
Cooling pipe
BWD module (Pisa)
FWD module
(Pisa)
Layer | Ladders (spares) | DSSDs / ladder
6 | 16 (4) | 5
5 | 12 (3) | 4
4 | 10 (2) | 3
3 | 7 (2) | 2
47 FWD + 47 BWD

## Slide 4: SVD Ladder Construction (I)
In 2016 Pisa completed the production of the needed 47 BW + 47 FW subassemblies. Prod. Line kept active in 2017:
  To feed the ladder assembly sites with the spare
  subassemblies needed for replacement in case of failures
  So far built extra +1 BW and +7 FW (Class B det’s!)
  A production of extra +4 BW needed before July
Origami production issue totally overcome: a sufficient number of tested class A origami circuits is now in our hand for ladder assembly.
Layer 6 assembly is on the critical path in the schedule.
  The L6 team (reinforced by an expert from Pisa) has implemented a shift system to use the assembly line at IPMU most efficiently: 1 ladder/21 days; in this way the global schedule (ladder mount) is matched but with very limited contingency.
FADC readout system
  FADC v3 has performed well at the test-beam in DESY in April 2016
  There are delays in v4 preparation

## Slide 5: SVD Ladder Construction (II)
Layer-3 : already completed the production with spares
Layer-4 :
Layer-5 :
Layer-6 :

## Slide 6
Unexpected failure after reinforcement!
Last week a L4 ladder experienced
a PF1 peel off, developed 6 days
after the half ladder assembly!
The failure mode indicates a glue
adhesion problem, and just adding
more glue is not enough.
Proposed a change in the assembly
procedures: the SFW glued is left on the ribs for about a week before
proceeding with the ladder assembly.
The whole SVD group is at work to find a definitive solution.

## Slide 7: SVD Milestones
Item/Operation | Updated in April 2017
Completion L4 production (10+2) | Oct 2017
Completion L5 production (12+3) | Sep 2017
Completion L6 (enough for the 1st shell) | Dec 2017
Completion L6 production (16+4) | Mar 2018
Ladder mount (1st half shell) | Aug 2017- mid. Dec 2017
Ladder mount (2nd half shell) | mid. Dec 2017 – mid. April 2018
SVD ready for integration with PXD | End of April 2018
The SVD Group produced a detailed Gant Schedule that is monthly updated taking into account the delay caused by the most important issues met along the path…
For instance …
FWD end-ring re-production
(QA failure at the Welcon)
A scratch on the component
(overlooked during the
production) caused a leak in
the cooling circuit.

## Slide 8: L3 cooling improvement (Melbourne)
Operation of the thermal mockup @ DESY indicated that the cooling of the APV chips on the L3 hybrids is marginal.
p-side APV chips in the FWD are ~70 °C above the coolant temperature, mainly due to the large temperature drop on the stainless steel FWD end-ring finger (45 °C)
L3 cooling is reinforced by adding copper inserts on the L3 fingers both in the FWD and in the BWD (Tmax decreases by ~30 °C)
Stress relief
Stress relief
Vacuum
Endring support
Gluing jig
Gluing support
Gluing station
Setup in Melbourne
The gluing of the copper inserts is foreseen before the June B2GM
Copper Insert

## Slide 9: Ladder Mount
Ladder pick-up and mounting
FOS fiber insertion (TS)
Cooling pipe positioning (PI)

## Slide 10: Cooling-pipe mounting (Pisa responsibility)
In the reharsal of Febr. We decided to modify the L4-pipe routing to allow its easy mounting.
It has been important to have at home a mock-up of the mounting table where to test the mechanical tools and the procedures:
The next step is just the next week when the pipe-mounting for the Layer4-5-6 and the L3-cover will be tested: work to be done with the Trieste group to test also the
fiber insertion.
The last dressed reharsal of the complete ladder mounting procedure scheduled before the June B2GM

## Slide 11: Main SVD Activities in 2018
The activities on beast2 (see LL’s talk) are also a useful exercise in preparation for the final SVD commissioning …, including the challenge of the tracking (ROI,...) on the SVD cartridge (Jan 2018)
2nd half SVD Ladder mount (first 4 months)
  SVD Commissioning, not yet completely defined in details, but foreseen:
    SVD standalone Cosmics data
    Integration with PXD
    Combined SVD/PXD Cosmics
    Installation VXD in Belle2
Cosmic Run before the Physics Run
A lot of exciting work @ KEK! Good opportunity for young people (free of teaching constraints) who gained expertise during the SVD module construction ...