## Slide 1: ITS Upgrade Activity at Frascati
Federico Ronchetti INFN-Laboratori Nazionali di Frascati ALICE Meeting 14/03/2017

## Slide 2: Outline
Status
Infrastructure
Tools
Soldiering procedure and stations
Mechanical ”Stave-0” assembly
ALPIDE test setup  (Marco, Pavel, Paula)
Meetings
Preparing for production
Computing: cluster installed with CentOS 8, batch system ongoing
ALICE Collaboration News

## Slide 3: Infrastructure
White and Grey Rooms were cleaned
Vacuum for HS base, HB, grippers:
  Two pump system being activated
  Pressure gauge: installed
  T-junction tube: to be installed
  … then electrical setup
CMM compressors:
  Still issue with ATLAS-CORP machine (Technical Division contacted)
  Secondary line still missing (filter and dryer)
  Need to clear safety protocol (Technical Division contacted)
ASTRA 11 kW conditioning system:
  Replacement with 25 kW system being prepared (inspection with TD today)
Primary
Secondary

## Slide 4: Infrastructure

## Slide 5: Mechanical Stave Assembly
Tools coming in
Back from Torino/SEL
  1 jig
  2 Half Stave stainless steel Bases
  1 reworked gluing mask positioner
  1 cross-cable compatible Handling Bar
    Final handling bar coming later (~mid April)
  C- brackets masks to be glued for the ruby pads (need Torino assistance) for Space Frame placing
  Power bus soldering jig (for gray area  relocate ALPIDE test station)
  2 Ecobond cartridges in from CERN
Tab cutting tool from Nikhef
PB jig

## Slide 6: Tab Cutting Tool
FPC extension cutting
Rough positioning (0.2mm) of module
with 5 dowel pins in module gripper
2
1
3
4
5
Considerations:
The cut has to be within 100 μm from the silicon
  Fine positioning needed
The FPC is flexible
  needs to be clamped close to the cut
  Need to fix the FPC not the Silicon
  Flipping of the module is required

## Slide 7: Tab Cutting Tool
Alignement of HIC
2 mm view around both edges of silicon
We align the shadow of the knife wrt the silicon
Silicon
Metalized
Kapton
0.55 mm
window
Copper removed in new design

## Slide 8: Tab Cutting Tool
50 um

## Slide 9: Tab Cutting Tool

## Slide 10: Soldering
Half Stave
New FPC-FPC interconnection structures received from Torino to be tested at LNF
EDSYN Sn62Pb36Ag2 ø=0.35 mm T= 183˚C wire (2reels) available
Power Bus
Chiller setup: detailed cooling loop design from Torino
Torino

## Slide 11: Half Stave Soldering and Test
Microscope
Half Stave Base
LNF
Microscope (M60) is fixed (heavy and has cables to screen)
HS base moves
Need a 3000 mm jig which would rest on a non-rectified table
Torino
Microscope is movable (on both sides of the table)
HS is fixed
Need a custom rectified table
Note: Torino has two microscopes:
For soldering Leica MZ6 binocular microscope FoV: 50°
M60 used only for visual inspections

## Slide 12: Outline of Stave Construction and Test Procedure
Each HIC is tested for power and readout
Tab is cut
HIC is re-tested for power
HIC is positioned on CP and lowered on glue
HIC is tested for power, if fails HIS is removed immediately before glue polymerizes
Repeat for 6 HICs
Type B HIC (with long tab) is glued and tested, if fails, removed
HS ready for soldering station
HS FPC-FPC interconnections are soldiered
HS is tested on the soldering table for power (need ad hoc service Power Bus, no cooling)
If a HIC is not fully connected, rework the missing/bad soldering
HS is moved to back to CMM table for flipping with Handling Bar
HS is aligned to SF and glued
Second HS construction starts (repeat 1-13)
Completed Stave moved to PB jig in Gray area
PB is soldered
Stave is tested with cooling for power and redout
Power Busses are folded over
Stave is re-tested for power

## Slide 13: LNF Expected Production Rate
108 Outer Layer Stave to be produced (1 Stave = 2 HS)
4 production sites (LNF, To, Liverpool, Nikhef)
For LNF the nominal is 27 staves: assume 24-31 with contingency
Production is by lots. LNF lots (nominal)
September 1, 2017  November 20, 2017  6 Staves
November 21, 2017  February 27, 2018  7 Staves
February 28, 2018  June 5, 2018  7 Staves
June 6, 2018  September 11, 2018  7 Staves
Note: the beginning of the above schedule could drift to October/November 2017

## Slide 14: Possible Production Shifts Scenario
Discussed with LNF director
Identification of X and Y ongoing
Note: we have 2 Half Stave Bases: in principle assembly work could be parallelized
However this will not match the manpower availability

## Slide 15: Mechanical Stave-0 at LNF
Request to our group from CERN to build a realistic stave for vibrational and bending tests
Use of realistic dummy HICs with bonded pad chips with tabs
Soldering would be needed
In principle should be ready for the PRR on April 27, however its likely that the PRR will be delayed
Material procurement
CP + SF: delivery at CERN March 20th
Modules: availability of 14 dummy modules of defines the stave assembly start date
FPC-FPC interconnection Bridges: available in LNF, being tested on dedicated test structures. More will be sent in the next days
PB: ?? do we foresee assembly of dummy stave with real PB ?? – no cooling probably
Vibrational test: Corrado alerted SERMS, Stave box needed to ship the Stave to Terni (INFN carrier)
Bending test: will take place at CERN, shipping from SERMS to CERN must be arranged

## Slide 16: Mechanical Stave-0 at LNF
 |  | March |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | April |  |  |  | 
 |  | 10 |  |  | 13 |  |  |  |  |  |  | 20 |  |  |  |  |  |  | 27 |  |  |  |  |  |  | 3 |  | 
 |  | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed
COLD PLATE AND SPACE FRAME |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Production at CERN: DONE | Corrado/Elisa |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Parylene coating | Company |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Delivery at CERN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Delivery to LNF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Metrology | LNF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLUING TOOLS |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mask printing (14+4spares) | Silvia |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Mask delivery to LNF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
GLUE, Spatula, glue dispenser, needles preparation | LNF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TAB cutting tools |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TAB cutter production | NIKHEF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TAB cutter test at LNF | LNF+NIKHEF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
ASSEMBLY TOOLS finalization |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stainless steel tools delivery |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Assembly and metrology | LNF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
CMM Software |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS assembly | Fabrizio |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Stave assembly | Fabrizio |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Migration to LNF | Fabrizio/Emiliano |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 17: Mechanical Stave-0 at LNF
 |  | April |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
 |  |  |  | 3 |  |  |  |  |  |  | 10 |  |  |  |  |  |  | 17 |  |  |  |  |  |  | 24 |  |  |  | 
 |  | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri
DUMMY STAVE ASSEMBLY (needs dummy modules) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
TAB cut | LNF+Nikhef |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS_0_R assembly | LNF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS_0_R FPC-FPC interconnections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS_0_L assembly |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS_0_L FPC-FPC interconnections |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS_0_R gluing to SF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
HS_0_L gluing to SF |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Power Bus soldering |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
STAVE 0 MECHANICAL CHARACTERIZATION |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Vibrational test | SERMS (Terni) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Bending test | CERN |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 18: Outer Layer Workshop at LNF
Only possible date is second part of May (from Luciano Musa, who supports the proposal)
30-40 people max
Organization load would go mostly on Alessandra and Lia (if they are available)

## Slide 19: ALICE Collaboration News
New elected Management Board member at the last CB

## Slide 20: Backup