## Sheet1
Categoria | Sub-Item | Sub-sub-item | WBS | # elementi | unità | Inizio pre-prod | Fine produzione | Note | Bologna | Cosenza | Genova | Lecce | LNF | Milano | Trento | Udine
Modules (1)
| Sensori 3D |  | 2.1.1.2 | 896 | modulo | 2019-05-01 | 2022-07-01 | Assunzione: layer 0, dove assumiamo ci siano sicuramente 3D. Sono moduli singoli. Va aggiunto 15% di pre-prod. In realtà però una metà dei 3D verranno fatti in Spagna. Potremmo voler aggiungere planari o mettere altri 3D sui rings interni. |  |  | Y |  |  |  | Y | Y (design)
| BB |  | 2.1.3.1 | 896 | mobulo | 2019-09-01 | 2022-08-01 |  |  |  | Y |  |  | Y (da definire) | Y (BB mask)
| Flex module |  | 2.1.3.2 | 896 | modulo | 2019-05-01 | 2022-07-01 |  |  |  | Y, if useful for 3D |  |  | Y (recente esperienza in produzione flex per LHCb)
| assembly |  | 2.1.3.3 | 896 | modulo | 2019-10-01 | 2022-11-01 |  |  | (disponibilità camera bianca, funzionalità da ripristinare) | Y |  |  | Y (disponibilità camera bianca e automatic bonding machine, ora usata per un programma di 800000 wire bond per LHCb)
| QA |  | 2.1.3.4 | 896 | modulo |  |  |  | Y (da definire) | Y (3D, setup da allestire) | No, we will built the setup as backup |  |  | Y (a seconda delle necessità) | Y (solo 3D, a seconda delle necessità) | Y (camera pulita, camera climatica, USBPix2)
| DAQ |  | 2.1.9.1 2.1.9.2 | [5 empty] | Electronic Boards e supporto |  | Y |  |  |  |  | Y
Half Rings
| struttura meccanica |  |  |  |  | 2020-04-01 | 2021-04-01 |  |  |  | Y, to be better defined | ditta CETMA |  |  |  | Y (to be better defined)
|  | carbon | 2.1.5.1.2 | 52 | half-ring | 2020-01-01 | 2020-07-01 | Nuovo layout; in quello Step 1.6 sono 102 |  |  |  | ditta CETMA |  | Y (design and FA, machining to be discussed)
|  | cooling pipe | 2.1.5.2.2 | 52 | half-ring | 2020-01-01 | 2020-07-01 |  |  |  |  | ditta CETMA |  | Y (design and FA, production possible) |  | Y (design of on-detector cooling)
|  | foam |  | 52 | half-ring | 2020-01-01 | 2020-07-01 |  |  |  |  | ditta CETMA |  | Y (design and FA, machining to be discussed)
| Type-0 |  | 2.1.4.1.2 | 52 | half-ring | 2020-04-01 | 2020-12-01 |  |  |  | Y |  |  | Y (recente esperienza in produzione flex per LHCb)
| EoS card |  | 2.1.4.2.3 | 52 | half-ring | 2020-04-01 | 2020-12-01 |  |  |  | Y
| assembly |  |  | 52 | half-ring | 2020-04-01 | 2021-04-01 | [6 empty] | Y
| QA |  |  | 52 | half-ring | 2020-04-01 | 2021-04-01 |  | DAQ e supporto | Y (caratterizzazione meccanica, termica) | Y Thermal, mechanics |  |  | Y |  | Y (thermomechanical characterization)
Module Loading (2)
| loading |  | 2.1.5.3.2 | 2472 | modulo | 2020-12-01 | 2022-12-01 | Nuovo layout; in quello Step 1.6 sono 4824 |  |  | Y | Y no integration | Y CMM esistente | Y (if needed, in such case reduction on activity on modules)
| QA |  |  | 52 | half-ring | 2021-01-01 | 2022-12-01 |  | DAQ e supporto |  | Y | Y no integration | Y | Y (if needed, in such case reduction on activity on modules)
| System test |  |  |  |  | 2017-05-01 | 2022-12-01 |  |  |  | Y |  | Y | Y (if needed, in such case reduction on activity on modules) |  | Y
Type-1 Services
| Cooling distribution |  | 2.1.4.3 | 6 | half-shell | 2022-06-01 | 2022-09-01
| Eletrical services |  | 2.1.4.4 2.1.4.5 | 6 | half-shell | 2022-06-01 | 2022-09-01 | [5 empty] | Y
| PP1 design |  | 2.1.4.8 | 1 | panel | 2018-01-01 | 2019-12-01
Integration
| preparazione half shell |  |  | 6 |  | 2022-01-01 | 2022-05-01 |  |  |  |  | Y no loading |  | Y (design and production with external firm, if needed)
| montaggio half ring |  |  | 52 | half-ring | 2022-09-01 | 2023-03-01 |  |  |  |  | Y no loading | Y (spazi e supporti logistici) | Y (production and design of tooling, experience with the pixel integration tool)
| QA |  |  | 6 | half-shell | 2022-09-01 | 2023-03-01 |  | DAQ e Supporto |  |  | Y no loading | Y
| integrazione half shells |  |  | 6 | half-shell | 2023-06-01 | 2023-07-01 |  |  |  |  | Y no loading | Y
Shipment
| end-cap to CERN |  |  | 1 | end-cap |  | 2023-03-01
NOTE
(1) max 2 laboratori coinvolti (non si applica per QA)
(2) max 2 laboratori coinvolti