## DCH
WBS | Item | MANPOWER SOURCES
|  | Phy | Eng | Tecn | Phys | LNF | NA | Can. | Miss | Eng | LNF | NA | Can. | Miss | Tecn | LNF | NA | Can. | Miss
1 | DCH (TDR) | 104 | 38 | 20.5 | 48 | 44 | 0 | 4 | 56 | 22 | 15 | 7 | 0 | 16 | 11.5 | 11.5 |  |  | 9
1.1 | External geometry optimization | 10 | 0 | 0 |  | 7
1.1.1 | Radius of inner cylinder | 2
1.1.2 | Length of DCH | 2
1.1.3 | Offset of DCH center | 2
1.1.4 | Shape of DCH end-plates | 4
1.2 | Cell geometry optimization (w/ or w/o cluster counting) | 69 | 2 | 12.5 |  | 36 |  | 4 | [7 empty] | 11.5
1.2.1 | Bkg occupancy vs. x/y/z | 12 | 0 | 0 |  | 1.5
1.2.1.1 | Tools (including validation, e.g. with BABAR) | ?
1.2.1.2 | Actual DCH studies | 12 |  |  |  | 1.5
1.2.2 | Performance studies (FAST simu) | 11.5 | 0 | 0 |  | 8
1.2.2.1 | Setup dE/dx in FastSim | 1.5 |  |  |  | 1.5
1.2.2.2 | Benchmark channels: momentum & dE/dx resolution | 5 | 0 | 0 |  | 4
1.2.2.2.1 | Setup tools | 2.5
1.2.2.2.2 | Actual DCH studies | 2.5
1.2.2.3 | stereo vs. stereo+axial | 3 |  |  |  | 2
1.2.2.4 | optimization of stereo angle | 1 |  |  |  | 0.5
1.2.2.5 | optimization of B field? | 1
1.2.3 | Garfield/Magboltz studies | 4 | 0 | 0 |  |  |  | 4
1.2.3.1 | spatial resolution vs. mixture | 2 | [5 empty] | 2
1.2.3.2 | dE/dx resolution vs. mixture | 2 | [5 empty] | 2
1.2.4 | Tests with small prototypes | 41.5 | 2 | 12.5 |  | 26.5 | [9 empty] | 11.5
1.2.4.1 | Prototype construction (1 table-top prototype) | 1.5 | 2 | 2.5 |  | 1.5 | [9 empty] | 2.5
1.2.4.1.1 | Design | 1 | 1 |  |  | 1
1.2.4.1.2 | Mechanics |  |  | 1 | [11 empty] | 1
1.2.4.1.3 | Stringing |  |  | 0.5 | [11 empty] | 0.5
1.2.4.1.4 | Electronics |  | 1 | 1 | [11 empty] | 1
1.2.4.1.5 | DAQ | 0.5 |  |  |  | 0.5
1.2.4.2 | Laboratory tests | 40 | 0 | 10 |  | 25 | [9 empty] | 9
1.2.4.2.1 | Measurement of gas mixture properties | 4
1.2.4.2.2 | Analysis software tools | 3 |  |  |  | 3
1.2.4.2.3 | Aging test | 3 |  | 2 |  | 1 | [9 empty] | 1
1.2.4.2.4 | Cosmic Test | 12 | 0 | 4 |  | 12 | [9 empty] | 4
1.2.4.2.4.1 | Laboratory operation | 6 |  | 4 | [11 empty] | 4
1.2.4.2.4.2 | Data analysis | 6
1.2.4.2.5 | Test Beam | 18 | 0 | 4 |  | 9 | [9 empty] | 4
1.2.4.2.5.1 | Set-up and operation | 6 |  | 4 | [11 empty] | 4
1.2.4.2.5.2 | Data analysis | 12
1.3 | Mechanical structure | 12 | 12 | 0 |  | 1
1.3.1 | Structure design | 11 | 9 |  |  | 1
1.3.2 | Mechanical Integration | 1 | 3
1.4 | Electronics (w/ or w/o cluster counting) | 12 | 24 | 8 | [6 empty] | 15 | 7
1.4.1 | Architecture
1.4.2 | HV distribution
1.4.3 | Front-End
1.4.4 | Trigger: include axial+stereo vs all stereo
1.4.5 | DAQ | [10 empty] | 7
1.5 | Gas System | 1 | 0 | 0
1.5.1 | Design | 1
|  | Phys |  | Physicist
|  | Eng |  | Engineer
|  | Tecn |  | Technician
|  | Comp Prof |  | Computing Professional
|  | In1,2,3 |  | Institutions contributing
|  | Miss |  | Missing Manpower
All numbers in man-months, under the hypothesis of two years for TDR preparation (2009-2010)
Institutions:
LNF
NA
Can.
Note on C4: fnc: Uncertainty: this group of tasks requires interaction with other subdetectors and some tools from the DGWG
Note on C12: fnc: - Large uncertainty: depends on number of iterations needed with Background Group. - This estimate is made only considering occupancy studies: a more sophisticated analysis, involving the time structure of background hits, requires more work.
Note on C32: fnc: To be better quantified by Mike et al.
Note on C35: fnc: Time needed to analyise cosmic ray data, assumed ~ continuous data taking in 2009-2010
Note on C36: fnc: Laboratory operations: data acquisition, check/adjustement of runnig conditions, bookkeeping, etc. Assume ~ continuous cosmic ray data taking in 2009-2010
Note on C37: fnc: Time needed to analyise cosmic ray data, assumed ~ continuous data taking in 2009-2010
Note on C38: fnc: Assuming 3 beam tests of ~7-10 days between 2009 and 2010
Note on C41: fnc: My guess. Still need to talk to the mechanical Engineer at LNF
Note on D41: fnc: My guess. Still need to talk to the mechanical Engineer at LNF
Note on D44: fnc: Estimate does not include R&D for cluster counting, probably 12mm more