## Slide 1: SVD Introduction & Ladder mount status
Belle II Italy Meeting – Nov. 21st Pisa
Ladders
End rings
Carbon fiber (CF) cone
End flange
PXD (independent sub-detector inside SVD)
Outer CF shell
Beam pipe
SVD session:
S. Bettarini
on behalf of the
Italian-SVD-Group

## Slide 2: On Nov. 18th the phase-2 VXD/BEAST detector installed into Belle II

## Slide 3: Ladder assembly
L6 Ladder (Kavli IPMU)
L5 Ladder
(HEPHY)
L4 Ladder (TIFR)
L3 Ladder (Melbourne)
FWD module
BWD module
Origami +z
Origami ce
Origami -z
BWD
FWD
Cooling pipe
Cooling pipe
Cooling pipe
BWD module (Pisa)
FWD module
(Pisa)
Layer | Ladders (spares) | DSSDs / ladder
6 | 16 (4) | 5
5 | 12 (3) | 4
4 | 10 (2) | 3
3 | 7 (2) | 2
47 FW + 47 BW

## Slide 4: SVD ladder production status
Ladder assembly is in its final phase: 3 out of 5 sites have completed their production:
  Pisa (FW/BW) Production completed – in total 60 class A FW and 55 BW subassemblies built
  Melbourne ( L3 ) Production completed – 11 good ladders available out of 7+2 ladders needed
  TIFR ( L4 ) 9 good ladders in hand, 3 more to build (expect to finish in Jan 2018)
  HEPHY ( L5 ) Production completed – 15 good ladders in hand
  Kavli-IPMU ( L6 ) 15 good ladders available, 5 more to go. Precisely on June 2017 B2GM schedule (end of production: second half of Feb 2018, consistent with the ladder mount schedule)
PF1 peel off problems have been addressed by “type 3” reinforcement and have not reappeared

## Slide 5: Threefold PF1 peel off mitigation strategy implemented by L4/L6 in June 2017
Staged assembly: FW sensor is glued first, assembly continues after 1 week wait (to minimize loss of sensors if peel-off happens)
Glue brace reinforcement: to secure the weakest corner (sacrificing one alignment mark)
Mylar strip with flaps (type 3): to mechanically push PF1/PF2 onto the sensor

## Slide 6: Ladder mount
Tools and procedures have undergone a series of technical reviews and were finally approved on Sep 5, 2017
LM has started; progress is behind the original schedule due to a number of issues on the L3
ladders; no issues are seen in the LM tools/procedures itself
+X (-X) half-shell is expected to be mounted by Jan (Apr) 2018

## Slide 7: Ladder mount tools
Mount tool
Protection cover and 3D measurement system
Cooling pipe attachment tool
Dry volume and CO2 system

## Slide 8: Ladder mount procedures
Helper/watcher
https://confluence.desy.de/display/BI/Process+Flow

## Slide 9: End of October: L4 completed!

## Slide 10: Brazing Issue

## Slide 11
Outcome of today 8 am SVD meeting…
SEM Investigation On brazing samples @UNIPI

## Slide 12
Readout electronics
FADC v4 has been produced and evaluated in the real Belle II environment at KEK; significant improvement in the noise performance is observed
Mass production has been started: half of the FADC system will be at KEK by end of Feb 2018; full system will arrive by mid Mar 2018
SVD Software
Online software is well on track for phase 2
Offline software is undergoing a refactoring to include important new features such as hit time determination; major effort is required to make it ready for phase 2