## Slide 1: QA and QC during Pixel Endcap Macro-assembly
Tim
5th April 2018
LNF Endcap Integration Meeting

## Slide 2: QA and QC
In general …
  QA is the process of making sure that the system should meet the design goals
  QC is the process of making sure that all the individual components of the system are up to specification
1 Endcap =
  = 6 half cylinders
  = 54 half rings
  180 SP chains
  1,000 modules
  3,000 data-links
Our accumulated knowledge tends to reflect our experience of QA/QC for large numbers of supposedly identical, relatively low-cost objects (eg. modules)
How do we deal with QA/QC for unique priceless deliverables ?

## Slide 3: Integration Model
I assume that all the services have been mounted onto the half-cylinder and checked before ring installation starts.

## Slide 4: Half-ring Insertion
Half-ring Reception Test
  Confirm that no damage had been sustained in transit.
    Visual inspection
    Perform a sub-set of the characterization tests on every module
  Duplicate the test system used to evaluate module performance after module mounting
Half-ring Installation
  Mount half-ring
  Weld half-ring cooling tubes to the on-cylinder pipework
  Connect the interface boards on the rings to the power tapes
  Connect the data links to each module
Functional test (in Serial Power tape groupings)
  Are all connections OK ?
    Low-power test modes
  Is there any damage to the half-ring ?
    Repeat of a sub-set of the characterization tests on every module

## Slide 5: Testing Complete Half-Cylinders
Full characterization the performance of each module at operating temperature.
  Mount half-cylinder in a dry enclosure and install into a temperature and humidity controlled room.
    Electrical and cooling services connections made to dummy interface panel on outside of dry enclosure to allow limited DAQ/PS system interconnects to be switched without opening
    Final ‘warm’ test to check all connections OK using low power operation modes
  Characterization of all modules at Tevap ≈ -35°C.
    Compare results to previous single-module and half-ring.
  Thermal cycle from RT to -50 °C a few times & re-test
    Cooling by pumping cold dry N2 gas into enclosure ?
  Need an enclosure design that can maintain DP < -60°C

## Slide 6: Half-cylinder Integration
Pairs of half-cylinders integrated together to form a complete cylinder and with the end supports
  No on-cylinder services (cooling, electrical services, etc) couple two half-cylinders together
    System-level autonomy should result in minimal interference between half-cylinders.
    Testing could be limited to that which picks up any interconnection errors.
    Issue might be what happens beyond Z=3.1m
During half-cylinder integration, the electrical services harnesses may need to be disconnected from their half-cylinder services supports and routed through apertures in the large-Z end-flanges.
  Check that none of these services have been damaged during their manipulation.
  Half-cylinder support frame design should allow a simple services transfer to minimise risk & need for re-re-re-testing
Test at room temperature
  Check one module per SP feed to check for connectivity.
  Check all modules return data (short-term power-on test)

## Slide 7: Final Test
Install full endcap into a dry enclosure & move into temperature & humidity controlled room.
  Electrical and cooling services connections made to dummy interface panel on outside of dry enclosure to allow limited DAQ/PS system interconnects to be switched without opening
  Final ‘warm’ test to check all connections OK
Services:
  Assume 10% of endcap DAQ/PS system at each site
  Cooling ?
Testing
  10% DAQ/PS availability limits scope of testing
  An endcap is roughly 60 half-rings so can look at different combinations of any 6 to check for proper functionality and possible interferences

## Slide 8: Transport & Reception Test
Transport (SCT endcaps)
  Very important to start design work early
    Significant engineering effort
    Integrated transport/test box with robust (temporary) services connections (PP1) accessible with minimal effort
  Verify with full trial shipment including all pack/un-pack, load/un-load and road transport steps
    Use the chosen shipping company
    Instrumentation
    Build the team
Reception Test
  Need to prepare an area with a copy of the infrastructure used during assembly before EC arrival
  Repeat final testing at assembly site to check all connections still OK before EC is removed from inner test box

## Slide 9: Summary
Manage QA/QC by understanding risks
Mitigate by considering system-level component design specifications
  Reliability during assembly & test
  Low-power tests for connectivity
  Simplicity
  Minimize subsequent work by thinking about complete EC life-cycle (i.e. until it is integrated into OC)
Develop robust, minimal-risk test systems
Optimise testing to be ‘just sufficient’ to guarantee success
  Half-ring reception test
  Half-ring connectivity after installation to half-cylinder
  Half-cylinder system test
  Full endcap system test
Establish staff training regimes that instil high level of professionalism