## Slide 1: Mu2e Calorimeter mechanics status of the design and parts realization
F. Happacher, A. Saputi
for the Calorimeter group

## Slide 2: status
We are going to undergo a Construction Readiness Review next July
The calorimeter mechanics design is almost final
  Need to check final tolerancies of crystals and Sipms
  Harmonize matching of all components
We built prototypes for all the parts
The most delicate task has been the realization of the cooling system for the SiPM and FEE.
We optimized it and tested with the module-0 and with dedicatet tests in vacuum (see Matteo and Fabrizio’s talks)
The assembly and integration of the calorimeter has been discussed and agreed upon with the Muon Beam line

## Slide 3: The Mu2e calorimeter view

## Slide 5
The calorimeter consists of two annuli each one composed of:
non chi comincia ma quel che persevera
FEE_Plate
SiPM holder
Crystals
n. 10 Readout elect . crates
Foot
Inner ring
Outer ring
Source_Plate
Manifolds
Hydraulic connections
Inner steps
Outer steps
Alignment targets
Calorimeter parts

## Slide 6: Prototypes
We have prototyped most of the mechanical parts of the calorimeter:
The feet
The outer cylinder
The inner CF cylinder
The crates and theyr cooling
The CF source plate
The FEE plate (module 0)
The FEE cooling circuit
The FEE holder

## Slide 7: Mock up activities
The prototyped outer cylinder didn’t have the stepped profile to arrange the crystals:
  We manufactured a monolithic stepped ring to insert in the outer cylinder
The CF inner ring also did not come with the stepped margin
  We 3D printed it @LNF
we now have this parts; we start piling up the iron fake crystals wrapped with Tyvek as soon as we assemble the two rings together.
Measure the alignment of crystals at every row
Build a front plate portion with the appropriate FEE apertures to check stacking tolerances

## Slide 9: Feet mock up

## Slide 10: Support rings
stepped margin

## Slide 17: Inner steps

## Slide 18: Survey of the geometry

## Slide 19: Crystal positioning survey

## Slide 20: Staggered stack

## Slide 21
non chi comincia ma quel che persevera
Detector assembly sequence
Step_2
Step_10
Step_4&6
Step_3
Step_5
Step_1
Step_7&8
Main assembly steps:
Outer ring
FEE plate (pre-assembled)
Crates (empty)
Crystals
Inner ring
Crystals
Alu sponge
Calibration source plate
EL boards
SiPM holders
Fibers (spheres, etc.)
Cables (LV connection)
The calorimeter components will be assembled using a workbench that allows also to move the calorimeter if needed.
The outer ring will be bolted on the workbench and all others components will be mounted on it.

## Slide 22: Services cables routing tray
1. red is the envelope of LV AWG 8 cables. ⦰ 40 mm.
2. yellow is the envelope of LV and HV AWG 12 cables. ⦰ 25 mm.
3. Green is the envelope of all HV AWG 22 cables. ⦰ 16 mm.

## Slide 23
Loop for recovering cables slack in/out when calo moves
No cable induced strain

## Slide 24
non chi comincia ma quel che persevera
Detector handling (Transport and installation tools)
Each disk will be transported and installed using the TI-frame.
The feet will be installed on the rails before the installation of the disk.

## Slide 25: Prototyping: Module-0
All the designed technology has been tested building a module 0 that implements all the choices of the actual calorimeter:
  Arrangement of crystals
  Cooling system
  Crate prototype
  FEE+Sipm housing
  Crystal wrapping

## Slide 26
non chi comincia ma quel che persevera
Module - 0
n. of crystals: 51
Fill Factor: ~81%
Total weight: ~70 kg
Overall sizes:
Dout= 356 mm
Depth = 226 mm

## Slide 27
non chi comincia ma quel che persevera
Module - 0
Al Cylinder
O-ring
Matrix
FEE_plate
Back_Plate
SiPM
+
FEE
Cylinder: INFN Lecce + INFN Padova
Back plate + base: INFN Lecce
FEE_plate: INFN Pisa
SiPM holders: INFN/LNF
Crystals wrapping: INFN/LNF
Assembly: all

## Slide 28: Al shell

## Slide 29: Preparation of wrapping: Tyvek folding (1)

## Slide 30: Preparation of wrapping: Tyvek folding (2)

## Slide 31: Crystal wrap: step-1, folding crystal in machine

## Slide 32: Crystal wrap: Step-2 .. Gluing of frames

## Slide 33: Crystal wrap: Step-2, gluing frames

## Slide 34: Crystal wrap: Step-3 Aluminum tape
After curing of frames on the Tyvek

## Slide 35: Preparation of wrapping: Crystal wrap

## Slide 37: Crystal wrap: final resut

## Slide 38: Module 0 FEE plate

## Slide 44: SiPM +FEE holder
New design for the Sipm+FEE holders
New prototype with more precise
production technique machining
The holder dimensions are customized
for the Hamamatsu SiPM.

## Slide 45: holder

## Slide 46
non chi comincia ma quel che persevera
SiPM & FEE holders
The holder houses the SiPMs, the FEE boards and fiber connectors.
The body of the holder is made of golden copper to achieve a good thermal conductivity and facilitate the gluing of the SiPMs.
It provides:
mechanical support for SiPM &FEE board;
heat exchange between SiPM and cooling circuit;
light-tightness;
faraday cage.

## Slide 47
SiPM & FEE holders: components
REG_Board
Faraday cage
SiPMs
Fiber optic connector
Holder
(copper+Au)
The SiPM are glued on the case (body)
The FEE is screwed
through a bridge resitor
Spacer
Screws
Fiber Guide
Closing Screw

## Slide 48
non chi comincia ma quel che persevera
Sipm holder: total cost
Parte | Q.ty | Prezzo unitario | Prezzo lotto
Body | 1650 | 15,50 € | 25.575 €
Fiber Guideline | 1650 | 0,45 € | 742,5 €
Closing screw | 1650 | 0,41 € | 676,5 €
Screws | 6600 | 0,37 € | 2442 €
Spacers | 3300 | 0,38 € | 627 €
 |  | TOTALE | 30.063 €
Gabbia di Faraday |  |  | 
ABS* | 1650 | 4,56 € | 7524 €
ASA* | 1650 | 4,59 € | 7573,5 €
Victrex@ Peek* | 1650 | 8,6 € | 14190 €
Alluminio imbutito | 1650 | 11,95 € | 19.717,5 €
Rame imbutito | 1650 | 12,32 € | 20.328 €
Alluminio pressofusione | 1650 | 18,6 € | 30.690 €
Stampa 3D – ASA** | 1650 | 18 € | 29.700 €

## Slide 49: additional costs to be sustained
SiPM holder
From the quotes in our hands, the overall cost of this component is estimated to be 60 kE
We hope that during the bids the costs will go down at least 10-15 %
Y adj
The Y adjustment mechanism has to be purchased, the cost is estimated to be 2250x4 =9 kE

## Slide 50: plans 2018
  Plan CRR in July 2018
The mock-up of a real size annulus is growing.
final designs for all the parts
Bids
  A tender is out for the purchase of the 2 Outer Al Cylinder
  We needed 14 kEuro extra to add stepped margin in the machining
  Tender in preparation for FEE plate – 10 kE extra cost
  FEE Cooling pipes machining 22 kE extra cost
  Divided in two: material and machining
  Tender in preparation for CF source plate, also in two parts.
  Feet and adjustment mechanism – LNF workshop
  2 annuli connection mechanisms – LNF workshop
  Assembly and lifting tools will be built @FNAL
  Changed manufacturing technique for SiPM + FEE holders
  we have now a first good prototype - assessing extra cost