## Slide 1: IDEA: The vertical slice Test Beam
R. Santoro

## Slide 2: IDEA Test Beam
Measurements:
  Particle Identification with:
    Drift Chamber Prototype (p, π, k) using dE/dx VS cluster counting
    Preshower + Dual Readout Calorimeters (e, π, μ)
    μRWell (e, μ)
  Preshower optimization studies
  Tracking qualification
  Qualification of a RD52 calorimeter with staggered fibers
  Qualification of a small calorimeter module readout with SiPM

## Slide 3: Setup schema
Trigger with 2 scintillators in coincidence + 1 veto (if needed)
2 DWC (Delayed Wire Chamber)
CEDAR (Differential Cherenkov detector)
Drift Chamber Prototype
Preshower with GEM: 2 layers GEM + absorber (0 – 2 X0)
Different Dual Readout prototypes
  RD52 calorimeter with PMT readout
  RD52 calorimeter with staggered fibers
  Small calorimeter module with SiPM readout
Muon chamber: 1 layer GEM + 2 layers μRWell
  The large scintillator usually used in the RD52 test beam will be also readout
RD52 Calorimeter
Preshower
Muon Chamber
DWC
Scintillators
280 cm
140 cm
50 cm
50 cm
Drift chamber
DWC

## Slide 4: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
RD52 calorimeter (already installed in the area)
Space for the drift chamber
Trigger + Delay Wire Chamber (DWC) already installed
Some space for the preshower
Control room: HNA – 468 (0887-1- Q70)
Space for the muon chamber
Gas systems

## Slide 5: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Control room: HNA – 468 (0887-1- Q70)
Place where to install the gas bottles (?? m from the detector)
ArCO2CF4: requested by preshower and muon chamber
He/Isobutene (90/10): requested by drift chamber

## Slide 6: Trigger and DaQ
Trigger based on scintillators in coincidence. It will be prepared in counting room and it will be delivered to all subsystems (expected delay 200 ns)
All subsystems are able to sustain 1kHz trigger rate with the exception of the drift chamber ( ??)
  Under investigation the possibility to record the number of the accepted trigger in the data header
3 different DaQ systems and Qas running in parallel
  Central (trigger, calorimeters, CEDAR and ancillaries detectors used the measure the energy leakage in the RD52 calorimeter)
  Preshower and muon chamber
  Drift chamber
1 Quasi on-line system (Tom Coates)
  Gets the data from each subsystem and displays the summary plots when the run is closed
  The data merging will be also tried during the test beam period
Test beam simulation (see talk from Lorenzo Pezzotti)

## Slide 7: Some general information
Access to the Area since August the 29th
  Free access with beam dumped upstream (beam dump before PPE168)
Safety inspection: September the 5th at 12:00
Alignment service: September the 5th at 14:00
Beam on: September the 5th at 18:00
Beam stop: September the 12th at 8:00
No machine development between us and the next users

## Slide 8: A preliminary plan (I)
Detector installation and qualification (from Aug - 29th to Sept. – 2nd)
System integration (from Sept – 3rd to Sept – 5th )
Beam on (Sept - 5th)
Calibration (1.5 days):
  RD52 calorimeter: calibration runs (60 GeV electrons)
    All modules calibrated with the absorber out
    Few modules calibrated with 1 X0 (or more?) of absorber in
  Drift Chamber: HV scan (60 GeV electrons)
  Drift Chamber: angle scan (60 GeV electrons)
    @ 2 – 3 angles (access to the area is needed to change the angle)
  Drift Chamber: Gas mixture test? (60 GeV electrons)
    It depends by the gas system (premixed or not), this is still something under discussion

## Slide 9: A preliminary plan (II)
Measurements with all systems (2.5 days)
  Energy Scan
    Drift Chamber request
      /k separation at different energies in the 6 – 60 GeV range
      10k and 10k kaons are requested at each energy
      CEDAR information available off-line
    Calorimeter request
      Energy scan with electron beams (6 – 60 GeV)
        and contamination is expected
      Energy scan with different absorbers (0 – 2 X0) to study the energy resolution degradation (6 – 60 GeV electron beam?)
      Energy scan with beam?
  Test in a multi-particle environment (target): under discussion

## Slide 10: A preliminary plan (III)
Tests with new calorimeters (2 days)
  Module with staggered fibres
    Calibration strategy (still under discussion)
    Test with electrons and pions
  Module with SiPM
    Ph-e / Gev measurement
    Cross-talk measurement

## Slide 11: Summary
The space available is good enough to install all subsystems
Each subsystem will come at CERN with his own support structure and it will be placed onto the platform / concrete block
The installation will start in Aug-29, 1 week before the beam time. This will allow us to test the system integration.
Quasi on-line and simulation is progressing. I’m always more convinced that they will have a crucial role for a successful test beam
I’ll start collecting the list of participant and the expected period they will spend at CERN for the test beam.

## Slide 12: Back up Slides

## Slide 13: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Control room: HNA – 468 (0887-1- Q70)
The space for the drift chamber
DWC
Trigger
1 m
Beam
46 cm

## Slide 14: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Control room: HNA – 468 (0887-1- Q70)
Drift chamber prototype
1 m
Beam
46 cm

## Slide 15: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Control room: HNA – 468 (0887-1- Q70)
1 RAC for the Drift chamber. Space available close to the detector is 50cm. It should be enough
  1 Crate Camac
  1 Crate VME
The HV module will be installed in the RAC used by the preshower + muon chamber
Drift chamber prototype

## Slide 16: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Preshower:
downstream the Drift chamber and just in front to the calorimeter
Control room: HNA – 468 (0887-1- Q70)
50 cm
1.26 m
Beam

## Slide 17: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Control room: HNA – 468 (0887-1- Q70)
Possible places where to install the calorimetric module with staggered fibres
RD52 Calorimeter:
already installed

## Slide 18: EHN1 – H8 – C (door 168, between ATLAS tile and Totem)
Space for the muon chamber downstream the calorimeter
Control room: HNA – 468 (0887-1- Q70)
2 m
1 RAC to install the electronics for the preshower and mu-chamber + HV power supply
Beam
1.26 m