## Slide 1: BTF/LINAC upgrade status
P. Valente
Acc. Div. Meeting, 15 Oct. 2018
What has been going on in the last months
Plans up to the end of PADME run-1

## Slide 2: PFN charging modulator upgrade
Installed on modulator D
2 weeks dedicated setup
Integrated with present control system
In operation from March 2018

## Slide 3: Timing system upgrade
New cooled rack for timing system
New RF source 4.5 us gated
  In operation
New phase shifter
  Installed in test setup
  More stable

## Slide 4: New modulator commissioning
All the components delivered in July 2018
Commissioning started
Progress slower than expected, since staff is busy with in the operation of DANE and SPARC linacs

## Slide 5: Control system upgrade
The new control system based on National Instrument modular electronics installed on Modulator B in «spy» mode.
  The FPGA DAQ run but does not control the modulator, only monitor it.
  Installed in October 2018

## Slide 6: BTF line splitting

## Slide 7: New BTF layout
DHRTB102 (PADME)
DHSTB02
QUATB04
QUATB03
DHPTB102
CHHVVTB03
SLTTB05
DHSTB201
DHSTB202
QUATB201
QUATB202
QUATB203
QUATB204
QUATB205
TGTTB02
BTF-1
BTF-2

## Slide 8
DHPTB102 (pulsatino)

## Slide 9: DHPTB102 (pulsatino)
15 Nov. ’17
5 Feb.
17 Apr.
29 May
11 Jun.
11 Jul. ’17
20 Jun.

## Slide 10: Dismantling & civil engineering

## Slide 11
DANE racks
Control room
BTF-2
DANE racks
BTF-1
BTF-1
Before
After

## Slide 12
21 Mar.
16 Mar.
14 Feb.
3 Apr.
6 Apr.
11 Apr.

## Slide 13
19 Apr.
30 Apr.
2 May
8 May
10 May
10 May

## Slide 14
11 May
18 May
17 May
29 May
7 Jun.

## Slide 15
22 Jun.
19 Jun.
26 Jun.

## Slide 16: Power, cooling, conditioning

## Slide 17
15 Jun.
19 May
14 Jun.
11 Sep.
Should be ready for new magnets

## Slide 18: BTF-1 installation and commissioning

## Slide 19
19 Jun.
5 Jun.
25 Jun.

## Slide 20
29 Jun.
26 Jun.
28 Jun.
2 Jul.
6 Jul.

## Slide 21
PADME setup
Target
Internal vessel
External vessel
Calorimeter
Small angle
Internal vessel

## Slide 22
30 May
27 Jun.
2 Sep.

## Slide 23
4 Jun.
13 Jun.
6 Jul.

## Slide 24
6 Sep.
14 Sep.
4 Oct.

## Slide 25: Beam restart

## Slide 26
Linac restart: 5 Jul.
Chicane rebuilt: 10 Jul.
BTF-1 first beam: 12 Jul.

## Slide 27
200 ns
Long pulse for PADME

## Slide 28: New dipoles

## Slide 29
Tender assigned to Sigmaphi: 6 Feb.
Last iteration on details of the design (yoke, coils) in May
31 May
7 May

## Slide 30
4 Oct.
28 Sep.

## Slide 31
LNF staff visit: 23 Oct. in order to:
Check yoke at the end of machining
Check coils
OK for final assembly
Delay for final delivery: 1 month

## Slide 32: New quadrupoles

## Slide 33
Tender assigned to Sigmaphi: Sep. 2018
Reviewing some details of coils, mechanical tolerances
Delivery due: Feb. 2019

## Slide 34: New power supplies

## Slide 35
Tender assigned: 6 Feb.
Factory acceptance tests:
9-10-11 Oct.
Delivery: end of October
90 ms ramp
Pulsatino
Quadrupoli
Dipoli DC

## Slide 36: Safety and radioprotection
Orders issued

## Slide 37: New bunker

## Slide 38
Order for concrete blocks: issued
Delivery: end of Oct. 2018

## Slide 39: Budget

## Slide 40
2018
Spesi:
417 k
Mancano:
40 k blocchi 40 k Camere a vuoto 30 k Chiller 75 k Dipolo 47 k Impianti
Totale:
649 k
2019
145 k Schede NI
50 k Alimentatori focalizzatori
Su infrastrutture:
60 k Camere a ionizzazione e radio-protezione

## Slide 41: Plans

## Slide 42: To do list: power supplies
Prepare new power supplies room (upstairs of BTF): power and cooling
Cabling for new magnets
Installation of new power supplies
Software and testing
New power supplies at LNF by end of Oct.
Get ready before the end of 2018

## Slide 43: To do list: new bunker and new conditioning
Concrete blocks available end of Oct.
Interference with PADME running (access to BTF experimental hall 1)
Need to build the bunker for the installation of new conditioning pipings

## Slide 44: To do list: new magnets
Magnetic field characterization of:
  2 DC dipoles (delivery Dec. 2018)
  7 quadrupoles (delivery Feb. 2019)
Magnetic measurement lab should be available from Jan. 2019

## Slide 45: To do list: BTF-2 installation
Installation and alignment of:
  Supports
  2 DC dipoles
  6 quadrupoles
Vacuum
  Pipes (to be ordered)
  Valves and pumps
Services:
  Connect water, cables, control cables
  New iron staircase for passing over the beam-lines
New magnets ready for installation Mar. 2019.

## Slide 47: PADME run status

## Slide 48
Diamond target
Scintillating bars veto
BGO calorimeter
PbF2
calorimeter
BTF beam

## Slide 49: Issues with PADME run
Not running at nominal intensity:
  5000 positrons/40 Hz, instead of 20000 positrons/50 Hz
  G9 ionization chamber close to 5 uSv/h, due to particles escaping from BTF target
  Possible solution #1: add shielding close to BTF target
  Possible solution #2: use primary positrons from LINAC

## Slide 50: Issues with PADME run
Need to install
  Timepix3 large area downstream beam monitor and soft Bremsstrahlung veto
  Final piece of scintillator veto (again for soft Bremsstrahlung)
    ADVACAM coming for installation on 22 Oct.
In parallel
  Add valve on scroll pumps
  Installation of fast valve on BTF-1 line
In parallel
  Check alignment of calorimeters