## Constants
This sheet contains constants used throughout the worksheet. You can use them directly in formulas.
Name | Value | Unit | Comment
EDIA | 15 | Euro/mm | Cost of engineers. Not really supposed to be used in the subsystem, but useful for consistency checks
LABOR | 10 | Euro/mm | Cost of technicians Not really supposed to be used in the subsystem, but useful for consistency checks
ESC9507 | 1.21 | Euro07/USD95 | Overall escalation factor from 95 to 07, see http://www.pi.infn.it/SuperB/?q=CDRBudget
USD2EURO | 0.9354 | Euro07/USD | Average exchange rate from USD to Euros. Can be used for conversion when estimate is in 2007 USD
USD07_EURO | 0.77 | Euro07/USD07 | 2007 exchange rate from USD to Euros. Debatable whether should be used at all, except for computing.

## CostTable
|  | EDIA | Labor | M\&S | Rep.Val.
WBS | Item | mm | mm | kEuro | kEuro
1 | SuperB detector | 2970.8132 | 1853.0406 | 40604.2731 | 46471.364
1.0 | Interaction region | 10 | 4 | 209.747 | 0
1.0.1 | Be Beampipe | 10 | 4 | 209.747 | 0
1.0.1.1 | Vertex chamber design | 4 | 0 | 0 | 0
1.0.1.2 | Finalize Physics Req.mnts | 0.5 | 0 | 0 | 0
1.0.1.3 | Fab method | 1 | 0 | 0 | 0
1.0.1.4 | Design Review | 0.5 | 0 | 0 | 0
1.0.1.5 | Chamber detailing | 2 | 0 | 0 | 0
1.0.1.6 | Support procurement | 2 | 0 | 3.63 | 0
1.0.1.7 | Procure Beampipe Assembly | 0 | 0 | 196.8 | 0
1.0.1.8 | Procure Vx chamber Misc parts | 0 | 0 | 9.317 | 0
1.0.1.9 | Assemble Vx chamber, test, clean | 0 | 2 | 0 | 0
1.0.1.A | Assemble Vx chamber fixtures | 0 | 2 | 0 | 0
1.1 | Tracker (SVT + L0 MAPS) | 248 | 348.3 | 5615.27 | 0
1.1.1 | SVT | 142 | 316.8 | 4380.27 | 0
1.1.1.1 | Mechanical | 14 | 186 | 313.39 | 0
1.1.1.2 | Cooling | 4 | 4.8 | 72.35 | 0
1.1.1.3 | Silicon Wafers and Fanout | 37 | 107 | 3240.38 | 0
1.1.1.4 | On-detector electronics | 69 | 11 | 671.55 | 0
1.1.1.5 | Detector monitoring | 4 | 4 | 72.6 | 0
1.1.1.6 | Detector assembly | 2 | 4 | 0 | 0
1.1.1.7 | System Engineering | 36 | 0 | 20 | 0
1.1.2 | L0 Striplet option | 23 | 33 | 323.917 | 0
1.1.2.1 | Mechanical | 6.5 | 16.5 | 3.025 | 0
1.1.2.2 | Cooling | 1.5 | 0.5 | 6.292 | 0
1.1.2.3 | Silicon Wafers and Fanout | 10 | 15 | 256.52 | 0
1.1.2.4 | On-detector electronics | 5 | 1 | 58.08 | 0
1.1.3 | L0 MAPS option | 106 | 31.5 | 1235 | 0
1.1.3.1 | Mechanical | 12 | 18 | 75 | 0
1.1.3.2 | Cooling | 2 | 2 | 20 | 0
1.1.3.3 | MAPS Modules Components | 92 | 11.5 | 1140 | 0
1.2 | DCH | 113 | 104 | 2861.65 | 0
1.2.1 | System engineering | 24 | 0 | 50 | 0
1.2.2 | Endplates | 14 | 0 | 550 | 0
1.2.3 | Inner cylinder | 4 | 0 | 157.3 | 0
1.2.4 | Outer cylinder | 4 | 0 | 100 | 0
1.2.5 | Wire | 3 | 0 | 242 | 0
1.2.6 | Feedthroughs | 9 | 10 | 344.85 | 0
1.2.A | Gas System | 4 | 8 | 50 | 0
1.2.B | Test | 3 | 6 | 40 | 0
1.3 | PID (DIRC Pixilated PMTs + TOF) | 110 | 222 | 7953.336 | 6728
1.3.1 | DIRC barrel - Pixilated PMTs | 78 | 152 | 4527.336 | 6728
1.3.1.1 | Radiator Support Structure | 0 | 0 | 0 | 2372
1.3.1.2 | Radiator Bars and Assemblies | 3 | 5 | 2244.96 | 4256
1.3.1.3 | Standoff box | 4 | 8 | 654.78 | 0
1.3.1.4 | Detector | 18 | 32 | 1590.18 | 0
1.3.1.5 | Calibration System | 1 | 3 | 18.708 | 0
1.3.1.6 | Mechanical Utilities | 4 | 8 | 18.708 | 100
1.3.1.7 | System Integration | 48 | 96 | 0 | 0
1.3.1 | DIRC barrel - Focusing DIRC | 92 | 179 | 6959.376 | 6728
1.3.1.1 | Radiator Support Structure | 0 | 0 | 0 | 2372
1.3.1.2 | Radiator Bars and Assemblies | 5 | 8 | 2806.2 | 4256
1.3.1.3 | Standoff box | 4 | 8 | 654.78 | 0
1.3.1.4 | Detector | 18 | 32 | 3460.98 | 0
1.3.1.5 | Calibration System | 1 | 3 | 18.708 | 0
1.3.1.6 | Mechanical Utilities | 4 | 8 | 18.708 | 100
1.3.1.7 | System Integration | 60 | 120 | 0 | 0
1.3.2 | Forward TOF | 32 | 70 | 3426 | 0
1.3.2.1 | Support structure | 3 | 3 | 75 | 0
1.3.2.2 | Radiator/Detector box | 6 | 10 | 220 | 0
1.3.2.3 | Detector | 5 | 18 | 3010 | 0
1.3.2.4 | Calibration System | 0 | 3 | 21 | 0
1.4 | EMC | 135.5849 | 222.4401 | 10094.6154 | 30120.234
1.4.1 | Barrel EMC | 20 | 5 | 170.8 | 30120.234
1.4.1.1 | Crystal Procurement | 0 | 0 | 0 | 20560.4068
1.4.1.2 | Light Sensors \& Readout | 0 | 0 | 0 | 2569.9903
1.4.1.3 | Crystal Support Modules | 0 | 0 | 0 | 2824.4359
1.4.1.4 | Barrel Structure | 0 | 0 | 0 | 3306.4563
1.4.1.5 | Calibration Systems | 0 | 0 | 0 | 625.4631
1.4.1.6 | Project Management | 0 | 0 | 0 | 233.4816
1.4.1.7 | Barrel Transport | 20 | 5 | 170.8 | 0
1.4.2 | Forward EMC | 73.3121 | 152.4173 | 6828.0521 | 0
1.4.2.1 | Crystal Procurement | 11.1073 | 44.3611 | 5542 | 0
1.4.2.2 | Light Sensors \& Readout | 23.3 | 31.3 | 459.5 | 0
1.4.2.3 | Crystal Support Modules | 18.725 | 59.15 | 315.5513 | 0
1.4.2.4 | Endcap Structure | 14.9313 | 16.5125 | 357.3933 | 0
1.4.2.5 | Calibration Systems | 1.5312 | 1.0938 | 100.8688 | 0
1.4.2.6 | Project Management | 3.7173 | 0 | 52.7388 | 0
1.4.3 | Backward EMC | 42.2729 | 65.0227 | 3095.7632 | 0
1.4.3.1 | Crystal Procurement | 1.1094 | 7.6132 | 2446.476 | 0
1.4.3.2 | Light Sensors \& Readout | 4.2882 | 17.0087 | 198.9042 | 0
1.4.3.3 | Crystal Support Modules | 8.1251 | 31.4316 | 225.7453 | 0
1.4.3.4 | Endcap Structure LSO | 8.7686 | 7.8755 | 148.6871 | 0
1.4.3.5 | Extended Barrel Structure CsI | 17 | 11 | 105.98 | 0
1.4.3.6 | Calibration Systems | 1 | 1.0938 | 47.8372 | 0
1.5 | IFR (scintillator) | 56.172 | 54.36 | 1268.4 | 0
1.5.1 | System engineering | 24.16 | 0 | 0 | 0
1.5.2 | scintillator strips + WLS fiber | 0 | 0 | 320.12 | 0
1.5.3 | Module factory retooling | 0 | 3.02 | 15.1 | 0
1.5.4 | Module fabrication | 0 | 27.18 | 67.95 | 0
1.5.5 | module installation | 0 | 0 | 13.59 | 0
1.5.6 | APD/preamp + cooling system | 4.832 | 0 | 662.89 | 0
1.5.7 | Services | 3.02 | 6.04 | 13.59 | 0
1.5.8 | LED pulser system | 0 | 0 | 24.16 | 0
1.5.9 | Detector Assembly | 24.16 | 18.12 | 151 | 0
1.6 | Magnet | 87 | 46.6905 | 1545.17 | 9623.13
1.6.0 | System Management | 36 | 0 | 0 | 577.17
1.6.1 | Superconducting solenoid | 0 | 0 | 0 | 2282.06
1.6.2 | Mag. Power/Protection | 0 | 0 | 0 | 170.61
1.6.3 | Cryogenics | 34.3333 | 35.5 | 1376.98 | 0
1.6.4 | Cryo monitor/Control | 16.6667 | 11.1905 | 168.19 | 0
1.6.5 | Flux return | 0 | 0 | 0 | 6108.08
1.6.6 | Installation/test equipment | 0 | 0 | 0 | 485.21
1.7 | Electronics | 286.0563 | 213 | 5565.3466 | 0
1.7.1 | SVT | 11 | 21 | 342.6084 | 0
1.7.2 | DCH | 53 | 47 | 1202.74 | 0
1.7.3 | DRC | 22.4496 | 0 | 1491.0276 | 0
1.7.4 | Forward PID | 42.6067 | 0 | 701.55 | 0
1.7.5 | EMC | 44 | 69 | 907.338 | 0
1.7.6 | IFR | 0 | 64 | 141 | 0
1.7.7 | Infrastructure | 4 | 12 | 246.84 | 0
1.7.8 | Systems Engineering | 12 | 0 | 0 | 0
1.7.9 | Hardware Trigger | 97 | 0 | 532.2426 | 0
1.8 | Online computing | 852 | 14 | 1480.7382 | 0
1.8.1 | DAQ | 0 | 2 | 19.6434 | 0
1.8.2 | Event Flow | 258 | 0 | 1176.7332 | 0
1.8.3 | Run Control / Slow Controls | 258 | 0 | 50.5116 | 0
1.8.4 | Infrastructure | 48 | 12 | 233.85 | 0
1.8.5 | Software Triggers | 216 | 0 | 0 | 0
1.8.6 | Coordination and Commissioning | 72 | 0 | 0 | 0
1.9 | Installation and integration | 353 | 624.25 | 3830 | 0
1.9.1 | Disassembly | 95 | 161 | 510 | 0
1.9.2 | Assembly | 222 | 463.25 | 3320 | 0
1.9.3 | Structural analysis | 36 | 0 | 0 | 0
1.A | Project Management | 720 | 0 | 180 | 0
1.A.1 | Project engineering | 300 | 0 | 100 | 0
1.A.2 | Budget, Schedule and Procurement | 300 | 0 | 40 | 0
1.A.3 | ES \& H | 120 | 0 | 40 | 0

## CDRTable
Range | Columns
BEAMPIPE | 1 | 2 | 3 | 4 | 7 | 0
SVT | 1 | 2 | 3 | 4 | 7 | 0
DCH | 1 | 2 | 3 | 5 | 7 | 0
DRCBARSOB | 1 | 2 | 12 | 13 | 16 | 11 | Dirc barrel with SOB
PIDBAR | 1 | 2 | 3 | 4 | 8 | 10 | Dirc barrel without SOB
PIDBARFOCUS | 1 | 2 | 3 | 4 | 8 | 10 | Dirc barrel focusing DIRC
PIDFORWTOF | 1 | 2 | 3 | 4 | 7 | 0
EMCBarrel | 1 | 2 | 3 | 4 | 5 | 13
EMCForward | 1 | 2 | 3 | 4 | 5
EMCBackward | 1 | 2 | 3 | 4 | 5
IFR | 1 | 2 | 3 | 4 | 7 | 0
MAGNET | 1 | 2 | 6 | 7 | 8 | 5
ELEX | 1 | 2 | 3 | 4 | 5
ONLINE | 1 | 2 | 3 | 4 | 5 | 0
PROJECT | 1 | 2 | 3 | 5 | 7 | 0
|  |  | Cost of new and refurbished components |  |  | Total Value of reused components
|  |  | EDIA | Labor | M\&S | EDIA+LABOR+M\&S
WBS | WBS-check | Item | [mm] | [mm] | [k€] | [2007 K€]
1 |  | SuperB detector | 2970.8132 | 1853.0406 | 40604.2731 | 46471.364
1.0 | 1.0 | Interaction region | 10 | 4 | 209.747
1.0.1 | 1.0.1 | Be Beampipe | 10 | 4 | 209.747
1.0.1.1 | 1.0.1.1 | Vertex chamber design | 4 | 0 | 0
1.0.1.2 | 1.0.1.2 | Finalize Physics Req.mnts | 0.5 | 0 | 0
1.0.1.3 | 1.0.1.3 | Fab method | 1 | 0 | 0
1.0.1.4 | 1.0.1.4 | Design Review | 0.5 | 0 | 0
1.0.1.5 | 1.0.1.5 | Chamber detailing | 2 | 0 | 0
1.0.1.6 | 1.0.1.6 | Support procurement | 2 | 0 | 3.63
1.0.1.7 | 1.0.1.7 | Procure Beampipe Assembly | 0 | 0 | 196.8
1.0.1.8 | 1.0.1.8 | Procure Vx chamber Misc parts | 0 | 0 | 9.317
1.0.1.9 | 1.0.1.9 | Assemble Vx chamber, test, clean | 0 | 2 | 0
1.0.1.A | 1.0.1.A | Assemble Vx chamber fixtures | 0 | 2 | 0
1.1 | 1.1 | Tracker (SVT + L0 MAPS) | 248 | 348.3 | 5615.27
1.1.1 | 1.1.1 | SVT | 142 | 316.8 | 4380.27
1.1.1.1 | 1.1.1.1 | Mechanical | 14 | 186 | 313.39
1.1.1.2 | 1.1.1.2 | Cooling | 4 | 4.8 | 72.35
1.1.1.3 | 1.1.1.3 | Silicon Wafers and Fanout | 37 | 107 | 3240.38
1.1.1.4 | 1.1.1.4 | On-detector electronics | 69 | 11 | 671.55
1.1.1.5 | 1.1.1.5 | Detector monitoring | 4 | 4 | 72.6
1.1.1.6 | 1.1.1.6 | Detector assembly | 2 | 4 | 0
1.1.1.7 | 1.1.1.7 | System Engineering | 36 | 0 | 20
1.1.2 | 1.1.2 | L0 Striplet option | 23 | 33 | 323.917
1.1.2.1 | 1.1.2.1 | Mechanical | 6.5 | 16.5 | 3.025
1.1.2.2 | 1.1.2.2 | Cooling | 1.5 | 0.5 | 6.292
1.1.2.3 | 1.1.2.3 | Silicon Wafers and Fanout | 10 | 15 | 256.52
1.1.2.4 | 1.1.2.4 | On-detector electronics | 5 | 1 | 58.08
1.1.3 | 1.1.3 | L0 MAPS option | 106 | 31.5 | 1235
1.1.3.1 | 1.1.3.1 | Mechanical | 12 | 18 | 75
1.1.3.2 | 1.1.3.2 | Cooling | 2 | 2 | 20
1.1.3.3 | 1.1.3.3 | MAPS Modules Components | 92 | 11.5 | 1140
1.2 | 1.2 | DCH | 113 | 104 | 2861.65
1.2.1 | 1.2.1 | System engineering | 24 | 0 | 50
1.2.2 | 1.2.2 | Endplates | 14 | 0 | 550
1.2.3 | 1.2.3 | Inner cylinder | 4 | 0 | 157.3
1.2.4 | 1.2.4 | Outer cylinder | 4 | 0 | 100
1.2.5 | 1.2.5 | Wire | 3 | 0 | 242
1.2.6 | 1.2.6 | Feedthroughs | 9 | 10 | 344.85
1.2.7 | 1.2.7 | Endplate systems | 8 | 0 | 302.5
1.2.8 | 1.2.8 | Electronics Interface | 8 | 8 | 75
1.2.9 | 1.2.9 | Assembly & Stringing | 32 | 72 | 950
1.2.A | 1.2.A | Gas System | 4 | 8 | 50
1.2.B | 1.2.B | Test | 3 | 6 | 40
1.3 | 1.3 | PID (DIRC Pixilated PMTs + TOF) | 110 | 222 | 7953.336 | 6728
1.3.1 | 1.3.1 | DIRC barrel - Pixilated PMTs | 78 | 152 | 4527.336 | 6728
1.3.1.1 | 1.3.1.1 | Radiator Support Structure | 0 | 0 | 0 | 2372
1.3.1.2 | 1.3.1.2 | Radiator Bars and Assemblies | 3 | 5 | 2244.96 | 4256
1.3.1.3 | 1.3.1.3 | Standoff box | 4 | 8 | 654.78 | 0
1.3.1.4 | 1.3.1.4 | Detector | 18 | 32 | 1590.18 | 0
1.3.1.5 | 1.3.1.5 | Calibration System | 1 | 3 | 18.708 | 0
1.3.1.6 | 1.3.1.6 | Mechanical Utilities | 4 | 8 | 18.708 | 100
1.3.1.7 | 1.3.1.7 | System Integration | 48 | 96 | 0 | 0
1.3.1 | 1.3.1 | DIRC barrel - Focusing DIRC | 92 | 179 | 6959.376 | 6728
1.3.1.1 | 1.3.1.1 | Radiator Support Structure | 0 | 0 | 0 | 2372
1.3.1.2 | 1.3.1.2 | Radiator Bars and Assemblies | 5 | 8 | 2806.2 | 4256
1.3.1.3 | 1.3.1.3 | Standoff box | 4 | 8 | 654.78 | 0
1.3.1.4 | 1.3.1.4 | Detector | 18 | 32 | 3460.98 | 0
1.3.1.5 | 1.3.1.5 | Calibration System | 1 | 3 | 18.708 | 0
1.3.1.6 | 1.3.1.6 | Mechanical Utilities | 4 | 8 | 18.708 | 100
1.3.1.7 | 1.3.1.7 | System Integration | 60 | 120 | 0 | 0
1.3.2 | 1.3.2 | Forward TOF | 32 | 70 | 3426
1.3.2.1 | 1.3.2.1 | Support structure | 3 | 3 | 75
1.3.2.2 | 1.3.2.2 | Radiator/Detector box | 6 | 10 | 220
1.3.2.3 | 1.3.2.3 | Detector | 5 | 18 | 3010
1.3.2.4 | 1.3.2.4 | Calibration System | 0 | 3 | 21
1.4 | 1.4 | EMC | 135.5849 | 222.4401 | 10094.6154 | 30120.234
1.4.1 | 1.4.1 | Barrel EMC | 20 | 5 | 170.8 | 30120.234
1.4.1.1 | 1.4.1.1 | Crystal Procurement | 0 | 0 | 0 | 20560.4068
1.4.1.2 | 1.4.1.2 | Light Sensors \& Readout | 0 | 0 | 0 | 2569.9903
1.4.1.3 | 1.4.1.3 | Crystal Support Modules | 0 | 0 | 0 | 2824.4359
1.4.1.4 | 1.4.1.4 | Barrel Structure | 0 | 0 | 0 | 3306.4563
1.4.1.5 | 1.4.1.5 | Calibration Systems | 0 | 0 | 0 | 625.4631
1.4.1.6 | 1.4.1.6 | Project Management | 0 | 0 | 0 | 233.4816
1.4.1.7 | 1.4.1.7 | Barrel Transport | 20 | 5 | 170.8 | 0
1.4.2 | 1.4.2 | Forward EMC | 73.3121 | 152.4173 | 6828.0521
1.4.2.1 | 1.4.2.1 | Crystal Procurement | 11.1073 | 44.3611 | 5542
1.4.2.2 | 1.4.2.2 | Light Sensors \& Readout | 23.3 | 31.3 | 459.5
1.4.2.3 | 1.4.2.3 | Crystal Support Modules | 18.725 | 59.15 | 315.5513
1.4.2.4 | 1.4.2.4 | Endcap Structure | 14.9313 | 16.5125 | 357.3933
1.4.2.5 | 1.4.2.5 | Calibration Systems | 1.5312 | 1.0938 | 100.8688
1.4.2.6 | 1.4.2.6 | Project Management | 3.7173 | 0 | 52.7388
1.4.3 | 1.4.3 | Backward EMC | 42.2729 | 65.0227 | 3095.7632
1.4.3.1 | 1.4.3.1 | Crystal Procurement | 1.1094 | 7.6132 | 2446.476
1.4.3.2 | 1.4.3.2 | Light Sensors \& Readout | 4.2882 | 17.0087 | 198.9042
1.4.3.3 | 1.4.3.3 | Crystal Support Modules | 8.1251 | 31.4316 | 225.7453
1.4.3.4 | 1.4.3.4 | Endcap Structure LSO | 8.7686 | 7.8755 | 148.6871
1.4.3.5 | 1.4.3.5 | Extended Barrel Structure CsI | 17 | 11 | 105.98
1.4.3.6 | 1.4.3.6 | Calibration Systems | 1 | 1.0938 | 47.8372
1.5 | 1.5 | IFR (scintillator) | 56.172 | 54.36 | 1268.4 |  | Note: factor 1.51 to scale from barrel only estimate
1.5.1 | 1.5.1 | System engineering | 24.16 | 0 | 0
1.5.2 | 1.5.2 | scintillator strips + WLS fiber | 0 | 0 | 320.12
1.5.3 | 1.5.3 | Module factory retooling | 0 | 3.02 | 15.1
1.5.4 | 1.5.4 | Module fabrication | 0 | 27.18 | 67.95
1.5.5 | 1.5.5 | module installation | 0 | 0 | 13.59
1.5.6 | 1.5.6 | APD/preamp + cooling system | 4.832 | 0 | 662.89
1.5.7 | 1.5.7 | Services | 3.02 | 6.04 | 13.59
1.5.8 | 1.5.8 | LED pulser system | 0 | 0 | 24.16
1.5.9 | 1.5.9 | Detector Assembly | 24.16 | 18.12 | 151
1.6 | 1.6 | Magnet | 87 | 46.6905 | 1545.17 | 9623.13
1.6.0 | 1.6.0 | System Management | 36 | 0 | 0 | 577.17
1.6.1 | 1.6.1 | Superconducting solenoid | 0 | 0 | 0 | 2282.06
1.6.2 | 1.6.2 | Mag. Power/Protection | 0 | 0 | 0 | 170.61
1.6.3 | 1.6.3 | Cryogenics | 34.3333 | 35.5 | 1376.98 | 0
1.6.4 | 1.6.4 | Cryo monitor/Control | 16.6667 | 11.1905 | 168.19 | 0
1.6.5 | 1.6.5 | Flux return | 0 | 0 | 0 | 6108.08
1.6.6 | 1.6.6 | Installation/test equipment | 0 | 0 | 0 | 485.21
1.7 | 1.7 | Electronics | 286.0563 | 213 | 5565.3466
1.7.1 | 1.7.1 | SVT | 11 | 21 | 342.6084
1.7.2 | 1.7.2 | DCH | 53 | 47 | 1202.74
1.7.3 | 1.7.3 | DRC | 22.4496 | 0 | 1491.0276
1.7.4 | 1.7.4 | Forward PID | 42.6067 | 0 | 701.55
1.7.5 | 1.7.5 | EMC | 44 | 69 | 907.338
1.7.6 | 1.7.6 | IFR | 0 | 64 | 141
1.7.7 | 1.7.7 | Infrastructure | 4 | 12 | 246.84
1.7.8 | 1.7.8 | Systems Engineering | 12 | 0 | 0
1.7.9 | 1.7.9 | Hardware Trigger | 97 | 0 | 532.2426
1.8 | 1.8 | Online computing | 852 | 14 | 1480.7382
1.8.1 | 1.8.1 | DAQ | 0 | 2 | 19.6434
1.8.2 | 1.8.2 | Event Flow | 258 | 0 | 1176.7332
1.8.3 | 1.8.3 | Run Control / Slow Controls | 258 | 0 | 50.5116
1.8.4 | 1.8.4 | Infrastructure | 48 | 12 | 233.85
1.8.5 | 1.8.5 | Software Triggers | 216 | 0 | 0
1.8.6 | 1.8.6 | Coordination and Commissioning | 72 | 0 | 0
1.9 | 1.9 | Installation and integration | 353 | 624.25 | 3830 |  | Note: this is not linked to the 1.9 sheet
1.9.1 | 1.9.1 | Disassembly | 95 | 161 | 510
1.9.2 | 1.9.2 | Assembly | 222 | 463.25 | 3320
1.9.3 | 1.9.3 | Structural analysis | 36 | 0 | 0
1.A | 1.A | Project Management | 720 | 0 | 180
1.A.1 | 1.A.1 | Project engineering | 300 | 0 | 100
1.A.2 | 1.A.2 | Budget, Schedule and Procurement | 300 | 0 | 40
1.A.3 | 1.A.3 | ES \& H | 120 | 0 | 40

## 1. BEAMPIPE
|  | Engineering | Technician | EDIA Keuro | LABOR Keuro | M&S | Subtot. | Contingency % | Contingency Total | Total | M&S
|  | [mm] | [mm] |  |  | [KEuros] |  |  |  |  | [$]
1.0 | Interaction region | 10 | 4 | 150 | 40 | 209.747 | 399.747 | 0 | 99.9368 | 499.6837 | from PEPII 95 if not new
1.0.1 | Be Beampipe | 10 | 4 | 150 | 40 | 209.747 | 399.747 |  | 99.9368 | 499.6837 | 0
1.0.1.1 | Vertex chamber design | 4 | 0 | 60 | 0 | 0 | 60 |  | 15 | 75 | 0
1.1.1.1.1 | Mech design | 2 | 0 | 30 | 0 | 0 | 30 | 25 | 7.5 | 37.5 | 0
1.1.1.1.2 | Vacuum calculation | 1 | 0 | 15 | 0 | 0 | 15 | 25 | 3.75 | 18.75 | 0
1.1.1.1.3 | Vacuum design | 1 | 0 | 15 | 0 | 0 | 15 | 25 | 3.75 | 18.75 | 0
1.0.1.2 | Finalize Physics Req.mnts | 0.5 | 0 | 7.5 | 0 | 0 | 7.5 |  | 1.875 | 9.375 | 0
1.0.1.2.1 | Region Design | 0.5 | 0 | 7.5 | 0 | 0 | 7.5 | 25 | 1.875 | 9.375 | 0
1.0.1.3 | Fab method | 1 | 0 | 15 | 0 | 0 | 15 |  | 3.75 | 18.75 | 0
1.0.1.3.1 | Vacuum engineering | 0.33 | 0 | 4.95 | 0 | 0 | 4.95 | 25 | 1.2375 | 6.1875 | 0
1.0.1.3.2 | Vacuum design | 0.67 | 0 | 10.05 | 0 | 0 | 10.05 | 25 | 2.5125 | 12.5625 | 0
1.0.1.4 | Design Review | 0.5 | 0 | 7.5 | 0 | 0 | 7.5 |  | 1.875 | 9.375 | 0
1.0.1.4.1 | Engineering | 0.25 | 0 | 3.75 | 0 | 0 | 3.75 | 25 | 0.9375 | 4.6875 | 0
1.0.1.4.2 | Design | 0.25 | 0 | 3.75 | 0 | 0 | 3.75 | 25 | 0.9375 | 4.6875 | 0
1.0.1.5 | Chamber detailing | 2 | 0 | 30 | 0 | 0 | 30 |  | 7.5 | 37.5 | 0
1.0.1.5.1 | Engineering | 1 | 0 | 15 | 0 | 0 | 15 | 25 | 3.75 | 18.75
1.0.1.5.2 | Design | 1 | 0 | 15 | 0 | 0 | 15 | 25 | 3.75 | 18.75 | 0
1.0.1.6 | Support procurement | 2 | 0 | 30 | 0 | 3.63 | 33.63 |  | 8.4075 | 42.0375
1.0.1.6.1 | Design engineering | 1 | 0 | 15 | 0 | 0 | 15 | 25 | 3.75 | 18.75 | 0
1.0.1.6.2 | Vendors visits | 1 | 0 | 15 | 0 | 3.63 | 18.63 | 25 | 4.6575 | 23.2875 | 3
1.0.1.7 | Procure Beampipe Assembly | 0 | 0 | 0 | 0 | 196.8 | 196.8 |  | 49.2 | 246
1.0.1.7.1 | Be inner vacuum pipe | 0 | 0 | 0 | 0 | 36.3 | 36.3 | 25 | 9.075 | 45.375 | 30
1.0.1.7.2 | Be outer water sleeve | 0 | 0 | 0 | 0 | 36.3 | 36.3 | 25 | 9.075 | 45.375 | 30
1.0.1.7.3 | End braze fitting pieces | 0 | 0 | 0 | 0 | 12.1 | 12.1 | 25 | 3.025 | 15.125 | 10
1.0.1.7.4 | End water routing rings | 0 | 0 | 0 | 0 | 12.1 | 12.1 | 25 | 3.025 | 15.125 | 10
1.0.1.7.5 | Manufacturing | 0 | 0 | 0 | 0 | 100 | 100 | 25 | 25 | 125 | 10
1.0.1.8 | Procure Vx chamber Misc parts | 0 | 0 | 0 | 0 | 9.317 | 9.317 |  | 2.3293 | 11.6463
1.0.1.8.1 | Cooling tubes | 0 | 0 | 0 | 0 | 0.121 | 0.121 | 25 | 0.03025 | 0.15125 | 0.1
1.0.1.8.2 | End rings | 0 | 0 | 0 | 0 | 1.452 | 1.452 | 25 | 0.363 | 1.815 | 1.2
1.0.1.8.3 | End eyelets | 0 | 0 | 0 | 0 | 1.452 | 1.452 | 25 | 0.363 | 1.815 | 1.2
1.1.1.8.4 | Welded bellows | 0 | 0 | 0 | 0 | 1.452 | 1.452 | 25 | 0.363 | 1.815 | 1.2
1.1.1.8.5 | Bellows RF shields | 0 | 0 | 0 | 0 | 4.84 | 4.84 | 25 | 1.21 | 6.05 | 4
1.0.1.9 | Assemble Vx chamber, test, clean | 0 | 2 | 0 | 20 | 0 | 20 |  | 5 | 25
1.1.1.9.1 | Leak test | 0 | 1 | 0 | 10 | 0 | 10 | 25 | 2.5 | 12.5 | 0
1.1.1.9.2 | Clean for UHV | 0 | 0.3 | 0 | 3 | 0 | 3 | 25 | 0.75 | 3.75 | 0
1.1.1.9.3 | Inside plate | 0 | 0.1 | 0 | 1 | 0 | 1 | 25 | 0.25 | 1.25 | 0
1.1.1.9.4 | Epoxy coating | 0 | 0.15 | 0 | 1.5 | 0 | 1.5 | 25 | 0.375 | 1.875 | 0
1.1.1.9.5 | Weld on water sleeve | 0 | 0.1 | 0 | 1 | 0 | 1 | 25 | 0.25 | 1.25 | 0
1.1.1.9.6 | Weld on bellows, flange, eyelet | 0 | 0.05 | 0 | 0.5 | 0 | 0.5 | 25 | 0.125 | 0.625 | 0
1.1.1.9.7 | Weld on water tubes | 0 | 0.05 | 0 | 0.5 | 0 | 0.5 | 25 | 0.125 | 0.625 | 0
1.1.1.9.8 | Leak/pressure test | 0 | 0.1 | 0 | 1 | 0 | 1 | 25 | 0.25 | 1.25 | 0
1.1.1.9.9 | Cleaning | 0 | 0.15 | 0 | 1.5 | 0 | 1.5 | 25 | 0.375 | 1.875 | 0
1.0.1.A | Assemble Vx chamber fixtures | 0 | 2 | 0 | 20 | 0 | 20 |  | 5 | 25
1.1.1.10.1 | Fixture fab | 0 | 1 | 0 | 10 | 0 | 10 | 25 | 2.5 | 12.5 | 0
1.1.1.10.2 | Fixture installation | 0 | 1 | 0 | 10 | 0 | 10 | 25 | 2.5 | 12.5 | 0
See Constants sheet for conversion values

## 1.1 SVT
|  | Engineering | Technician | EDIA Keuro | LABOR Keuro | M&S | Subtot. | Contingency % | Contingency Total | Total | M&S
|  | [mm] | [mm] |  |  | [KEuros] |  |  |  |  | [$]
1.1 | Tracker (SVT + L0 MAPS) | 248 | 348.3 | 3720 | 3483 | 5615.27 | 12818.27 | 0 | 3204.5675 | 16022.8375 | from BaBar 95 if not new
1.1.1 | SVT | 142 | 316.8 | 2130 | 3168 | 4380.27 | 9678.27 |  | 2419.5675 | 12097.8375 | 3607
1.1.1.1 | Mechanical | 14 | 186 | 210 | 1860 | 313.39 | 2383.39 |  | 595.8475 | 2979.2375 | 259
1.1.1.1.1 | Dector Modules | 12 | 172 | 180 | 1720 | 275.88 | 2175.88 | 25 | 543.97 | 2719.85 | 228
1.1.1.1.2 | Design tool | 0 | 0 | 0 | 0 | 1.21 | 1.21 | 25 | 0.3025 | 1.5125 | 1
1.1.1.1.3 | Measurement gauges | 0 | 2 | 0 | 20 | 0 | 20 | 25 | 5 | 25 | 0
1.1.1.1.4 | Mechanical Support | 2 | 11 | 30 | 110 | 36.3 | 176.3 | 25 | 44.075 | 220.375 | 30
1.1.1.1.5 | Transition Card Support | 0 | 1 | 0 | 10 | 0 | 10 | 25 | 2.5 | 12.5
1.1.1.2 | Cooling | 4 | 4.8 | 60 | 48 | 72.35 | 180.35 |  | 45.0875 | 225.4375 | 45
1.1.1.2.1 | HDI cooling | 1.5 | 0.6 | 22.5 | 6 | 24.2 | 52.7 | 25 | 13.175 | 65.875 | 20
1.1.1.2.2 | Transition Card Cooling | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 10
1.1.1.2.3 | Ambient cooling | 0.5 | 0.2 | 7.5 | 2 | 18.15 | 27.65 | 25 | 6.9125 | 34.5625 | 15
1.1.1.2.4 | Controls and interlocks | 2 | 4 | 30 | 40 | 30 | 100 | 25 | 25 | 125
1.1.1.3 | Silicon Wafers and Fanout | 37 | 107 | 555 | 1070 | 3240.38 | 4865.38 |  | 1216.345 | 6081.725 | 2678
1.1.1.3.1 | Silicon wafers | 10 | 57 | 150 | 570 | 2861.65 | 3581.65 | 25 | 895.4125 | 4477.0625 | 2365
1.1.1.3.2 | Fanout circuits | 15 | 24 | 225 | 240 | 354.53 | 819.53 | 25 | 204.8825 | 1024.4125 | 293
1.1.1.3.3 | Detector-Fanout assmbly | 12 | 26 | 180 | 260 | 24.2 | 464.2 | 25 | 116.05 | 580.25 | 20
1.1.1.4 | On-detector electronics | 69 | 11 | 1035 | 110 | 671.55 | 1816.55 |  | 454.1375 | 2270.6875 | 555
1.1.1.4.1 | Readout IC | 48 | 3 | 720 | 30 | 399.3 | 1149.3 | 25 | 287.325 | 1436.625 | 330
1.1.1.4.2 | HDI | 8 | 0 | 120 | 0 | 90.75 | 210.75 | 25 | 52.6875 | 263.4375 | 75
1.1.1.4.3 | Transition card | 13 | 8 | 195 | 80 | 181.5 | 456.5 | 25 | 114.125 | 570.625 | 150
1.1.1.5 | Detector monitoring | 4 | 4 | 60 | 40 | 72.6 | 172.6 |  | 43.15 | 215.75 | 60
1.1.1.5.1 | Temperature monitors | 1 | 1 | 15 | 10 | 0 | 25 | 25 | 6.25 | 31.25
1.1.1.5.2 | Radiation monitors | 2 | 2 | 30 | 20 | 36.3 | 86.3 | 25 | 21.575 | 107.875 | 30
1.1.1.5.3 | Capacitecs | 1 | 1 | 15 | 10 | 36.3 | 61.3 | 25 | 15.325 | 76.625 | 30
1.1.1.6 | Detector assembly | 2 | 4 | 30 | 40 | 0 | 70 |  | 17.5 | 87.5
1.1.1.6.1 | Module mounting | 1 | 2 | 15 | 20 | 0 | 35 | 25 | 8.75 | 43.75 | 0
1.1.1.6.2 | Assembly onto beampipe | 1 | 2 | 15 | 20 | 0 | 35 | 25 | 8.75 | 43.75 | 0
1.1.1.7 | System Engineering | 36 | 0 | 540 | 0 | 20 | 560 |  | 140 | 700 | 10
1.1.1.7.1 | Electrical Engineering | 24 | 0 | 360 | 0 | 10 | 370 | 25 | 92.5 | 462.5 | 10
1.1.1.7.2 | Mechanical Engineering | 12 | 0 | 180 | 0 | 10 | 190 | 25 | 47.5 | 237.5 | 10
1.1.2 | L0 Striplet option | 23 | 33 | 345 | 330 | 323.917 | 998.917 |  | 249.7293 | 1248.6463
1.1.2.1 | Mechanical | 6.5 | 16.5 | 97.5 | 165 | 3.025 | 265.525 |  | 66.3812 | 331.9062
1.1.2.1.1 | Dector Modules | 6.5 | 16.5 | 97.5 | 165 | 3.025 | 265.525 | 25 | 66.3812 | 331.9062 | 2.5
1.1.2.1.2 | Design tool | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.1.3 | Measurement gauges | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.1.4 | Mechanical Support | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.1.5 | Transition Card | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.2 | Cooling | 1.5 | 0.5 | 22.5 | 5 | 6.292 | 33.792 |  | 8.448 | 42.24
1.1.2.2.1 | HDI cooling | 1.5 | 0.5 | 22.5 | 5 | 6.292 | 33.792 | 25 | 8.448 | 42.24 | 5.2
1.1.2.2.2 | Transition Card Cooling | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.3 | Silicon Wafers and Fanout | 10 | 15 | 150 | 150 | 256.52 | 556.52 |  | 139.13 | 695.65
1.1.2.3.1 | Silicon wafers | 3 | 2 | 45 | 20 | 185.13 | 250.13 | 25 | 62.5325 | 312.6625 | 153
1.1.2.3.2 | Fanout circuits | 5 | 7 | 75 | 70 | 68.97 | 213.97 | 25 | 53.4925 | 267.4625 | 57
1.1.2.3.3 | Detector-Fanout assmbly | 2 | 6 | 30 | 60 | 2.42 | 92.42 | 25 | 23.105 | 115.525 | 2
1.1.2.4 | On-detector electronics | 5 | 1 | 75 | 10 | 58.08 | 143.08 |  | 35.77 | 178.85
1.1.2.4.1 | Readout IC | 2 | 1 | 30 | 10 | 26.62 | 66.62 | 25 | 16.655 | 83.275 | 22
1.1.2.4.2 | HDI | 3 | 0 | 45 | 0 | 31.46 | 76.46 | 25 | 19.115 | 95.575 | 26
1.1.2.4.3 | Transition card | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.5 | Detector monitoring (included in SVT) |  |  |  |  | 0 | 0 |  | 0 | 0
1.1.2.5.1 | Temperature monitors | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.5.2 | Radiation monitors | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.5.3 | Capacitecs | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.6 | Detector assembly | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1.1.2.6.1 | Module mounting | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.6.2 | Assembly onto beampipe | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0 | 0
1.1.2.7 | System Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3 | L0 MAPS option | 106 | 31.5 | 1590 | 315 | 1235 | 3140 |  | 785 | 3925
1.1.3.1 | Mechanical | 12 | 18 | 180 | 180 | 75 | 435 |  | 108.75 | 543.75
1.1.3.1.1 | Dector Modules | 12 | 18 | 180 | 180 | 75 | 435 | 25 | 108.75 | 543.75
1.1.3.1.2 | Design tool | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.1.3 | Measurement gauges | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.1.4 | Mechanical Support | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.1.5 | Transition Card | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.2 | Cooling | 2 | 2 | 30 | 20 | 20 | 70 |  | 17.5 | 87.5
1.1.3.2.1 | HDI cooling | 2 | 2 | 30 | 20 | 20 | 70 | 25 | 17.5 | 87.5
1.1.3.3 | MAPS Modules Components | 92 | 11.5 | 1380 | 115 | 1140 | 2635 |  | 658.75 | 3293.75
1.1.3.3.1 | MAPS chips | 84 | 6 | 1260 | 60 | 1000 | 2320 | 25 | 580 | 2900
1.1.3.3.2 | Fanout circuits | 2 | 5.5 | 30 | 55 | 95 | 180 | 25 | 45 | 225
1.1.3.3.3 | HDI | 3 | 0 | 45 | 0 | 15 | 60 | 25 | 15 | 75
1.1.3.3.4 | Transition card | 3 | 0 | 45 | 0 | 30 | 75 | 25 | 18.75 | 93.75
1.1.3.4 | Detector monitoring (included in SVT) |  |  |  |  | 0 | 0 |  | 0 | 0
1.1.3.4.1 | Temperature monitors | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.4.2 | Radiation monitors | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.4.3 | Capacitecs | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.5 | Detector assembly | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0
1.1.3.5.1 | Module mounting | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.5.2 | Assembly onto beampipe | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
1.1.3.6 | System Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | 0
See Constants sheet for edia and labor constants

## 1.2 DCH
|  | Engineering |  | Technician |  | M&S | Total | Value of in-kind components | Assumptions | Contingency | Comment | Basis for estimate
|  | [mm] | [Euros] | [mm] | [Euros] | [KEuros] | [kEuros]
1.2 | DCH | 113 | 1695 | 104 | 1040 | 2861.65 | 6446.65
1.2.1 | System engineering | 24 | 360 | 0 | 0 | 50 | 1030
1.2.1.1 | Design & Integration | 24 | 360 | 0 | 0 | 50 | 410 | [5 empty] | 0.15 | 0
1.2.2 | Endplates | 14 | 210 | 0 | 0 | 550 | 760 | [5 empty] | 0.0875 | 0
1.2.2.1 | Research & Development | 6 | 90 | 0 | 0 | 50 | 140 | [5 empty] | 0.0375 | 0
1.2.2.2 | Design | 4 | 60 | 0 | 0 | 0 | 60
1.2.2.3 | Procurement | 4 | 60 | 0 | 0 | 500 | 560 |  |  |  |  | Escalated aluminum endplate is 440k | 0.025 | 0
1.2.3 | Inner cylinder | 4 | 60 | 0 | 0 | 157.3 | 217.3 | [5 empty] | 0.025 | 0
1.2.3.1 | Design | 4 | 60 | 0 | 0 | 0 | 60 | [5 empty] | 0.025 | 0
1.2.3.2 | Procurement | 0 | 0 | 0 | 0 | 157.3 | 157.3 |  |  |  |  | BABAR DCH w/escalation | 0 | 0
1.2.4 | Outer cylinder | 4 | 60 | 0 | 0 | 100 | 160 | [5 empty] | 0.025 | 0
1.2.4.1 | Design | 4 | 60 | 0 | 0 | 0 | 60 | [5 empty] | 0.025 | 0
1.2.4.2 | Procurement | 0 | 0 | 0 | 0 | 100 | 100 | [5 empty] | 0 | 0
1.2.5 | Wire | 3 | 45 | 0 | 0 | 242 | 287 | [5 empty] | 0.01875 | 0
1.2.5.1 | Design | 3 | 45 | 0 | 0 | 0 | 45 | [5 empty] | 0.01875 | 0
1.2.5.2 | Procurement | 0 | 0 | 0 | 0 | 242 | 242 |  |  |  |  | BABAR DCH w/escalation | 0 | 0
1.2.6 | Feedthroughs | 9 | 135 | 10 | 100 | 344.85 | 579.85
1.2.6.1 | Design | 6 | 90 | 0 | 0 | 0 | 90
1.2.6.2 | Procurement & Assembly | 3 | 45 | 10 | 100 | 344.85 | 489.85 |  |  |  |  | BABAR DCH w/escalation
1.2.7 | Endplate systems | 8 | 120 | 0 | 0 | 302.5 | 652.5 | [5 empty] | 0.05 | 0
1.2.7.1 | Design | 8 | 120 | 0 | 0 | 0 | 120 | [5 empty] | 0.05 | 0
1.2.7.2 | Procurement | 0 | 0 | 0 | 0 | 302.5 | 302.5 |  |  |  |  | BABAR DCH w/escalation | 0 | 0
1.2.7.3 | Installation | 4 | 60 | 12 | 120 | 50 | 230
1.2.8 | Electronics Interface | 8 | 120 | 8 | 80 | 75 | 275
1.2.8.1 | HV & Signal distribution | 4 | 60 | 4 | 40 | 25 | 125
1.2.8.2 | Front-end assemblies | 4 | 60 | 4 | 40 | 50 | 150
1.2.9 | Assembly & Stringing | 32 | 480 | 72 | 720 | 950 | 2150 | [5 empty] | 0.2 | 0.45
1.2.9.1 | Fixture Design | 10 | 150 | 0 | 0 | 0 | 150 | [5 empty] | 0.0625 | 0
1.2.9.2 | Procurement | 2 | 30 | 0 | 0 | 250 | 280 | [5 empty] | 0.0125 | 0
1.2.9.3 | Clean Room | 2 | 30 | 4 | 40 | 300 | 370 | [5 empty] | 0.0125 | 0.025
1.2.9.4 | Stringing Robots | 6 | 90 | 6 | 60 | 300 | 450 | [5 empty] | 0.0375
1.2.9.5 | Assembly | 6 | 90 | 12 | 120 | 50 | 260
1.2.9.6 | Stringing | 6 | 90 | 50 | 500 | 50 | 640 |  |  |  |  | BABAR DCH | 0.0375 | 0.3125
1.2.A | Gas System | 4 | 60 | 8 | 80 | 50 | 190
1.2.A.1 | Design | 4 | 60 | 0 | 0 | 0 | 60
1.2.A.2 | Procurement & Assembly | 0 | 0 | 8 | 80 | 50 | 130
1.2.B | Test | 3 | 45 | 6 | 60 | 40 | 145 | [5 empty] | 0.01875 | 0.0375
1.2.B.1 | Design | 3 | 45 | 0 | 0 | 0 | 45 | [5 empty] | 0.01875 | 0
1.2.B.2 | Procurement | 0 | 0 | 0 | 0 | 40 | 40 | [5 empty] | 0 | 0
1.2.B.3 | Test | 0 | 0 | 6 | 60 | 0 | 60 | [5 empty] | 0 | 0.0375

## 1.3.1 DRC with SOB
|  | Cost (1997) | EDIA | Labor | M&S | EDIA | Labor | Summed | Value(2007) | Reuse value | Engineering | Technician | EDIA Keuro | LABOR Keuro | M&S | Subtot. | Contingency % | Contingency Total | Total New Cost | Offset Value | Total Value
|  | K$ | K$ | K$ | K$ | MM | MM | Cost (1997) | Keuros | 2007 kEuros | [mm] | [mm] | 15 | 10 | [KEuros] | [5 empty] | kEuros
1.3 | PID |  |  |  |  | 10 | 5 | [5 empty] | Above not used | Above not used
1.3.1 | DIRC Barrel | 8876 | 1737 | 974 | 6165 | 173.7 | 194.8 | 8876 | 10739.96 | 9003.61 | 46 | 84 | 330 | 360 | 1751 | 3481 |  | 1387.7 | 4868.7 |  | 13872.31
1.3.1.1 | Radiator Support Structure | 1960 | 838 | 288 | 834 | 83.8 | 57.6 | 1960 | 2371.6 | 2371.6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 2371.6
1.3.1.1.1 | Central Support Tube | 623 | 304 | 167 | 152 | 30.4 | 33.4 | 623 | 753.83 | 753.83 | [8 empty] | 0 |  | 753.83
1.3.1.1.2 | Strong Support Tube | 516 | 178 | 12 | 326 | 17.8 | 2.4 | 516 | 624.36 | 624.36 | [8 empty] | 0 |  | 624.36
1.3.1.1.3 | Bar Assembly Boxes | 550 | 259 | 97 | 194 | 25.9 | 19.4 | 550 | 665.5 | 665.5 | [8 empty] | 0 |  | 665.5
1.3.1.1.5 | External Support Structure | 271 | 97 | 12 | 162 | 9.7 | 2.4 | 271 | 327.91 | 327.91 | [8 empty] | 0 |  | 327.91
1.3.1.2 | Radiator Bars and Assemblies | 3517 | 238 | 343 | 2936 | 23.8 | 68.6 | 3517 | 4255.57 | 4255.57 | 6 | 16 | 90 | 160 | 80 | 330 |  | 82.5 | 412.5 |  | 4668.07 | Take Wedge cost into 3.1.2.2
1.3.1.2.1 | Fused Silica Procurement | 1031 | 27 | 0 | 1004 | 2.7 | 0 | 1031 | 1247.51 | 1247.51 | [5 empty] | 0 |  | 0 | 0 |  | 1247.51
1.3.1.2.2 | Fused Silica Bar Fabrication | 2283 | 134 | 241 | 1908 | 13.4 | 48.2 | 2283 | 2762.43 | 2762.43 | [5 empty] | 0 |  | 0 | 0 |  | 2762.43 | Get better number for final cost
1.3.1.2.3 | Window Fabrication | 32 | 12 | 16 | 4 | 1.2 | 3.2 | 32 | 38.72 | 38.72 | [5 empty] | 0 |  | 0 | 0 |  | 38.72
1.3.1.2.4 | Bar Assembly in Boxes | 123 | 54 | 59 | 10 | 5.4 | 11.8 | 123 | 148.83 | 148.83 | 4 | 12 | 60 | 120 | 60 | 240 | 25 | 60 | 300 | 300 | 148.83
1.3.1.2.5 | Bar Assembly and Storage | 48 | 11 | 27 | 10 | 1.1 | 5.4 | 48 | 58.08 | 58.08 | 2 | 4 | 30 | 40 | 20 | 90 | 25 | 22.5 | 112.5 | 112.5 | 58.08
1.3.1.3 | Standoff Box | 1599 | 405 | 144 | 1050 | 40.5 | 28.8 | 1599 | 1934.79 | 1934.79 | [5 empty] | 0 |  |  | 0 |  | 1934.79
1.3.1.3.1 | SOB Design and Specs | 165 | 165 | 0 | 0 | 16.5 | 0 | 165 | 199.65 | 199.65 | [5 empty] | 0
1.3.1.3.2 | SOB Procurement | 1060 | 60 | 0 | 1000 | 6 | 0 | 1060 | 1282.6 | 1282.6 | [5 empty] | 0
1.3.1.3.3 | SOB Fabrication | 177 | 80 | 72 | 25 | 8 | 14.4 | 177 | 214.17 | 214.17 | [5 empty] | 0
1.3.1.3.4 | SOB Testing | 197 | 100 | 72 | 25 | 10 | 14.4 | 197 | 238.37 | 238.37 | [5 empty] | 0
1.3.1.4 | Detector | 1435 | 138 | 91 | 1206 | 13.8 | 18.2 | 1435 | 1736.35 | 0 | 16 | 20 | 240 | 200 | 1671 | 2111 |  | 1045.2 | 3156.2 |  | 3156.2
1.3.1.4.1 | PMT | 1240 | 80 | 60 | 1100 | 8 | 12 | 1240 | 1500.4 | 0 | 8 | 12 | 120 | 120 | 1571 | 1811 | 65.8209 | 970.2 | 2781.2 |  | 2781.2 | Using Burle Tubes.Large contingency because of differential to Hamamatsu
1.3.1.4.2 | Bases | 195 | 58 | 31 | 106 | 5.8 | 6.2 | 195 | 235.95 | 0 | 8 | 8 | 120 | 80 | 100 | 300 | 25 | 75 | 375 |  | 375 | Assuming New Bases
1.3.1.5 | Calibration Systems | 200 | 40 | 60 | 100 | 4 | 12 | 200 | 242 | 242 | [5 empty] | 0 |  | 0 | 0 |  | 242
1.3.1.5.1 | System | 200 | 40 | 60 | 100 | 4 | 12 | 200 | 242 | 242
1.3.1.6 | Mechanical Utilities | 165 | 78 | 48 | 39 | 7.8 | 9.6 | 165 | 199.65 | 199.65 | [5 empty] | 0 |  | 0 | 0 |  | 199.65
1.3.1.7 | System Integration | 0 | [6 empty] | 0 | 0 | 24 | 48 | 360 | 480 | 200 | 1040 | 25 | 260 | 1300 |  | 1300 | Base EDIA/Labor support. Overall move, disassembly, reassembly etc elsewhere
NOTE: Electronics is not summed
1.7.3 | Electronics (FE) | 1100 | [6 empty] | 1331 |  | 34.4496 | 0 | 336.744 | 0 | 1491.16 | 1827.904 |  |  | 2284.88 | 2284.88 | 2284.88 | Cost of electronics estimated by Gunther + extrapolated from BaBar
1.7.3.1 | FE-IC proto | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 25 | 0 | 0 |  |  | NOT SUMMED INTO THE TOTAL
1.7.3.2 | FE-IC prod (qty 4000) | [7 empty] | 0 |  | 2.4944 |  | 37.416 |  | 211.75 | 249.166 | 25 | 62.2915 | 311.4575 |  |  | IC's:
1.7.3.3 | FPGA (qty 1000) | [7 empty] | 0 |  | 3.7416 |  | 56.124 |  | 154 | 210.124 | 25 | 52.531 | 262.655 |  |  | Assume 4-ch=10sqmm->16-ch ~ 40sqmm
1.7.3.4 | FE assembly (qty 1000) | [7 empty] | 0 |  | 3.118 |  | 46.77 |  | 77 | 123.77 | 25 | 30.9425 | 154.7125 |  |  | TSMC IC:
1.7.3.5 | Cables & Connectors (BaBar) | 176 | [6 empty] | 212.96 |  | 0.6236 |  | 9.354 |  | 212.96 | 222.314 | 25 | 55.5785 | 277.8925 |  |  | 155k mask, 2 lots x 50k ~250k, assume 2 lots since one run won't yield spares
1.7.3.6 | DFB equi (qty 15) | [7 empty] | 0 |  | 3.7416 |  | 56.124 |  | 57.75 | 113.874 | 25 | 28.4685 | 142.3425 |  |  | plus add $25k M&S for testing
1.7.3.7 | DCC (qty 1) | [7 empty] | 0 |  | 1.8708 |  | 28.062 |  | 11.55 | 39.612 | 25 | 9.903 | 49.515
1.7.3.8 | PDB (qty 1) | [7 empty] | 0 |  | 0 |  | 0 |  | 0 | 0 | 25 | 0 | 0
1.7.3.9 | Crates & LV Pwr Supplies (BaBar) | 98 | [6 empty] | 118.58 |  | 0 |  | 0 |  | 118.58 | 118.58 | 25 | 29.645 | 148.225
1.7.3.10 | prototyping (qty 12) | [7 empty] | 0 |  | 6.236 |  | 93.54 |  | 38.5 | 132.04 | 25 | 33.01 | 165.05
1.7.3.11 | Final installation | [7 empty] | 0 |  | 0.6236 |  | 9.354 |  | 7.7 | 17.054 | 25 | 4.2635 | 21.3175
1.7.3.12 | HT power supplies & cables (BaBar) | 282 | [6 empty] | 341.22 |  | 4 |  |  |  | 341.22 | 341.22 | 25 | 85.305 | 426.525
1.7.3.13 | Infrastructure and Monitor elec (BaBar) | 117 | [6 empty] | 141.57 |  | 4 |  |  |  | 141.57 | 141.57 | 25 | 35.3925 | 176.9625
1.7.3.14 | Electronics Test Bench (BaBar) | 98 | [6 empty] | 118.58 |  | 4 |  |  |  | 118.58 | 118.58 | 25 | 29.645 | 148.225

## 1.3.1 DRC without SOB
|  | Engineering | Technician | EDIA kEuro | LABOR kEuro | M&S | M&S | Subtotal | Resuse | Contingency | Contingency | Total Cost | Offset | Total | Comment
|  | [mm] | [mm] | 15 | 10 | k$ | kEuro | kEuro | KE | % | Keuros | New | Value | Value
Option A |  |  |  | ABOVE NOT USED | [8 empty] | Keuros | Keuros
1.3 | PID
1.3.1 | DIRC barrel - Pixilated PMTs | 78 | 152 | 1155 | 1520 | 4840 | 4527.336 | 7202.7752 | 6728 |  | 1688.4238 | 8891.199 | 1562.475 | 14056.724
1.3.1.1 | Radiator Support Structure | [6 empty] | 0 | 2372 |  |  | 0 | 0 | 2372
1.3.1.2 | Radiator Bars and Assemblies | 3 | 5 | 45 | 50 | 2400 | 2244.96 | 2339.96 | 4256 |  | 584.99 | 2924.95 | 1462.475 | 5718.475
1.3.1.2.1 | Fused Silica coupling | 3 | 5 | 45 | 50 | 2400 | 2244.96 | 2339.96 |  | 25 | 584.99 | 2924.95 |  | 2924.95 | Assume that we have 12 optical couplings, each $200K
1.3.1.3 | Standoff box | 4 | 8 | 60 | 80 | 700 | 654.78 | 794.78 |  |  | 198.695 | 993.475 |  | 993.475
1.3.1.3.1 | Box | 2 | 4 | 30 | 40 | 500 | 467.7 | 537.7 |  | 25 | 134.425 | 672.125 | 0 | 672.125 | (May think about alternatives to Fused Silica)
1.3.1.3.2 | Support structure | 2 | 4 | 30 | 40 | 200 | 187.08 | 257.08 |  | 25 | 64.27 | 321.35 | 0 | 321.35
1.3.1.4 | Detector | 18 | 32 | 270 | 320 | 1700 | 1590.18 | 2180.18 |  |  | 435.8525 | 2616.0325 | 0 | 2616.0325
1.3.1.4.1 | 64 ch. MaPMT (qty 1000) | 4 | 6 | 60 | 60 | 1600 | 1496.64 | 1616.64 |  | 25 | 404.16 | 2020.8 |  | 2020.8 | Cost is from Hamamatsu for H-8500 MaPMT
1.3.1.4.2 | HV distribution | 4 | 2 | 60 | 20 | 50 | 46.77 | 126.77 |  | 25 | 31.6925 | 158.4625 |  | 158.4625
1.3.1.4.3 | MaPMT assembly | 4 | 12 | 60 | 120 | 50 | 46.77 | 226.77 |  | 25 | 56.6925 | 283.4625 |  | 283.4625
1.3.1.4.4 | Testing | 6 | 12 | 90 | 120 | 0 | 0 | 210 |  | 25 | 52.5 | 262.5 |  | 262.5
1.3.1.5 | Calibration System | 1 | 3 | 0 | 30 | 20 | 18.708 | 49.1472 |  |  | 9.2093 | 58.3565 |  | 58.3565
1.3.1.5.1 | Pulser (qty 4) |  |  | 0 | 0 | 10 | 9.354 | 9.354 |  | 25 | 2.3385 | 11.6925 |  | 11.6925
1.3.1.5.2 | Fibers |  | 1 | 0 | 10 | 5 | 4.677 | 14.677 |  | 25 | 3.6692 | 18.3463 |  | 18.3463
1.3.1.5.3 | Optical components |  |  | 0 | 0 | 3 | 2.8062 | 2.8062 |  | 25 | 0.70155 | 3.5078 |  | 3.5078
1.3.1.5.4 | Integration | 1 | 1 | 0 | 10 | 2 | 1.8708 | 12.31 |  | 25 | 0 | 12.31 |  | 12.31
1.3.1.5.5 | Testing |  | 1 | 0 | 10 | 0 | 0 | 10 |  | 25 | 2.5 | 12.5 |  | 12.5
1.3.1.6 | Mechanical Utilities | 4 | 8 | 60 | 80 | 20 | 18.708 | 158.708 | 100 | 25 | 39.677 | 198.385 | 100 | 198.385
1.3.1.7 | System Integration | 48 | 96 | 720 | 960 | 0 | 0 | 1680 |  | 25 | 420 | 2100 |  | 2100
1.7.3 | Electronics (FE) |  |  |  |  | 1594 | 1491.0276 | 1827.7716 |  | 350 | 456.9429 | 2284.7145 |  |  | Cost of electronics estimated by Gunther. Not Summed
1.7.3.1 | FE-IC proto | 0 |  | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0
1.7.3.2 | FE-IC prod (qty 4000) | 2.4944 |  | 37.416 |  | 275 | 257.235 | 294.651 |  | 25 | 73.6628 | 368.3138 |  |  | IC's:
1.7.3.3 | FPGA (qty 1000) | 3.7416 |  | 56.124 |  | 200 | 187.08 | 243.204 |  | 25 | 60.801 | 304.005 |  |  | Assume 4-ch=10sqmm->16-ch ~ 40sqmm
1.7.3.4 | FE assembly (qty 1000) | 3.118 |  | 46.77 |  | 100 | 93.54 | 140.31 |  | 25 | 35.0775 | 175.3875 |  |  | TSMC IC:
1.7.3.5 | Cables (qty 1000) | 0.6236 |  | 9.354 |  | 70 | 65.478 | 74.832 |  | 25 | 18.708 | 93.54 |  |  | 155k mask, 2 lots x 50k ~250k, assume 2 lots since one run won't yield spares
1.7.3.6 | DFB equi (qty 15) | 3.7416 |  | 56.124 |  | 75 | 70.155 | 126.279 |  | 25 | 31.5697 | 157.8487 |  |  | plus add $25k M&S for testing
1.7.3.7 | DCC (qty 1) | 1.8708 |  | 28.062 |  | 15 | 14.031 | 42.093 |  | 25 | 10.5233 | 52.6163
1.7.3.8 | PDB (qty 1) | 0 |  | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0
1.7.3.9 | Crates & LV Supplies | 0 |  | 0 |  | 98 | 91.6692 | 91.6692 |  | 25 | 22.9173 | 114.5865
1.7.3.10 | prototyping (qty 12) | 6.236 |  | 93.54 |  | 50 | 46.77 | 140.31 |  | 25 | 35.0775 | 175.3875
1.7.3.11 | Final installation | 0.6236 |  | 9.354 |  | 10 | 9.354 | 18.708 |  | 25 | 4.677 | 23.385
1.7.3.12 | HT Power Supplies |  |  |  |  | 282 | 263.7828 | 263.7828 |  | 25 | 65.9457 | 329.7285
1.7.3.13 | Infrastructure and Monitor |  |  |  |  | 321 | 300.2634 | 300.2634 |  | 25 | 75.0658 | 375.3293 |  |  | Rationalized cost
1.7.3.14 | Electronics test Bench |  |  |  |  | 98 | 91.6692 | 91.6692 |  | 25 | 22.9173 | 114.5865
Option B
3 | PID
1.3.1 | DIRC barrel - Focusing DIRC | 92 | 179 | 1365 | 1790 | 7440 | 6959.376 | 10114.8152 | 6728 |  | 2416.4338 | 12531.249 | 1950.75 | 17308.499
1.3.1.1 | Radiator Support Structure | [6 empty] | 0 | 2372 |  |  | 0 | 0 | 2372
1.3.1.2 | Radiator Bars and Assemblies | 5 | 8 | 75 | 80 | 3000 | 2806.2 | 2961.2 | 4256 |  | 740.3 | 3701.5 | 1850.75 | 6106.75
1.3.1.2.1 | Fused Silica coupling | 5 | 8 | 75 | 80 | 3000 | 2806.2 | 2961.2 |  | 25 | 740.3 | 3701.5 |  | 3701.5 | Assume that we have 12 optical couplings, each $200K
1.3.1.3 | Standoff box | 4 | 8 | 60 | 80 | 700 | 654.78 | 794.78 |  |  | 198.695 | 993.475 |  | 993.475
1.3.1.3.1 | Box | 2 | 4 | 30 | 40 | 500 | 467.7 | 537.7 |  | 25 | 134.425 | 672.125 |  | 672.125
1.3.1.3.2 | Support structure | 2 | 4 | 30 | 40 | 200 | 187.08 | 257.08 |  | 25 | 64.27 | 321.35 |  | 321.35
1.3.1.4 | Detector | 18 | 32 | 270 | 320 | 3700 | 3460.98 | 4050.98 |  |  | 903.5525 | 4954.5325 |  | 4954.5325
1.3.1.4.1 | 256 ch. MaPMT (qty 1000) | 4 | 6 | 60 | 60 | 3600 | 3367.44 | 3487.44 |  | 25 | 871.86 | 4359.3 |  | 4359.3 | Cost is from Hamamatsu for H-9500 MaPMT
1.3.1.4.2 | HV distribution | 4 | 2 | 60 | 20 | 50 | 46.77 | 126.77 |  | 25 | 31.6925 | 158.4625 |  | 158.4625
1.3.1.4.3 | MaPMT assembly | 4 | 12 | 60 | 120 | 50 | 46.77 | 226.77 |  | 25 | 56.6925 | 283.4625 |  | 283.4625
1.3.1.4.4 | Testing | 6 | 12 | 90 | 120 | 0 | 0 | 210 |  | 25 | 52.5 | 262.5 |  | 262.5
1.3.1.5 | Calibration System | 1 | 3 | 0 | 30 | 20 | 18.708 | 49.1472 |  |  | 9.2093 | 58.3565 |  | 58.3565
1.3.1.5.1 | Pulser (qty 4) |  |  | 0 | 0 | 10 | 9.354 | 9.354 |  | 25 | 2.3385 | 11.6925 |  | 11.6925
1.3.1.5.2 | Fibers |  | 1 | 0 | 10 | 5 | 4.677 | 14.677 |  | 25 | 3.6692 | 18.3463 |  | 18.3463
1.3.1.5.3 | Optical components |  |  | 0 | 0 | 3 | 2.8062 | 2.8062 |  | 25 | 0.70155 | 3.5078 |  | 3.5078
1.3.1.5.4 | Integration | 1 | 1 | 0 | 10 | 2 | 1.8708 | 12.31 |  | 25 | 0 | 12.31 |  | 12.31
1.3.1.5.5 | Testing |  | 1 | 0 | 10 | 0 | 0 | 10 |  | 25 | 2.5 | 12.5 |  | 12.5
1.3.1.6 | Mechanical Utilities | 4 | 8 | 60 | 80 | 20 | 18.708 | 158.708 | 100 | 25 | 39.677 | 198.385 | 100 | 198.385
1.3.1.7 | System Integration | 60 | 120 | 900 | 1200 | 0 | 0 | 2100 |  | 25 | 525 | 2625 |  | 2625
1.7.3 | Electronics (FE) |  |  |  |  | 1594 | 1491.0276 | 1827.7716 |  | 350 | 456.9429 | 2284.7145 |  |  | Cost of electronics estimated by Gunther. Not Summed
1.7.3.1 | FE-IC proto | 0 |  | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0
1.7.3.2 | FE-IC prod (qty 4000) | 2.4944 |  | 37.416 |  | 375 | 350.775 | 388.191 |  | 25 | 97.0477 | 485.2387 |  |  | IC's:
1.7.3.3 | FPGA (qty 1000) | 3.7416 |  | 56.124 |  | 200 | 187.08 | 243.204 |  | 25 | 60.801 | 304.005 |  |  | TSMC IC: | rect 20x20 mm, 55 copies/wafer, 6 of 12 wafers guaranteed: no issue with getting 1,000 device from one lot
1.7.3.4 | FE assembly (qty 1000) | 3.118 |  | 46.77 |  | 100 | 93.54 | 140.31 |  | 25 | 35.0775 | 175.3875 |  |  | 155k mask, 1 lots x 50k ~200k
1.7.3.5 | Cables (qty 1000) | 0.6236 |  | 9.354 |  | 70 | 65.478 | 74.832 |  | 25 | 18.708 | 93.54 |  |  | plus add $25k M&S for testing
1.7.3.6 | DFB equi (qty 15) | 3.7416 |  | 56.124 |  | 75 | 70.155 | 126.279 |  | 25 | 31.5697 | 157.8487
1.7.3.7 | DCC (qty 1) | 1.8708 |  | 28.062 |  | 15 | 14.031 | 42.093 |  | 25 | 10.5233 | 52.6163
1.7.3.8 | PDB (qty 1) | 0 |  | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0
1.7.3.9 | Crates & LV Pwr Supplies | 0 |  | 0 |  | 119 | 111.3126 | 111.3126 |  | 25 | 27.8282 | 139.1407
1.7.3.10 | prototyping (qty 12) | 6.236 |  | 93.54 |  | 50 | 46.77 | 140.31 |  | 25 | 35.0775 | 175.3875
1.7.3.11 | Final installation | 0.6236 |  | 9.354 |  | 10 | 9.354 | 18.708 |  | 25 | 4.677 | 23.385
1.7.3.12 | HT Power Supplies |  |  |  |  | 282 | 263.7828 | 263.7828 |  | 25 | 65.9457 | 329.7285
1.7.3.13 | Infrastructure and Monitor |  |  |  |  | 200 | 187.08 | 187.08 |  | 25 | 46.77 | 233.85 |  |  | Rationalized cost
1.7.3.14 | Electronics test Bench |  |  |  |  | 98 | 91.6692 | 91.6692 |  | 25 | 22.9173 | 114.5865

## 1.3.2 Forward PID
|  | Engineering | Technician | EDIA kEuro | LABOR kEuro | M&S | M&S | Subtotal | Contingency | Contingency | Total Cost | Comment
|  | [mm] | [mm] | 15 | 10 | k$ | kEuro | kEuro | % | Keuros
1.3 | PID
1.3.2 | Forward TOF | 32 | 70 | 480 | 1050 | 3426 | 2638.02 | 3818.02 | 25 | 852.355 | 4670.375
1.3.2.1 | Support structure | 3 | 3 | 45 | 30 | 75 | 57.75 | 132.75 |  | 33.1875 | 165.9375
1.3.2.1.1 | Support structure | 3 | 3 | 45 | 30 | 75 | 57.75 | 132.75 | 25 | 33.1875 | 165.9375
1.3.2.2 | Radiator/Detector box | 6 | 10 | 90 | 450 | 220 | 169.4 | 359.4 |  | 46.75 | 406.15
1.3.2.2.1. | Radiator Fused silica tiles | 2 | 5 | 30 | 50 | 120 | 92.4 | 172.4 | 25 | 0 | 172.4
1.3.2.1.2 | Radiator/Detector box | 4 | 5 | 60 | 50 | 100 | 77 | 187 | 25 | 46.75 | 233.75
1.3.2.3 | Detector | 5 | 18 | 75 | 180 | 3010 | 2317.7 | 2572.7 |  | 584.125 | 3156.825
1.3.2.3.1 | PMT (qty 1000) | 1 | 3 | 15 | 30 | 2900 | 2233 | 2278 | 25 | 569.5 | 2847.5 | Cost is from P. Hinks of Burle/Photonis for a 1 channel/tube
1.3.2.3.2 | HV distribution |  | 2 | 0 | 20 | 50 | 38.5 | 58.5 | 25 | 14.625 | 73.125 | If we need 4 channels/tube the cost will go to $3.2k/tube
1.3.2.3.3 | Radiator/PMT Assembly | 4 | 12 | 60 | 120 | 60 | 46.2 | 226.2 | 25 | 56.55 | 282.75
1.3.2.3.4 | Testing |  | 1 | 0 | 10 |  | 0 | 10 | 25 | 2.5 | 12.5
1.3.2.4 | Calibration System | 0 | 3 | 0 | 30 | 21 | 16.17 | 46.17 |  | 11.5425 | 57.7125
1.3.2.4.1 | Pulser (qty 4) |  |  | 0 | 0 | 10 | 7.7 | 7.7 | 25 | 1.925 | 9.625
1.3.2.4.2 | Fibers |  | 1 | 0 | 10 | 5 | 3.85 | 13.85 | 25 | 3.4625 | 17.3125
1.3.2.4.3 | Optical components |  |  | 0 | 0 | 3 | 2.31 | 2.31 | 25 | 0.5775 | 2.8875
1.3.2.4.4 | Integration |  | 1 | 0 | 10 | 3 | 2.31 | 12.31 | 25 | 3.0775 | 15.3875
1.3.2.4.5 | Testing |  | 1 | 0 | 10 |  | 0 | 10 | 25 | 2.5 | 12.5
1.3.2.7 | Integration and assembly | 18 | 36 | 270 | 360 | 100 | 77 | 707 | 25 | 176.75 | 883.75
1.3.2.7.1 | System | 18 | 36 | 270 | 360 | 100 | 77 | 707 | 25 | 176.75 | 883.75
This should go in the electronics WBS
1.3.2.5 | Electronics (FE) | 42.6067 |  | 639.1 |  | 750 | 577.5 | 1216.6 |  | 304.15 | 1520.75 | Cost of electronics estimated by Gunther
1.3.2.5.1 | FE-IC proto (qty 1) | 25.6667 |  | 385 |  | 250 | 192.5 | 577.5 | 25 | 144.375 | 721.875
1.3.2.5.2 | FE-IC prod (qty 1000) | 2.0533 |  | 30.8 |  | 225 | 173.25 | 204.05 | 25 | 51.0125 | 255.0625 | IC's:
1.3.2.5.3 | FPGA prod (qty 1000) | 2.0533 |  | 30.8 |  | 25 | 19.25 | 50.05 | 25 | 12.5125 | 62.5625 | TSMC IC: rect 20x20 mm, 55 copies/wafer, 6 of 12 wafers guaranteed: no issue with getting 1,000 device from one lot
1.3.2.5.4 | FE assembly (qty 1000) | 2.5667 |  | 38.5 |  | 100 | 77 | 115.5 | 25 | 28.875 | 144.375 | 155k mask, 1 lots x 50k ~200k
1.3.2.5.5 | DFB equi (qty 15) | 3.08 |  | 46.2 |  | 75 | 57.75 | 103.95 | 25 | 25.9875 | 129.9375 | plus add $25k M&S for testing
1.3.2.5.6 | DCC (qty 1) | 1.54 |  | 23.1 |  | 15 | 11.55 | 34.65 | 25 | 8.6625 | 43.3125 | FPGA each serving one PMT, DFB each serving 64 PMT's, 15 DFB's in 1 crate
1.3.2.5.7 | PDB (qty 1) | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 0 | 0 | Assume reuse of PDB and crate, othwise need to add $.
1.3.2.5.8 | Crates (qty 1) | 0 |  | 0 |  | 0 | 0 | 0 | 25 | 0 | 0 | Large unknown is EDI for prototype. Specifications could make this one very expensive.
1.3.2.5.9 | prototyping (qty 12) | 5.1333 |  | 77 |  | 50 | 38.5 | 115.5 | 25 | 28.875 | 144.375 | May need more than 500k for NRE to get final perfect performing device, definitly need large contingency
1.3.2.5.10 | Final installation | 0.51333 |  | 7.7 |  | 10 | 7.7 | 15.4 | 25 | 3.85 | 19.25

## 1.4.1 Barrel EMC
|  | New costs |  |  | Replacement costs
|  | Engineering | Technician | M&S | Engineering | Technician | Engineering | Labor | M&S | M&S | M&S | TOTAL REPLACEMENT COST | Basis of Estimate
|  | [mm] | [mm] | [Keuro(2007)] | [mm] | [mm] | KE2007 | KE2007 | [ $K (1996,7)] | [$K (1995)] | [Keuro(2007)] | KE2007
[5 empty] | (168hr/mm) | (168hr/mm) | Needed because these are replacement costs |  | (avg yr expend) | (=1996,7/1.03) | (=1995*1.21) |  | manpower estimates derived from reported project costs and wage scales, with a suitable mix of manpower based on wjw memory of participants
1.4 | EMC
1.4.1 | Barrel EMC | 20 | 5 | 170.8 | 170.7 | 362.1 | 2560.5 | 3621 | 20377.6 | 19784.0777 | 23938.734 | 30120.234
1.4.1.1 | Crystal Procurement |  |  |  | 16.4 | 95.1 | 246 | 951 | 16482.9 | 16002.8155 | 19363.4068 | 20560.4068
1.4.1.1.1 | Development |  |  |  | 3.8 | 9.1 | 57 | 91 | 310.8 | 301.7476 | 365.1146 |  | BaBar SLAC actuals
1.4.1.1.2 | Salt Production |  |  |  | 0 | 0 | 0 | 0 | 2843.6 | 2760.7767 | 3340.5398 |  | BaBar SLAC actuals adjusted for endcap (removed) and Dresden rings (added)
1.4.1.1.3 | Crystal Production |  |  |  | 6 | 18.8 | 90 | 188 | 13209.3 | 12824.5631 | 15517.7214 |  | BaBar SLAC actuals adjusted for endcap (removed) and Dresden rings (added)
1.4.1.1.4 | Facilities (store and measure) |  |  |  | 3 | 8.8 | 45 | 88 | 39.7 | 38.5437 | 46.6379 |  | BaBar SLAC actuals
1.4.1.1.5 | Crystal Q/C \& tune |  |  |  | 3.6 | 58.4 | 54 | 584 | 79.5 | 77.1845 | 93.3932 |  | BaBar SLAC actuals adjusted for endcap (removed)
1.4.1.2 | Light Sensors \& Readout |  |  |  | 33.6 | 68.8 | 504 | 688 | 1173 | 1138.835 | 1377.9903 | 2569.9903 | includes photodiodes, preamps, cables to end-flange, end-flange crates including fanout and backplane, cooling of preamps
1.4.1.2.1 | Development |  |  |  | 1.8 | 0 | 27 | 0 | 12 | 11.6505 | 14.0971 |  | BaBar SLAC actuals
1.4.1.2.2 | Diodes \& Test |  |  |  | 6 | 12 | 90 | 120 | 667 | 647.5728 | 783.5631 |  | approximate manpower use; quote for diode prices ($637K); test equipment
1.4.1.2.3 | Diode package: dsgn, fab, install |  |  |  | 6 | 36 | 90 | 360 | 44 | 42.7184 | 51.6893 |  | estimate by wjw
1.4.1.2.4 | Preamp: design, fab, test |  |  |  | 12 | 12 | 180 | 120 | 310 | 300.9709 | 364.1748 |  | estimate by wjw with input from gxh
1.4.1.2.5 | Cable procurement |  |  |  | 0.3 | 0.5 | 4.5 | 5 | 36 | 34.9515 | 42.2913 |  | recollection by wjw
1.4.1.2.6 | Preamp cooling, end-flange crates |  |  |  | 7.5 | 8.3 | 112.5 | 83 | 104 | 100.9709 | 122.1748 |  | actuals
1.4.1.3 | Crystal Support Modules |  |  |  | 42.8 | 135.2 | 642 | 1352 | 706.9 | 686.3107 | 830.4359 | 2824.4359
1.4.1.3.1 | Design \& Prototype |  |  |  | 20.2 | 23 | 303 | 230 | 90.2 | 87.5728 | 105.9631 |  | actuals with estimated manpower mix
1.4.1.3.2 | Fab Facility \& Tooling |  |  |  | 6.2 | 19.8 | 93 | 198 | 208.1 | 202.0388 | 244.467 |  | actuals with estimated manpower mix
1.4.1.3.3 | Fabrication |  |  |  | 10 | 51.8 | 150 | 518 | 126.3 | 122.6214 | 148.3718 |  | actuals with estimated manpower mix
1.4.1.3.4 | Module Assembly |  |  |  | 2.4 | 31.6 | 36 | 316 | 277.5 | 269.4175 | 325.9951 |  | actuals with estimated manpower mix
1.4.1.3.5 | Module test |  |  |  | 4 | 9 | 60 | 90 | 4.8 | 4.6602 | 5.6388 |  | actuals with estimated manpower mix
1.4.1.4 | Barrel Structure |  |  |  | 60.1 | 56 | 901.5 | 560 | 1570.5 | 1524.7573 | 1844.9563 | 3306.4563
1.4.1.4.1 | Support cylinder \& closure structures |  |  |  | 32.9 | 19.6 | 493.5 | 196 | 1122 | 1089.3204 | 1318.0777 |  | actuals with estimated manpower mix
1.4.1.4.2 | Barrel assembly facilities |  |  |  | 4.2 | 9 | 63 | 90 | 163.5 | 158.7379 | 192.0728 |  | actuals with estimated manpower mix
1.4.1.4.3 | Assembly fixtures and assembly |  |  |  | 19.7 | 27.3 | 295.5 | 273 | 238.8 | 231.8447 | 280.532 |  | actuals with estimated manpower mix
1.4.1.4.4 | Installation into magnet |  |  |  | 3.3 | 0.1 | 49.5 | 1 | 46.2 | 44.8544 | 54.2738 |  | costs to calorimeter team only
1.4.1.5 | Calibration Systems |  |  |  | 9.8 | 7 | 147 | 70 | 347.7 | 337.5728 | 408.4631 | 625.4631
1.4.1.5.1 | Source calibration |  |  |  | 9.8 | 7 | 147 | 70 | 197.7 | 191.9417 | 232.2495 |  | actuals with estimated manpower mix
1.4.1.5.2 | Light pulser system |  |  |  | 0 | 0 | 0 | 0 | 150 | 145.6311 | 176.2136 |  | WAG. Physicists provided all EDIA and Labor.
1.4.1.6 | Project Management |  |  |  | 8 | 0 | 120 | 0 | 96.6 | 93.7864 | 113.4816 | 233.4816
New Costs
1.4.1.7 | Barrel Transport | 20 | 5 | 170.8 | [8 empty] | 135.4Keuro new M&S
1.4.1.7.1 | Engineering Feasibility: Unit Transport | 15 | 0
1.4.1.7.1.1 | finite element model resurrection | 4 | 0 | N/A | [8 empty] | Hodgson model. Skarpaas as consultant for Hodgson guidance. (3:1) (wjw estimate, HJK concurrence)
1.4.1.7.1.2 | design cradle for transport | 8 | 0 | N/A | [8 empty] | requires draftsman and engineer, equal time. (wjw estimate, HJK concurrence)
1.4.1.7.1.3 | finite element model of barrel in cradle | 3 | 0 | N/A | [8 empty] | supervising engineer; analyst. (1:2) (wjw estimate, HJK concurrence)
1.4.1.7.2 | Cradle fabrication | 5 | 5 | 170.8
1.4.1.7.2.1 | Forward suspension fixturing | 5 | 1 | 35.4 | [8 empty] | reuse tooling from LST upgrade load transfer. Actual costs 2006.
1.4.1.7.2.2 | Backward suspension fixturing | 0 | 1 | 35.4 | [8 empty] | new tooling, costs based on actuals: $45,945 = 35.4Keuro
1.4.1.7.2.3 | cradle frame | 0 | 3 | 100 | [8 empty] | new frame. WAG: wjw & HJK
note: use flexible supports

## 1.4.2 Forward EMC
|  | Engineering | Technician | M&S | Basis of Estimate
|  | [mm] | [mm] | [Keuro(2007)]
|  | (168hr/mm) | (168hr/mm)
1.4 | EMC |  |  |  | note: BaBar actual = BaBar barrel actual (reuse estimate), when called out below.
1.4.2 | Forward EMC | 73.3121 | 152.4173 | 6828.0521
1.4.2.1 | Crystal Procurement | 11.1073 | 44.3611 | 5542 | philosophy: when scaling BaBar actuals from the CsI barrel experience, scale by LSO/CsI crystal count
1.4.2.1.1 | Development | 3.8 | 9.1 | 78 | use array 6 crystals wide, last 6 rows in phi. Qualify 2 vendors 3x6. use $15/cc. sensor: 3.7K euro ( assume $135/sensor small count); 20K electronics.
1.4.2.1.3 | Crystal Production | 6 | 18.8 | 5400 | high value from the CDR
1.4.2.1.4 | Facilities (measure) | 0.51979 | 3.6861 | 23.1 | base on BaBar prep experience, dry room costs removed.
1.4.2.1.5 | Crystal Q/C \& tune | 0.7875 | 12.775 | 40.9 | use BaBar CsI(Tl) Q/C costs. Tuning for uniformity likely to be unnecessary: this represented about 50% of BaBar effort; halve manpower needs, adjust for 2520/5760.
assume test equipment needs for Q/C scale with crystal quantity: 2520/5760
1.4.2.2 | Light Sensors \& Readout | 23.3 | 31.3 | 459.5 | philosophy: when scaling BaBar actuals from the CsI barrel experience, scale by LSO/CsI crystal count
1.4.2.2.1 | Development | 1.8 | 0 | 14.1 | use BaBar cost
1.4.2.2.2 | Diodes \& Test | 6 | 5.25 | 300.1 | ED&I: use BaBar actual. Labor: use BaBar scaled by number of diodes:basis 2520 crystals x 2 photodiodes (note time to test 1 APD likely to be ~same as 2 PD). Cost(conservative): quote for CMS APD (non-CMS quantity) ~$135; PD BBR 112*1.21~$135--> just scale by count 2520/6580.
1.4.2.2.3 | Diode package: dsgn, fab, install | 6 | 15.75 | 22.6 | ED&I: use BaBar actual. Labor: use BaBar scaled by number of diodes: 2520/5760. M&S scale by count 2520/5760.
1.4.2.2.4 | Cable procurement | 2 | 2 | 15.8 | ED&I: cable issue more complicated than barrel: requires complicated mock-up. Scale M&S by count (fat: length much less, but connector count same/crystal)
1.4.2.2.5 | Preamp cooling, support plate crates | 7.5 | 8.3 | 106.9 | ED&I: use BaBar actual. Complex routing. For APD, cooling is critical; less so for PD. M&S: take into account complexity-double cost after count correction
1.4.2.3 | Crystal Support Modules | 18.725 | 59.15 | 315.5513 | philosophy: when scaling BaBar actuals from the CsI barrel experience, scale by LSO/CsI crystal count. (Note: this estimate may be somewhat fat)
1.4.2.3.1 | Design \& Prototype | 8.8375 | 10.0625 | 46.375 | Scale barrel costs by crystal count. (M&S may be somewhat light)
1.4.2.3.2 | Fab Facility \& Tooling | 2.7125 | 8.6625 | 59.1763 | Scale barrel ED&I and Labor actuals by LSO/CsI count ratio. Scale barrel M&S for facilities actuals by volume ratio (.36/5.18~1/14) and tooling by LSO/CsI count ratio (measure of length of material between crystals); the tooling cost is likely be an overestimate, since number of module types for EC is likely to be smaller than the scaling would indicate.
1.4.2.3.3 | Fabrication | 4.375 | 22.6625 | 64.925 | Scale barrel costs by crystal count.
1.4.2.3.4 | Module Assembly | 1.05 | 13.825 | 142.625 | Scale barrel costs by crystal count.
1.4.2.3.5 | Module test | 1.75 | 3.9375 | 2.45 | Scale barrel costs by crystal count.
1.4.2.4 | Endcap Structure | 14.9313 | 16.5125 | 357.3933 | philosopy: when scaling BaBar actuals from the CsI barrel experience, scale by CsI(endcap BaBar)/CsI(barrel BaBar) crystal count ratio (closer to a solid angle argument)
1.4.2.4.1 | Support plate \& closure structures | 5.1406 | 3.0625 | 205.9531 | support plate is much simpler than barrel swiss cheese. Scale by CsI barrel/endcap crystal ratio: 900/5760.
1.4.2.4.2 | Endcap assembly facilities | 0.65625 | 1.4062 | 13.7214 | facilities do not require humidity control; temperature control is more straightforward. Design and labor: scale by crystal count(900/5760). Scale facility M&S by crystal volume(14).
1.4.2.4.3 | Assembly fixtures and assembly | 8.6188 | 11.9437 | 122.7188 | Scale barrel costs by crystal count (LSO:CsI--2520/5760) since assembly is driven by actual crystals installed.
1.4.2.4.4 | Installation onto barrel | 0.51562 | 0.1 | 15 | Estimator judgement
1.4.2.5 | Calibration Systems | 1.5312 | 1.0938 | 100.8688
1.4.2.5.1 | Source calibration | 1.5312 | 1.0938 | 23.7812 | Scale barrel costs by crystal count for EDIA & Labor (900/5760). Subtract neutron generator cost and scale M&S by crystal count.
1.4.2.5.2 | Light pulser system | 0 | 0 | 77.0875 | Scale barrel costs by crystal count
1.4.2.6 | Project Management | 3.7173 | 0 | 52.7388 | Scale barrel costs by ratio of project engineering duration as measured by ED&I:75.6/162.7

## 1.4.3 Backward EMC
|  | Engineering | Technician | M&S | Basis of Estimate
|  | [mm] | [mm] | [Keuro(2007)]
|  | (168hr/mm) | (168hr/mm) |  | This is a real WAG in the absence of details in the CDR. Fig 4-2 provides some guidance, but looks like coverage is marginal. Will assume:
1. CsI (pure) outside the DIRC. 240 crystals. $4/cc
1.a. 50th ring overlaps the flange, consequently, it is likely to be about half length. Assume half volume of ring 48.
1.b. 49th ring may need to be shorter. However, for estimate purposes, assume volume as ring 48.
2. LSO behind the DCH endplate. $15/cc
2.a. OD. As drawn, the calorimeter clears the DIRC support tube. Assume able to install a larger OD wedge for costing: to 80.5cm.
2.b. Crystal length. Appears that full length crystals (20cm) (17.5 r.l.)can fit. However, leaves no provision structure, readout, etc.
Assume crystal is only 10r.l. deep (12cm).
[5 empty] | 2.c. Take ID as 54.9. | 54.9072
[5 empty] | 2.d. Annulus volume = .13 cu m. | 130674.475
1.4 | EMC
1.4.3 | Backward EMC | 42.2729 | 65.0227 | 3095.7632
1.4.3.1 | Crystal Procurement | 1.1094 | 7.6132 | 2446.476
1.4.3.1.1 | Development (LSO \\& CsI) | 0 | 0 | 14.1064 | forward EC LSO provides vendor development and experience with material. Need a few short crystals. Pure CsI also need a few short crystals.
1.4.3.1.2 | Crystal Production (LSO) | 0 | 0 | 1950 | forward EC LSO cost scaled by .13/.36. (Assumptions above probably lead to an overestimate here)
1.4.3.1.3 | Crystal Production (CsI) | 0.25 | 0.78333 | 462.3696 | barrel scaled by fraction of crystals (240/5760)
1.4.3.1.4 | Facilities (measure) | 0.5 | 1 | 10 | dry closet for CsI storage: engineering estimate
1.4.3.1.5 | Crystal Q/C \\& tune | 0.35938 | 5.8299 | 10 | assume test equipment for LSO common with forward EC, so no M&S cost. Test equipment for CsI estimate 10K euro. Scale labor: LSO (.13/.36), CsI (240/5760)
assume crystal tuning not needed.
1.4.3.2 | Light Sensors \& Readout | 4.2882 | 17.0087 | 198.9042 | APDs needed for CsI; PD or APD ok for LSO
1.4.3.2.1 | Development | 1.8 | 0 | 5 | WAG
1.4.3.2.2 | Diodes \& Test | 0 | 5.25 | 133.3174 | Labor: scale forward endcap for LSO readout (.13/.36). Add in CsI (240 crystals at $135 each)
1.4.3.2.2 | Diode package: dsgn, fab, install | 0 | 7.1094 | 10.2014 | scale forward EC with a factor of 1.25 to account for CsI and .13/.36 to account for backward/forward ratio.
1.4.3.2.3 | Cable procurement | 0.90278 | 0.90278 | 7.1319 | scale forward EC with a factor of 1.25 to account for CsI and .13/.36 to account for backward/forward ratio.
1.4.3.2.4 | Preamp cooling, support plate crates | 3.3854 | 3.7465 | 48.2535 | scale forward EC with a factor of 1.25 to account for CsI and .13/.36 to account for backward/forward ratio. M&S is likely an overestimate.
1.4.3.3 | Crystal Support Modules | 8.1251 | 31.4316 | 225.7453
1.4.3.3.1 | Design \& Prototype CsI | 0 | 0 | 0 | assume that techniques used in barrel can be straighforwardly applied.
1.4.3.3.2 | Design \& Prototype LSO | 3.1913 | 3.6337 | 16.7465 | scale forward EC by LSO volume ratio. This is likely an underestimate, but smaller radial extent may simplify.
1.4.3.3.3 | Fab Facility \& Tooling | 0 | 0 | 66.2788 | use forward facilities for fab. Tooling for LSO take to be 50 Keuro. Tooling for CsI: use barrel actuals, scale by 1/7 for modules.
1.4.3.3.4 | Fabrication | 3.0084 | 15.5837 | 44.6451 | scale forward EC by LSO volume ratio for LSO fab estimate. Scale barrel by 1/7 for CsI
1.4.3.3.5 | Module Assembly | 0.72202 | 9.5066 | 98.0749 | scale forward EC by LSO volume ratio for LSO fab estimate. Scale barrel by 1/7 for CsI
1.4.3.3.6 | Module test | 1.2034 | 2.7076 | 0 | scale forward EC by LSO volume ratio for LSO fab estimate. Scale barrel by 1/7 for CsI. No M&S: use forward EC equipment
1.4.3.4 | Endcap Structure LSO | 8.7686 | 7.8755 | 148.6871
1.4.3.4.1 | Support plate \& closure structures | 5.1406 | 3.0625 | 74.372 | keep forward ED&I and labor. Scale plate by volume ratio.
1.4.3.4.2 | Endcap assembly facilities | 0 | 0 | 0 | use forward endcap facilities
1.4.3.4.3 | Assembly fixtures and assembly | 3.1123 | 4.313 | 44.3151 | scale forward EC by LSO volume ratio. This gives the right ball park (gut estimation) for ED&I, Labor & M&S
1.4.3.4.4 | Installation into support tube barrel | 0.51562 | 0.5 | 30 | estimator judgement
1.4.3.5 | Extended Barrel Structure CsI | 17 | 11 | 105.98 | this is a problematic item. Significant FEA needed.
1.4.3.5.1 | Module support/bell housing replace | 9 | 3 | 45.98 | estimator judgement
1.4.3.5.2 | Module install tooling \& install | 6 | 6 | 40 | estimator judgement
1.4.3.5.3 | Environmental closure | 2 | 2 | 20 | estimator judgement
1.4.3.6 | Calibration Systems | 1 | 1.0938 | 47.8372
1.4.3.6.1 | Source calibration for LSO | 1 | 1.0938 | 20 | estimator judgement
1.4.3.6.2 | Light pulser system | 0 | 0 | 27.8372 | scale forward EC by LSO volume
1.4.3.7 | Project Management | 1.9816 | 0 | 28.1134 | Scale barrel costs by ratio of project engineering duration as measured by ED&I:40.3/162.7

## 1.5 IFR
|  | Engineering | Technician | EDIA [Keuro] | LABOR[Keuro} | M&S | Subtot | Cont. | Contingency [keuro] | Total
|  | [mm] | [mm] |  |  | [1000 Euros]
9 | Barrel IFR (RPC) |  |  | 0 | 58.7223 | 130.7531 | 199.2624 |  | 39.8525 | 1816.8749
9.1 | Gas Volume | 0 | 0.090661 | 0 | 0.40779 | 0.25768 | 0.66548 |  | 0.1331 | 0.79857
9.1.1 | Bakelite sheet | 0 | 0 | 0 | 0 | 0.14688 | 0.14688 | 0.2 | 0.029375 | 0.17625
9.1.2 | Bakelite cut | 0 | 0.01511 | 0 | 0.067966 | 0 | 0.067966 | 0.2 | 0.013593 | 0.081559
9.1.3 | gap construction | 0 | 0.075551 | 0 | 0.33983 | 0.075808 | 0.41564 | 0.2 | 0.083127 | 0.49876
9.1.4 | HV connectors | 0 | 0 | 0 | 0 | 0.035 | 0.035 | 0.2 | 0.007 | 0.042
9.2 | Chamber |  |  | 0 |  | 0.65033 | 0.71829 |  | 0.14366 | 0.86195
9.2.1 | strip panel | 0 | 0.01511 | 0 | 0.067966 | 0.25 | 0.31797 | 0.2 | 0.063593 | 0.38156
9.2.2 | strip (copper) | 0 | 0 | 0 | 0 | 0.20312 | 0.20312 | 0.2 | 0.040625 | 0.24375
9.2.3 | cables on RPC | 0 | 0 | 0 | 0 | 0.06 | 0.06 | 0.2 | 0.012 | 0.072
9.2.4 | connectors | 0 | 0 | 0 | 0 | 0.0072 | 0.0072 | 0.2 | 0.00144 | 0.00864
9.2.5 | gas tubing | 0 | 0 | 0 | 0 | 0.13 | 0.13 | 0.2 | 0.026 | 0.156
9.3 | QA/QC | 36 | 0 | 306 | 0 | 100 | 406 | 0.2 | 81.2 | 487.2
9.4 | Gas System |  |  |  |  | 103.6 |  |  |  | 141.12
9.4.1 | mixing station | 0 | 1 | 0 | 7 | 70 | 77 | 0.2 | 15.4 | 92.4
9.4.2 | tubing | 0 | 0 | 0 | 0 | 15.6 | 15.6 | 0.2 | 3.12 | 18.72
9.4.3 | distribution chassis | 0 | 1 | 0 | 7 | 18 | 25 | 0.2 | 5 | 30
9.5 | High Voltage | 0 | 0 | 0 | 0 | 140 | 140 | 0.2 | 28 | 168
| Power supply | 0 | 0 | 0 | 0
| Distribution chassis | 0 | 0 | 0 | 0
| cables + connectors | 0 | 0 | 0 | 0
|  | 0 | 0 | 0 | 0
9.6 | Electronics | 0 | 0 | 0 | 0 | 331.2 | 331.2 |  | 66.24 | 397.44
9.6.1 | Preamp | 0 | 0 | 0 | 0 | 187.2 | 187.2 | 0.2 | 37.44 | 224.64
9.6.2 | FEC+crates | 0 | 0 | 0 | 0 | 144 | 144 | 0.2 | 28.8 | 172.8
9.7 | Detector Assembly |  |  | 136 | 84 | 100 | 320 |  | 64 | 384
9.7.1 | shipping | 0 | 0 | 0 | 0 | 100 | 100 | 0.2 | 20 | 120
9.7.2 | installation in situ | 16 | 12 | 136 | 84 | 0 | 220 | 0.2 | 44 | 264
9.8 | Spare | [8 empty] | 0
Notes: | 8.5 | 7 | 0.049133 | 0.017341
bakelite cost/sqm | 0.0235
module area | 3.125
1mm = 24dm = 173hm
# chamber/layer | 3
layers | 8
sextants | 6
| area ratio FWD vs barrel | 0.76509 | 1.307
| eng/phys | 4 | 4.5
| tech | 2.5 | 4.5
| factory tech | 4.498
Barrel only. To get total multiply by 1.51
1.5 | IFR (scintillator) | 37.2 | 36 | 316.2 | 252 | 840 | 1408.2 | 4.45 | 276.15 | 1684.35
1.5.1 | System engineering | 16 | 0 | 136 | 0 | 0 | 136 | 0.25 | 34 | 170
1.5.2 | scintillator strips + WLS fiber | 0 | 0 | 0 | 0 | 212 | 212 | 0.15 | 31.8 | 243.8
1.5.3 | Module factory retooling | 0 | 2 | 0 | 14 | 10 | 24 | 0.75 | 9.5 | 33.5
1.5.3.1 | Materials | 0 | 0 | 0 | 0 | 10 | 10 | 0.25 | 2.5 | 12.5
1.5.3.2 | labor | 0 | 2 | 0 | 14 | 0 | 14 | 0.5 | 7 | 21
1.5.4 | Module fabrication | 0 | 18 | 0 | 126 | 45 | 171 | 0.8 | 39.75 | 210.75
1.5.4.1 |  | 0 | 0 | 0 | 0 | 33 | 33 | 0.35 | 11.55 | 44.55
1.5.4.2 | QC | 0 | 18 | 0 | 126 | 0 | 126 | 0.2 | 25.2 | 151.2
1.5.4.3 | crate + transport | 0 | 0 | 0 | 0 | 12 | 12 | 0.25 | 3 | 15
1.5.5 | module installation | 0 | 0 | 0 | 0 | 9 | 9 | 0.25 | 2.25 | 11.25
1.5.6 | APD/preamp + cooling system | 3.2 | 0 | 27.2 | 0 | 439 | 466.2 | 0.65 | 73.85 | 540.05
1.5.6.1 | QC & burn-in | 3.2 | 0 | 27.2 | 0 | 0 | 27.2 | 0.25 | 6.8 | 34
1.5.6.2 | module components | 0 | 0 | 0 | 0 | 427 | 427 | 0.15 | 64.05 | 491.05
1.5.6.3 | Power supplies + controls | 0 | 0 | 0 | 0 | 12 | 12 | 0.25 | 3 | 15
1.5.7 | Services | 2 | 4 | 17 | 28 | 9 | 54 | 0.6 | 16.2 | 70.2
1.5.7.1 | Materials | 0 | 0 | 0 | 0 | 9 | 9 | 0.3 | 2.7 | 11.7
1.5.7.2 | Labor | 2 | 4 | 17 | 28 | 0 | 45 | 0.3 | 13.5 | 58.5
1.5.8 | LED pulser system | 0 | 0 | 0 | 0 | 16 | 16 | 0.6 | 4.8 | 20.8
1.5.8.1 | module components | 0 | 0 | 0 | 0 | 8 | 8 | 0.3 | 2.4 | 10.4
1.5.8.2 | drivers + control | 0 | 0 | 0 | 0 | 8 | 8 | 0.3 | 2.4 | 10.4
1.5.9 | Detector Assembly | 16 | 12 | 136 | 84 | 100 | 320 | 0.4 | 64 | 384
1.5.9.1 | shipping | 0 | 0 | 0 | 0 | 100 | 100 | 0.2 | 20 | 120
1.5.9.2 | installation in situ | 16 | 12 | 136 | 84 | 0 | 220 | 0.2 | 44 | 264
0
Electronics should go in the Electronics WBS | [9 empty] | 0
10.10 | Front end electronics |  | 64 |  |  | 141 |  |  |  | 0
10.10.1 | Preamp/discriminator | [8 empty] | 0
| design/test | 0 | 21.6667 | 0 | 151.6667 | 0 | 151.6667 | 0.3 | 45.5 | 197.1667
| prototype | 0 | 0 | 0 | 0 | 25 | 25 | 0.25 | 6.25 | 31.25
| production | 0 | 0 | 0 | 0 | 34 | 34 | 0.3 | 10.2 | 44.2
10.10.2 | preamplifier board | [8 empty] | 0
| design | 0 | 8.6667 | 0 | 60.6667 | 0 | 60.6667 | 0.3 | 18.2 | 78.8667
| prototype | 0 | 0 | 0 | 0 | 3 | 3 | 0.2 | 0.6 | 3.6
| production | 0 | 0 | 0 | 0 | 12 | 12 | 0.2 | 2.4 | 14.4
10.10.3 | cables to DFB | [8 empty] | 0
| production | 0 | 0 | 0 | 0 | 8 | 8 | 0.25 | 2 | 10
10.10.4 | DFB borad | [8 empty] | 0
| design and test | 0 | 30.3333 | 0 | 212.3333 | 0 | 212.3333 | 0.3 | 63.7 | 276.0333
| prototype | 0 | 0 | 0 | 0 | 5 | 5 | 0.2 | 1 | 6
| production | 0 | 0 | 0 | 0 | 13 | 13 | 0.3 | 3.9 | 16.9
| components/panel/connectors | 0 | 0 | 0 | 0 | 26 | 26 | 0.3 | 7.8 | 33.8
| test | 0 | 3.3333 | 0 | 23.3333 | 15 | 38.3333 | 0.2 | 7.6667 | 46
0
scintillator option for 9 layer
IFR

## 1.6 Magnet
|  | Babar total cost |  | Reuse value | Engineering | Technician | M&S | CHECK VALUE | From Babar budget
|  | USD | kEuro | kEuro | mm | mm | [1000 Euros] |  | ENG (hours) | Labor(hours) | M&S (USD)
1.6 | Magnet | 7953 | 9623.13 | 9623.13 | 87 | 46.6905 | 1545.17
1.6.0 | System Management | 477 | 577.17 | 577.17 | 36
1.6.1 | Superconducting solenoid | 1886 | 2282.06 | 2282.06
1.6.2 | Mag. Power/Protection | 141 | 170.61 | 170.61
1.6.3 | Cryogenics | 0 | 0 | 0 | 34.3333 | 35.5 | 1376.98 | 2246.98 | 5768 | 5964 | 1138
1.6.4 | Cryo monitor/Control | 0 | 0 | 0 | 16.6667 | 11.1905 | 168.19 | 530.0948 | 2800 | 1880 | 139
1.6.5 | Flux return | 5048 | 6108.08 | 6108.08
1.6.6 | Installation/test equipment | 401 | 485.21 | 485.21
WAS
1.6.3 | Cryogenics | 1420 | 1718.2 | 1718.2
1.6.4 | Cryo monitor/Control | 465 | 562.65 | 562.65

## 1.7 Electronics
|  | EDIA | Labor | M&S | Basis | Comments
|  | [mm] | [mm] | [1000 Euros]
1.7 | Electronics | 286.0563 | 213 | 5565.3466
1.7.1 | SVT | 11 | 21 | 342.6084
1.7.1.1 | Data Transmission Card | 4 | 9.5 | 127.05 | Gunther
1.7.1.1.1 | Development | 4 | 1.5 | 36.3 | Gunther
1.7.1.1.2 | Production - 148 units |  | 8 | 90.75 | Gunther
1.7.1.2 | Data IO Board | 4 | 7.5 | 96.8 | Gunther
1.7.1.2.1 | Development | 4 | 1.5 | 36.3 | Gunther
1.7.1.2.2 | Production - 74 units |  | 6 | 60.5 | Gunther
1.7.1.3 | LV & Bias | 3 | 4 | 118.7584 | 1.7.1.2.2.5.2 include 20% factor for new L0
1.7.1.4 | Cables
1.7.2 | DCH | 53 | 47 | 1202.74
1.7.2.1 | 4-ch Amplifier ASIC | 12 | 12 | 272.25 | Gunther
1.7.2.1.1 | 4 prototype runs TSMC process | 12 | 6 | 121 | Gunther
1.7.2.1.2 | Production - 2000 units |  | 6 | 151.25 | Gunther
1.7.2.2 | 8-ch TDC ASIC | 12 | 12 | 272.25 | Gunther
1.7.2.2.1 | 4 prototype runs TSMC process | 12 | 6 | 121 | Gunther
1.7.2.2.2 | Production - 1000 units |  | 6 | 151.25 | Gunther
1.7.2.3 | ADB Board | 5 | 3.5 | 96.8 | Gunther
1.7.2.3.1 | Development | 5 | 1.5 | 42.35 | Gunther
1.7.2.3.2 | Production - 150 units |  | 2 | 54.45 | Gunther
1.7.2.4 | Readout Interface Board | 4 | 3.5 | 96.8 | Gunther
1.7.2.4.1 | Development | 4 | 1.5 | 60.5 | Gunther
1.7.2.4.2 | Production - 48 units |  | 2 | 36.3 | Gunther
1.7.2.5 | Trigger IO Board | 4 | 3.5 | 60.5 | Gunther
1.7.2.5.1 | Development | 4 | 1.5 | 36.3 | Gunther
1.7.2.5.2 | Production - 8 units |  | 2 | 24.2 | Gunther
1.7.2.6 | Data IO Board | 4 | 3.5 | 60.5 | Gunther
1.7.2.6.1 | Development | 4 | 1.5 | 36.3 | Gunther
1.7.2.6.2 | Production - 8 units |  | 2 | 24.2 | Gunther
1.7.2.7 | Enclosures | 12 | 6 | 121 | Gunther
1.7.2.8 | LV |  |  | 24.2 | 1.7.2.2.2.5.1
1.7.2.9 | HV |  | 1 | 24.2 | 1.7.2.2.2.5.2
1.7.2.A | Cables |  | 2 | 174.24 | 1.7.2.2.1.3
1.7.2.B | Signal & HV Distribution Cards
1.7.3 | DRC | 22.4496 |  | 1491.0276 | Cost of electronics estimated by Gunther.
1.7.3.1 | FE-IC proto | 0 |  | 0
1.7.3.2 | FE-IC prod (qty 4000) | 2.4944 |  | 257.235 | IC's:
1.7.3.3 | FPGA (qty 1000) | 3.7416 |  | 187.08 | Assume 4-ch=10sqmm->16-ch ~ 40sqmm
1.7.3.4 | FE assembly (qty 1000) | 3.118 |  | 93.54 | TSMC IC:
1.7.3.5 | Cables (qty 1000) | 0.6236 |  | 65.478 | 155k mask, 2 lots x 50k ~250k, assume 2 lots since one run won't yield spares
1.7.3.6 | DFB equi (qty 15) | 3.7416 |  | 70.155 | plus add $25k M&S for testing
1.7.3.7 | DCC (qty 1) | 1.8708 |  | 14.031
1.7.3.8 | PDB (qty 1) | 0 |  | 0
1.7.3.9 | Crates & LV Supplies | 0 |  | 91.6692
1.7.3.A | prototyping (qty 12) | 6.236 |  | 46.77
1.7.3.B | Final installation | 0.6236 |  | 9.354
1.7.3.C | HT Power Supplies |  |  | 263.7828
1.7.3.D | Infrastructure and Monitor |  |  | 300.2634 | Rationalized cost
1.7.3.E | Electronics test Bench |  |  | 91.6692
1.7.4 | Forward PID | 42.6067 |  | 701.55
1.7.4.5.1 | FE-IC proto (qty 1) | 25.6667 |  | 233.85
1.7.4.5.2 | FE-IC prod (qty 1000) | 2.0533 |  | 210.465
1.7.4.5.3 | FPGA prod (qty 1000) | 2.0533 |  | 23.385
1.7.4.5.4 | FE assembly (qty 1000) | 2.5667 |  | 93.54
1.7.4.5.5 | DFB equi (qty 15) | 3.08 |  | 70.155
1.7.4.5.6 | DCC (qty 1) | 1.54 |  | 14.031
1.7.4.5.7 | PDB (qty 1) | 0 |  | 0
1.7.4.5.8 | Crates (qty 1) | 0 |  | 0
1.7.4.5.9 | prototyping (qty 12) | 5.1333 |  | 46.77
1.7.4.5.10 | Final installation | 0.51333 |  | 9.354
1.7.5 | EMC | 44 | 69 | 907.338
1.7.5.1 | CARE | 12 | 20 | 210.465 | Gunther
1.7.5.1.1 | 4 prototype runs TSMC process | 12 | 12 | 93.54 | Gunther
1.7.5.1.2 | Production - 2000 Units |  | 8 | 116.925 | Gunther
1.7.5.2 | Fanout Board | 4 | 9.5 | 65.478 | Gunther
1.7.5.2.1 | Development | 4 | 1.5 | 18.708 | Gunther
1.7.5.2.2 | Production 500 units |  | 8 | 46.77 | Gunther
1.7.5.3 | ADC Board | 8 | 16 | 261.912 | Gunther
1.7.5.3.1 | Development | 8 | 4 | 28.062 | Gunther
1.7.5.3.2 | Production 560 units |  | 12 | 233.85 | Gunther
1.7.5.4 | IO Board | 4 | 9.5 | 65.478 | Gunther
1.7.5.4.1 | Development | 4 | 1.5 | 18.708 | Gunther
1.7.5.4.2 | Production 100 units |  | 8 | 46.77 | Gunther
1.7.5.5 | Enclosures | 6 | 6 | 93.54 | Gunther
1.7.5.6 | Endcap preamps | 10 | 8 | 210.465 | Gunther
1.7.5.6.1 | Development | 10 | 4 | 93.54 | Gunther
1.7.5.6.2 | Production 2500 units |  | 4 | 116.925 | Gunther
1.7.5.7 | LV |  | 1 | 54.45 | 1.7.4.2.2.5.1
1.7.5.8 | HV |  | 1 | 14.52 | 1.7.4.2.2.5.2
1.7.5.9 | Cables |  | 1 | 17.545 | 1.7.4.2.1.4 but divide by 10 for fewer ROMs/Fibers
1.7.6 | IFR |  | 64 | 141 | Barrel Scintillator
1.7.6.1 | Preamp/discriminator |  | 21.6667 | 59 | all in Labor, needs to be split into EDIA/Labor?
1.7.6.1.1 | design/test prototype |  | 21.6667 | 25
1.7.6.1.2 | production |  | 0 | 34
1.7.6.2 | preamplifier board |  | 8.6667 | 15
1.7.6.2.1 | design & prototype |  | 8.6667 | 3
1.7.6.2.2 | production |  | 0 | 12
1.7.6.3 | cable to DFB |  | 0 | 8
1.7.6.4 | DFB board |  | 30.3333 | 18
1.7.6.4.1 | design/test prototype |  | 30.3333 | 5
1.7.6.4.2 | production |  | 0 | 13
1.7.6.5 | components/panel/connectors |  | 0 | 26
1.7.6.6 | test |  | 3.3333 | 15
1.7.6.7 | LV
1.7.6.8 | HV
1.7.6.9 | Cables
1.7.7 | Infrastructure | 4 | 12 | 246.84 | 1.7.C
1.7.8 | Systems Engineering | 12 |  |  | AJR estimates
1.7.9 | Hardware Trigger | 97 |  | 532.2426 | Su Dong's estimates
1.7.9.1 | GLT | 12 |  | 32.739
1.7.9.2 | DCT | 41 |  | 243.204
1.7.9.2.1 | ZPD | 16 |  | 116.925
1.7.9.2.2 | BLT | 9 |  | 32.739
1.7.9.2.3 | TSF | 16 |  | 93.54
1.7.9.3 | EMT | 16 |  | 56.124
1.7.9.4 | Interface Boards | 28 |  | 121.602
1.7.9.4.1 | Communication Boards (12) | 13 |  | 37.416
1.7.9.4.2 | DCT/GLT interface boards | 9 |  | 56.124
1.7.9.4.3 | EMT interface | 6 |  | 28.062
1.7.9.5 | Infrastructure |  |  | 78.5736
1.7.9.5.1 | DCT/FLT crates (6) |  |  | 46.77
1.7.9.5.2 | Backplanes (8) |  |  | 22.4496
| Links for primitives towards processors |  |  | ?
1.7.9.5.3 | Cables & Test equipment |  |  | 9.354
1.7.10 | ETD (without Trigger)
1.7.10.1 | FCTS | 144 |  | 120
1.7.10.1.1 | FCTS crates and supplies | 2 |  | 30
1.7.10.1.2 | Control and Distribution Module
1.7.10.1.3 | Fast Control and Timing Module
1.7.10.1.2 | Clock & Control Link Switch Module
1.7.10.1.2 | Throttle Switch Module
1.7.10.2 | CFEE
1.7.10.2.1 | FCTS mezzanine | 96
1.7.10.2.2 | Level 1 Buffer Control | 6
1.7.10.2.2 | Readout link control & serializer | 96
1.7.10.3 | ROM
1.7.10.3.1 | ROM crates and supplies |  |  | ?
1.7.10.3.2 | ROM boards | 144 |  | ?
1.7.10.4 | ECS
1.7.10.4.1 | SPECS masters | 3 |  | ?
| SPECS Mezzanine | 6
1.7.10.4.2 | SPECS links
1.7.10.5 | Clock & Control Links |  |  | ?
1.7.10.6 | Readout links |  |  | ?

## 1.8 Online computing
|  | EDIA | Labor | M&S | Basis | Comments
|  | FTEmonths | FTEmonths | [1000 Euros]
1.8 | Online computing | 852 | 14 | 1480.7382
1.8.1 | DAQ | 0 | 2 | 19.6434 |  | EDIA includes subsystem FEX, labor for testing of modules
1.8.1.1 | Partition Router ROM (compl) |  | 2 | 19.6434 | new design | DAQ, spares, 34 OL, 1 10GigE
1.8.2 | Event Flow | 258 | 0 | 1176.7332
1.8.2.1 | Event Build Network |  |  | 233.85 | new design
1.8.2.2 | Level 3 Farm | 0 | 0 | 448.992
1.8.2.2.1 | Farm Nodes |  |  | 336.744 | new design
1.8.2.2.2 | Disks |  |  | 112.248 | new design
1.8.2.3 | Data Quality Monitoring | 0 | 0 | 112.248
1.8.2.3.1 | Farm Nodes |  |  | 112.248 | new design
1.8.2.4 | Logging | 0 | 0 | 381.6432
1.8.2.4.1 | Network Switch (near) |  |  | 187.08 | new design
1.8.2.4.2 | Network Switch (far) |  |  | 187.08 | new design
1.8.2.4.3 | Cross-Site Link |  |  | 7.4832 | new design | 2 x 24-strand x 1km single mode fiber
1.8.2.5 | Software Engineering | 258 |  |  | replicate BaBar
1.8.3 | Run Control / Slow Controls | 258 | 0 | 50.5116
1.8.3.1 | Run Control | 36 |  |  | replicate BaBar
1.8.3.2 | Slow Controls | 108 |  | 50.5116 | new estimate | assumes greater uniformity across subsystems than BaBar
1.8.3.3 | Databases, Web, Logbook | 114 |  |  | new estimate
1.8.4 | Infrastructure | 48 | 12 | 233.85 | combination | consoles,file servers and storage, app servers, network infrastructure
1.8.5 | Software Triggers | 216 |  |  | replicate BaBar
1.8.6 | Coordination and Commissioning | 72 |  |  | replicate BaBar
[7 empty] | DAQ Components | Unit Cost (USD) | # Central DAQ | # Test Stands / Lab | # Spares | # total | cost total
[7 empty] | Base CE Module | 2
[7 empty] | Partition Router CE Module | 10
[7 empty] | 250MByte/s Fiberoptic Transceiver | 0.03
[7 empty] | 10GigE Transceiver (Copper) | 0.3
[7 empty] | Fiber, terminated | 0.05
[7 empty] | Crate (full-size) | 4
[7 empty] | Crate (mini) | 0.5
[7 empty] | Accel. Clock interface | 5
[7 empty] | CE Module, complete | 2.42 | 17 | 10 | 14 | 41 | 99.22
[7 empty] | Partition Router CE Module | 11.32 | 1 | 1 | 1 | 3 | 33.96
[7 empty] | Crate (full-size) | 4 | 2 | 2 | 2 | 6 | 24
[7 empty] | Crate (mini) | 0.5 | 0 | 8 | 2 | 10 | 5
[7 empty] | Fibers, terminated | 0.05 | 34 | 32 | 10 | 76 | 3.8
[7 empty] | Accel. Clock Interface CE Module | 7 | 1 | 0 | 2 | 3 | 21

## 1.9 IntegrationInstallation
| Description | Engineering Man Months | Designer Man Months | Tech Supt Supv Man Months | Sr Mech Tech Man Months | Rigger Man Months | Pipefitter Man Months | Sr Elect Tech Man Months | Electrician Man Months | Surveyor Man Months | Cable Puller Man Months | Safety Oversight Man Months | M&S K$
1.9 | Integration and Integration
1.9.1 | Disassemble BaBar Detector
1.9.1.1 | Prep IR-2 Hall for Detector Removal | 0.5 |  | 0.5 | 1.5 | 0.5 |  | 0.5 |  |  |  | 0.5
1.9.1.2 | Remove PEP Rafts and Support Tube | 1.5 | 1.5 | 1.5 | 15 | 3 | [5 empty] | 1.5
1.9.1.3 | Disconnect and Roll Back Electronics House
1.9.1.3.1 | Project Integration Engineering | 2 | 2
1.9.1.3.2 | Remove Equip from Electronics House 2nd Floor | 0.5 |  | 0.5 | 6 | 0.5 |  | 1 | 0.25 |  |  | 0.5
1.9.1.3.3 | Remove Equip from Inside Electronics House | 0.75 |  | 0.75 | 2.25 | 0.75 |  | 1.5 | 0.25 |  |  | 0.75
1.9.1.3.4 | Mechanically Discconnect Electronics House | 0.25 |  | 0.25 | 0.75 | [6 empty] | 0.25
1.9.1.3.5 | Roll Back Electronics House | 0.25 |  | 0.25 | 0.75 | [6 empty] | 0.25 | 20
1.9.1.4 | Remove Chiller/Heat Exchanger Components | 0.5 |  | 0.5 | 1.5 | 0.5 | [5 empty] | 0.5
1.9.1.5 | Remove Platforms, Walkways & Stairs | 0.5 |  | 0.5 | 1.5 | 0.5 | [5 empty] | 0.5
1.9.1.6 | Remove FWD Layer 13-16 Modules & End Plugs
1.9.1.6.1 | Remove FWD Layer 13-16 Modules | 0.25 |  | 0.25 | 0.75 | 0.25 | [5 empty] | 0.25
1.9.1.6.2 | Remove End Plug Components | 0.25 |  | 0.25 | 0.75 | 0.25 | [5 empty] | 0.25
1.9.1.7 | Remove Barrel LSTs and Brass
1.9.1.7.1 | Project Integration Engineering | 2 | 2
1.9.1.7.2 | Perform EMC Load Transfer | 0.25 |  | 0.25 | 0.75 | 0.25 | [5 empty] | 0.25
1.9.1.7.3 | Remove FWD Steel | 0.25 |  | 0.25 | 0.75 | 0.25 | [5 empty] | 0.25
1.9.1.7.4 | Remove LSTs | 2 |  | 2 | 6 | 2 | [5 empty] | 2
1.9.1.7.5 | Remove Brass | 1.25 |  | 1.25 | 3.75 | 1.25 | [5 empty] | 1.25
1.9.1.7.6 | Replace FWD Steel | 0.25 |  | 0.25 | 0.75 | 0.25 | [5 empty] | 0.25
1.9.1.7.7 | Perform EMC Load Transfer | 0.25 |  | 0.25 | 0.75 | 0.25 | [5 empty] | 0.25
1.9.1.8 | Remove FWD End Cap EMC | .
1.9.1.8.1 | Project Integration Engineering | 2 | 2
1.9.1.8.2 | Remove FWD End Cap EMC | 0.5 |  | 0.5 | 1.5 | 1 | [5 empty] | 0.5 | 30
1.9.1.9 | Connect End Doors to Barrel
1.9.1.9.1 | Project Integration Engineering | 1 | 1
1.9.1.9.2 | Remove FWD Belt Chambers and Steel | 0.25 |  | 0.25 | 0.75 | 0.5 | [5 empty] | 0.25 | 20
1.9.1.9.3 | Connect End Doors to Barrel | 0.25 |  | 0.25 | 0.75 | 0.5 | [5 empty] | 0.25
1.9.1.10 | Remove End Door RPCs and Brass
1.9.1.10.1 | Project Integration Engineering | 1 | 1
1.9.1.10.2 | Remove FWD & BWD RPCs | 1.25 |  | 1.25 | 3.75 | 1.25 | [5 empty] | 1.25 | 30
1.9.1.10.3 | Remove FWD Brass | 1 |  | 1 | 3 | 1 | [5 empty] | 1
1.9.1.11 | Roll Out BaBar Detector
1.9.1.11.1 | Project Integration Engineering | 1 | 1
1.9.1.11.2 | Roll Out BaBar Detector | 0.5 |  | 0.5 | 1.5 | 0.5 | [5 empty] | 0.5 | 30
1.9.1.12 | Disassemble End Doors
1.9.1.12.1 | Project Integration Engineering | 2 | 2
1.9.1.12.2 | Disassemble End Doors | 2 |  | 2 | 6 | 4 | [5 empty] | 2 | 40
1.9.1.13 | Remove Barrel Platform Electronics | 0.5 |  | 0.5 | 0 |  |  | 1 |  |  |  | 0.5
1.9.1.14 | Remove Barrel Cabling | 0.5 |  | 0.5 |  |  |  | 1 |  |  | 12 | 0.5
1.9.1.15 | Remove Barrel Piping | 0.5 |  | 0.5 | 1.5 | [6 empty] | 0.5
1.9.1.16 | Remove Barrel Platforms and Side Valve Panels | 0.5 |  | 0.5 | 11.5 | 1 | [5 empty] | 0.5
1.9.1.17 | Remove DIRC Stand Off Box
1.9.1.17.1 | Project Integration Engineering | 2 | 2
1.9.1.17.2 | Remove DIRC Stand Off Box | 0.5 |  | 0.5 | 1.5 | 1 | [5 empty] | 0.5 | 40
1.9.1.18 | Remove Drift Chamber Assembly
1.9.1.18.1 | Project Integration Engineering | 1 | 1
1.9.1.18.2 | Remove Drift Chamber Assembly | 0.5 |  | 0.5 | 1.5 | 1 | [5 empty] | 0.5 | 30
1.9.1.19 | Remove DIRC Central Support Tube Assembly
1.9.1.19.1 | Project Integration Engineering | 3 | 3
1.9.1.19.2 | Remove DIRC Central Support Tube Assembly | 0.75 |  | 0.75 | 2.25 | 1.5 | [5 empty] | 0.75 | 50
1.9.1.20 | Remove Barrel EMC
1.9.1.20.1 | Project Integration Engineering | 4 | 4
1.9.1.20.2 | Remove Barrel EMC | 0.75 |  | 0.75 | 2.25 | 1.5 | [5 empty] | 0.75 | 70
1.9.1.21 | Remove Valve Box and Superconducting Solenoid
1.9.1.21.1 | Project Integration Engineering | 3 |  | 3
1.9.1.21.2 | Remove Valve Box and Superconducting Solenoid | 0.75 |  | 0.75 | 2.25 | 1.5 | [5 empty] | 0.75 | 50
1.9.1.22 | Disassemble Barrel Iron
1.9.1.22.1 | Project Integration Engineering | 2 | 2
1.9.1.22.2 | Disassemble Barrel Iron | 1.5 |  | 1.5 | 3 | 6 | [5 empty] | 1.5 | 100
| Total BaBar Disassembly | 48 | 24.5 | 25 | 86.5 | 32.75 | 0 | 5 | 0.5 |  | 12 | 22 | 510
| Approx SLAC Labor Rate with Benefits & Burden | 130 | 85 | 100 | 75 | 75 | 85 | 75 | 85 | 85 | 85 | 100
| Total K$ (SLAC Equivalent) | 998.4 | 333.2 | 400 | 1038 | 393 | 0 | 60 | 6.8 | 0 | 163.2 | 352 | 4254.6
1.9.2 | Assemble SuperB Detector
1.9.2.1 | Detector Assembly |  |  | 25 | 86.5 | 32.75 |  | 5 |  |  | 24 | 22 | 3320
1.9.2.2 | Install Electrical Power for Experiment | [7 empty] | 90
1.9.2.3 | Install Chillers and Heat Exchangers | 6 | 3 | 3 | 6 | [6 empty] | 6
1.9.2.4 | Install Detector Piping | 18 | 18 | 15 |  |  | 60 |  |  |  |  | 15
1.9.2.5 | Survey and Alignment | [8 empty] | 24
1.9.2.6 | Project Integration Engineering | 108 | 108
1.9.2.7 | Magnet Mapping | 4 | 6 | [9 empty] | 80
| Total SuperB Assembly | 136 | 135 | 43 | 92.5 | 32.75 | 60 | 5 | 90 | 24 | 24 | 43 | 3320
| Total K$ (SLAC Equivalent) | 2828.8 | 1836 | 688 | 1110 | 393 | 816 | 60 | 1224 | 326.4 | 326.4 | 688 | 13616.6
| SuperB Assembly M&S | Unit | No. Units | Unit Cost | Total K$
| Supplies | Months | 24 | 10 | 240
| Rental Equipment | Months | 18 | 10 | 180
| Scaffolding | Each | 1 | 80 | 80
| Fire Protection System | Each | 1 | 100 | 100
| VESDA System | Each | 1 | 100 | 100
| Cable Trays | FT | 2000 | 0.03 | 60
| Gas House | Each | 1 | 150 | 150
| Gas Safety Systems | Lump | 1 | 50 | 50
| Detector Shielding | Lump | 1 | 200 | 200
| Data Assembly Building | SQFT | 1600 | 0.1 | 160
| Miscellaneous Cables | FT | 10000 | 0.005 | 50
| Piping Supplies | Lump | 1 | 700 | 700
| Electrical Power Equipment | Lump | 1 | 750 | 750
| Integration Engineering M&S | Lump | 1 | 500 | 500
| Total M&S |  |  |  | 3320

## 1.A Project Management
|  | Engineering |  | Technician |  | M&S | Total
|  | [mm] | [Euros] | [mm] | [Euros] | [KEuros] | [kEuros]
1.A | Project Management | 720 | 10800 | 0 | 0 | 180 | 10980
1.A.1 | Project engineering | 300 | 4500 | 0 | 0 | 100 | 4600
1.A.1.1 | Chief mechanical engineer and deputy | 150 | 2250 | 0 | 0 | 50 | 2300
1.A.1.2 | Chief electrical engineer and deputy | 150 | 2250 | 0 | 0 | 50 | 2300
1.A.2 | Budget, Schedule and Procurement | 300 | 4500 | 0 | 0 | 40 | 4540
1.A.2.1 | Budget and Schedule officers | 120 | 1800 | 0 | 0 | 20 | 1820
1.A.2.2 | Procurement office | 180 | 2700 | 0 | 0 | 20 | 2720
1.A.3 | ES \& H | 120 | 1800 | 0 | 0 | 40 | 1840
1.A.3.1 | Chief ESH officer | 60 | 900 | 0 | 0 | 20 | 920
1.A.3.2 | Oversight officer | 60 | 900 | 0 | 0 | 20 | 920

## ChangeLog
Log of changes to the Budget
Date | System | What
v3
v4
v5
2007-03-20 | ALL | v6 released
2007-03-22 | SVT | Remove SVT 0 lines in Maps and striplets
2007-03-22 | SVT | Change header MAPS -> Layer0 MAPS
2007-03-22 | DCH | DCH - new cost estimate from dbmacf with stringing robots et al.
2007-03-22 | IFR | Replace gas and chilled water modifications with services
2007-04-04 | IFR | Inflate some manpower numbers
2007-04-04 | IFR | Introduced system engineering instead of module engineering and increased the number
2007-04-04 | DAQ | New cost estimates
2007-04-04 | PID | New cost estimates for barrel without SOB
2007-04-04 | PID | Corrected mistake in sum of reuse value (was counting the PMs as well)
2007-04-04 | PID | Replaced PID in main table with PID no sob.
2007-04-04 | PID | Included PID with focusing readout as option (not summed) in main table
2007-04-04 | PRO | Introduced Project management
2007-04-04 | ASS | Introduced structural analysis
2007-04-04
2007-04-04
2007-04-04
2007-04-04