## Slide 1
FOOT calorimeter
Status Report
Crystals
SiPMs
Readout
DAQ
Mechanics
Plans
Contributions by:
S. Argirò
N. Bartosik
F. Cavanna
G. Giraudo
E. Lopez Torres
M. Mignone
N. Pastrone
M. Penna
L. Ramello
G. Scalise
L. Scavarda
M. Sitta
Piergiorgio Cerello

## Slide 2
BGO crystals
Crystal size mapping: completed
Crystal painting vs. wrapping, coupling
- TYVEK wrapping
- SiPM coupling: tested in Feb2020
4 Crystals coupled to this slice of fast scintillator in front
        Crystals wrapping and coupling at CERN
              Holder design completed, order being placed
BGO Crystals

## Slide 3
SiPM tiles: to do list
Order for production and packaging placed
Silicon production successfully completed
Tile delivery: 10 tiles by May 2021, 160 by August, 160 by November
SiPM tiles
Front-end boards
received
Module holders
received

## Slide 4
SiPM tiles
Power supply distribution: to do list
System designed (4 switch boards + 32 supply boards)
        Board1 (32 pieces): design completed, order being places
        Board2 (4 pieces): design completed by June 2021
Cables:
  Readout: 5m length, order being placed
  Power supply: stage 3 (from Board1 to FE-board), order being placed
  Power supply: stage 1 (create to Board2) and 2 (Board2 to Board1): order as soon as Board2 design completed)

## Slide 5
HV
LV
DB25
DB37
Switch
Board
1
Crystals
16 ch
16 ch
4 ch
4 ch
x2
1 in, 10 out
HV 1 in, 8 out (2 ch/connector)
Racks
Calorimeter
16
Switch
Board
Temp.
.
.
.
.
.
.
.
.
LV 1 in, 8 out
2 x +6V
2 x -6V
2 x +6V
2 x -6V
2x
Board1
Board2

## Slide 6
SiPM readout: to do list
Power supplies (CAEN SY5527 + supply boards) - received
Readout: from CAEN V1742 to Wavedream – received
SiPM readout
Temperature correction
System designed
Prototype completed
Orders to be placed in 2021 (2022?)

## Slide 7
Mechanics: to do list
  System design completed
  Components: order procedure started
  Mechanical structure for calibration
          - x/y displacement remote control
Mechanics

## Slide 8
Temperature Readout
Mechanics
53.1 mm
12.4 mm
U5
U4
U2
U1
U3
U6
U1, U2, U4, U5:
Presa DB-25 da c.s. 90° femmina
U3, U6:
Connettore 3M-24 da c.s. maschio
N2524-6002RB diritto a 24 pin
233.35 +0 -0.3 mm
Da U3 e U6 partono due cavi piatti verso
connettori identici sulla scheda principale
65 mm
pin 1
FOOT-CTR-aux

## Slide 9
Temperature Readout
Mechanics
U4
U3
U2
U1
U5
U6
U5, U6:
Connettore 3M da c.s. maschio
N2524-6002RB diritto a 24 pin
ingombro
scheda FOOT-CTR-aux
J1, J2:
Connettore VME tipo C da c.s. maschio a 90°, 96 pin (DIN 41612) su 3 file (a, b, c)
U1, U2, U3, U4:
Presa DB-25 da c.s. 90° femmina
160 mm
J1
J2
59 mm
81 mm
Lasciare spazio per Arduino,
verrà montato sulla
scheda «master»
65 mm
233.35 +0 -0.3 mm
FOOT-CTR-main

## Slide 10
Temperature Readout
Mechanics
FOOT-CTR-main (detailed view)
J2
c b a
riga 32
riga 1
//
//
J3
J4
Disegno non in scala, solo
per l’orientamento di J3 e J4
rispetto ad Arduino e a J2
GND
GND

## Slide 11
Software
Calibration protocol to be defined
  Dedicated Beam test at CNAO asap
Software

## Slide 12
Overview
Design (nearly) completed – only intermediate mixing power supply board to be completed (end of June)
Procurement is ongoing
We will definitely have budget issues (about ~ 10 kE missing, even though the Temperature readout system funded by UPO)
Overview