## TIMELINE_TEMPLATE
Name of the project: PLAYING WITH PROTONS GOES DIGITAL
PROJECT TIMETABLE
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24
| 2021-06-01 | 2021-07-01 | 2021-08-01 | 2021-09-01 | 2021-10-01 | 2021-11-01 | 2021-12-01 | 2022-01-01 | 2022-02-01 | 2022-03-01 | 2022-04-01 | 2022-05-01 | 2022-06-01 | 2022-07-01 | 2022-08-01 | 2022-09-01 | 2022-10-01 | 2022-11-01 | 2022-12-01 | 2023-01-01 | 2023-02-01 | 2023-03-01 | 2023-04-01 | 2023-05-01
Project activity*
Project Management, Coordination and Reporting (A.1) | 2021-11-01: MS1
Management and Coordination (A.1.1)
Management Plan (A.1.2) | bar: 2021-06-01 to 2021-07-01; 2022-05-01
Pilot Implementation Plan (A.1.3) | bar: 2021-06-01 to 2021-11-01; 2022-05-01
Final Report (A.1.3) | bar: 2023-05-01
Quality Assurance Plan (A.1.4) | bar: 2021-06-01 to 2021-07-01
Communication (A.2)
Project Meetings (A.2.1.a, b, c, d, e) | 2021-06-01: M1; 2021-12-01: M2; 2022-07-01: M3; 2022-12-01: M4; 2023-05-01: M5
Project Communication Activities (A.2.2)
Intellectual Outputs and associated activities (A.3) | 2021-11-01: MS1; 2022-05-01: MS2; 2023-05-01: MS3
Needs analysis (A.3.1) | bar: 2021-06-01 to 2021-09-01
Online environment specifications and features (A.3.2) | bar: 2021-06-01 to 2021-11-01
Beta version of online platform (A.3.3) | bar: 2021-09-01 to 2022-03-01
Delivery of Conceptual and Methodological Framework (IO1) | 2022-05-01: IO1
Delivery of initial set of activities (A.3.4) | bar: 2021-06-01 to 2022-05-01
Completion of international teachers’ summer school (A.3.5) | bar: 2022-07-01
Delivery of final set of activities in Handbook (IO2) | 2023-04-01: IO2
Initial version of Evaluation and eTwinning Toolkit (A.3.6) | bar: 2022-05-01 to 2022-11-01
Initial version of Recommendations Hanbook (A.3.7) | bar: 2022-05-01 to 2022-11-01
Delivery of Digital Online Platform (IO3) | 2023-05-01: IO3
Delivery of final version of Evaluation and eTwinning Toolkit (IO4) | 2023-05-01: IO4
Delivery of final version of Recommendations Handbook (IO5) | 2023-05-01: IO5
Multiplier Events (E) | 2022-05-01: MS2; 2023-04-01: MS3
Multiplier Event 1 (E1) | bar: 2022-01-01 to 2022-03-01
Multiplier Event 2 (E2) | bar: 2022-01-01 to 2022-03-01
Multiplier Event 3 (E3) | bar: 2022-01-01 to 2022-03-01
Multiplier Event 4 (E4) | bar: 2022-01-01 to 2022-03-01
Multiplier Event 5 (E5) | bar: 2023-01-01 to 2023-03-01
Multiplier Event 6 (E6) | bar: 2023-01-01 to 2023-03-01
Multiplier Event 7 (E7) | bar: 2023-01-01 to 2023-03-01
Multiplier Event 8 (E8) | bar: 2023-01-01 to 2023-03-01
Dissemination (A.4) | 2021-11-01: MS1
Dissemination Plan (A.4.1) | bar: 2021-06-01 to 2021-07-01
Dissemination Materials and Events (A.4.2)
Website and Social Media Presence (A.4.3) | bar: 2021-10-01 to 2023-05-01
Please insert rows as needed
*Project activity types:
An | 2021-06-01: - PROJECT MANAGEMENT, IMPLEMENTATION & DISSEMINATION ACTIVITIES
IOn | 2021-06-01: - INTELLECTUAL OUTPUTS
Mn | 2021-06-01: - TRANSNATIONAL PROJECT MEETINGS
En | 2021-06-01: - MULTIPLIER EVENTS
MSn | 2021-06-01: - MILESTONES
n | 2021-06-01: - number of the activity
Please enter all main project activities and meetings, intellectual outputs and related activities, multiplier events and training/teaching/learning activities. Use the reference numbers as they appear in the application form. Where no numbers exist in the application form (i.e. for activities included in project management and implementation), use reference numbers A1, A2 etc. For each activity, meeting or event, indicate the month(s) in which they will be produced/take place by colouring the corresponding cells.