## WBS
HORIZON-INFRA-2022-DEV-01-01 Muon Collider Study
Muon Collider | [6 empty] | 1st YEAR | [6 empty] | 2nd YEAR | [16 empty] | 3rd YEAR | [6 empty] | 4th YEAR
Task | Description | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48
1 | Project Management and Coordination of the test programme
1.1 | Management
1.2 | Parameter and Lay-out Committee
1.3 | Test Programme Committee
1.4 | Community Meetings
1.5 | Liaison with Non-European Communities
1.6 | Dissemination of Information and Industry outreach
2 | Physics case and Detector performance
2.1 | Coordination and Communication
2.2 | 3 TeV Physics case
2.3 | 10+ TeV Physics case
2.4 | Detectors 1
2.5 | Detectors 2
2.6 | MDI?
3 | Proton Complex
3.1 | Coordination and Communication
3.2 | Proton Complex at CERN (LINAC4 + SPL)
3.3 | Accumulator and combiner rings
3.4 | Contribution to test programme
3.5
4 | Ionisation Coooling and Targets
4.1 | Coordination and Communication
4.2
4.3
4.4
4.5
5 | RF
5.1 | Coordination and Communication
5.2
5.3
5.4
6 | Magnets
6.1 | Coordination and Communication
6.2
6.3
6.4
7 | Cooling Cell
7.1 | Coordination and Communication | 2nd YEAR 15: M7.3; 4th YEAR 48: D7.1
7.2 | Survey and selection of possible technologies for Magnets, RF and absorbers | 1st YEAR 12: M7.1; 2nd YEAR 18: M7.4
7.3 | Analysis of different types of Cells, selection of the most suitable for first test | 1st YEAR 12: M7.2; 2nd YEAR 18: M7.5
7.4 | Design of components | 3rd YEAR 30: M7.6; 3rd YEAR 36: M7.8
7.5 | Integration of Cell | 3rd YEAR 30: M7.7; 4th YEAR 48: D7.2
8 | High Energy
8.1 | Coordination and Communication
8.2
8.3
8.4

## WP7 Deliverables
HORIZON-INFRA-2022-DEV-01-01 Muon Collider
1.3.4. Deliverables list
Table 1.3 b: Deliverables List
Del. | Deliverable name | WP no. | Nature | Dissemi | Delivery
no. 1 |  |  | 2 | nation | date4
level3
D7.1 | Final report on Absorbers, RF & Magnets | 7 (Task 7.4) | R | PU | M48
D7.2 | Final report on the Selection and Integration of the Cell | 7 (Task 7.5) | R | PP | M48
1 Deliverable numbers in order of delivery dates.
2 R = Report, P = Prototype, D = Demonstrator, O = Other
3 PU = Public
PP = Restricted to other programme participants (including the Commission Services).
RE = Restricted to a group specified by the consortium (including the Commission Services).
CO = Confidential, only for members of the consortium (including the Commission Services).
4 Measured in months from the project start date (month 1).
25

## WP7 Milestones
HORIZON-INFRA-2022-DEV-01-01 Muon Collider
1.3.4. Deliverables list
Table 1.3 b: Deliverables List
Del. | Deliverable name | WP no. | Nature | Dissemi | Delivery
no. 1 |  |  | 2 | nation | date4
level3
M7.1 | Preliminary report on Absorbers, RF & Magnets | 7 (Task 7.2) | R | PU | M12
M7.2 | Preliminary report on cooling cell | 7 (Task 7.3) | R | PU | M12
M7.3 | Workshop to discuss results of WP 7.2-7.3 | 7 (Task 7.1) | O | PU | M15
M7.4 | Selection of absorber, RF and Magnet Technology for test | 7 (Task 7.2) | R | PU | M18
M7.5 | Selection of Cooling cell for test | 7 (Task 7.3) | R | PU | M18
M7.6 | Preliminary Report on Design of Components | 7 (Task 7.5) | R | PP | M30
M7.7 | Preliminary Report on Integration of Cell | 7 (Task 7.6) | R | PP | M30
M7.8 | Design of Components (RF, magnets) achieved | 7 (Task 7.5) | O | PP | M36
1 Deliverable numbers in order of delivery dates.
2 R = Report, P = Prototype, D = Demonstrator, O = Other
3 PU = Public
PP = Restricted to other programme participants (including the Commission Services).
RE = Restricted to a group specified by the consortium (including the Commission Services).
CO = Confidential, only for members of the consortium (including the Commission Services).
4 Measured in months from the project start date (month 1).
25

## Sheet1
HORIZON-INFRA-2022-DEV-01-01 Muon Collider
List of participants:
Participant n. | Participant organisation name | Short | Country | Institute/group | Contact person(s)
1 (Coordinator) | European Organization for Nuclear Research | CERN | IEIO1 |  | R. Losito, D. Schulte
, | Commissariat à l'Énergie Atomique et aux énergies alternatives | CEA | France | Irfu
3 | Istituto Nazionale di Fisica Nucleare | INFN | Italy |  | N. Pastrone
4 | Centre National de la Recherche Scientifique | CNRS | France
5 | Science & Technology Facilities Council | STFC | UK | STFC | UK
6
7 | Consejo Superior de Investigaciones Cientificas | CSIC | Spain | CSIC | Spain
8 | École Polytechnique Fédérale de Lausanne | EPFL | Switzerland | EPFL | Switzerland
9 | Royal Holloway, University of London | RHUL | UK | RHUL | UK
10 | University of Southampton | SOTON | UK | SOTON | UK
11
12 | University of Lancaster | ULANC | UK | ULANC | UK
13 | University of Liverpool | UNILIV | UK | UNILIV | UK
14 | University of Manchester | UNIMAN | UK | UNIMAN | UK
15 | High Energy Accelerator Research Organization | KEK | Japan | KEK | Japan
16 | Brookhaven National Laboratory | BNL | USA | BNL | USA
17 | Fermi National Accelerator Laboratory | FNAL | USA | FNAL | USA
(Fermilab)
18 | Lawrence Berkeley National Laboratory | LBNL | USA | LBNL | USA
19 | Old Dominion University | ODU | USA | ODU | USA
20 | SLAC National Accelerator Laboratory | SLAC | USA | SLAC | USA
1 International European Interest Organisation
2