## Slide 1: Work organization and deadlines
Giuseppe Andronico
INFN, Sez CT

## Slide 2: Starting point
Status:
  DCI up and running with 4 sites
  Some data challenge already positively performed
  Joined LHCONE
  JUNO resources already on LHCONE

## Slide 3: Considerations on the network
Link between IHEP and Europe is 10 Gb/s
To my knowledge, problems with peering between China and Russia; is this true?
Links between CNAF and CC-IN2P3 order of 100 Gb/s
Link between GEANT and Russia order of 10 Gb/s
Proposal:
IHEP is the JUNO Tier0
CNAF should be the nodal center for the data flows

## Slide 4: Possible plan
Following BELLE II example:
Check CNAF connection vs other sites
  For each site we test both directions: CNAF  SiteX and SiteX  CNAF
  Each site will be made from a set of FTS jobs, for example 100x10GB
Use different configurations, i.e. file number (25,50,100) and TCP streams (from 1 to 16)

## Slide 5: Documentation
For every site collect local configuration, including Network and Storage setup

## Slide 6: Monitoring
Following BELLE II example:
FTS statistics, retrieved every x seconds by a local script
Plots provided by sites from the relative locasl monitoring systems
Plots from the NRENs monitoring system

## Slide 7: Tentative workplan
ID | Action | Who | Where | When
T0.1 | Collect local configuration | Every data center | Store in a common repository | By Feb 15
T0.2 | Create monitoring infrastructure | DCI, Data centers, NREN | Store in one common place | By Feb 15
T0.3 | Schedule test | DCI, Data centers, NREN |  | By Feb 15
T1 | Perform first test | DCI, Data centers, NREN | Store results in monitoring system | Before March 31
T2 | Perform second test | DCI, Data centers, NREN | Store results in monitoring system | Before June 30