## Slide 1
FOOT calorimeter
Status Report
Construction

## Slide 2
Missing items:
Mechanical pieces: delivered on May, 30th
HV power cable (30 m): out for delivery on May, 30th
            - original order place in January 2022
            - delivery foreseen in April 2022, delayed to May then October
            - alternative option identified (3 pieces available on RS-Italy)
            Detectors:
                - 40 available and glued
                - then, FBK had problem with the resin layer
                - May 27th: they stated they solved them and will deliver the second batch in
                mid June
Overview

## Slide 3
Timeline:
Modules: 1st to be assembled at CERN on June 2nd – 3rd
Mechanical structure: to be assembled (dummy) next week
            Detectors gluing:
                - to be resumed as soon as the second batch is delivered
                - for HIT we already have 40 crystals, 5 more just require 1 extra day
                of gluing
Overview

## Slide 4
FOOT calorimeter
Status Report
Calibrations / Software / Data analysis

## Slide 5
Timeline:
HIT data taking: 5 modules (more?), with temperature reading
Calibrations: start with the crystals we will use at HIT
  - energy: at CNAO, beam availability to be agreed
  - temperature: in the climatic chamber available in Torino
SW in SHOE: calibrations and corrections (T, range) already implemented, clustering studies ongoing
            Upgrade for neutrons:
                - see Francesca B.’s talk
                - next steps to be agreed, but priority to the construction and commissioning of the Calorimeter
Overview