## Slide 1
RICH Status Report
Valery Kubarovsky
Monday June 6, 2022 Hall-B meeting

## Slide 2: RICH-II Installation and Commissioning
Tuesday. Detector was assembled in the EEL clean room
－Mechanical construction
－Electronic panel with 391 H12700 MaPMTs, home-made front-end electronics and DAQ boards
－Aerogel radiator
－Spherical mirrors
－Flat mirrors
Wednesday. RICH detector was moved to Hall-B
Thursday. RICH was installed to Forward Carriage
Friday. All cables are connected: HV, LV, DAQ fibers, slow control.
Saturday. Commissioning of the detector subsystems done.
INFN (Italy), ANL, and JLAB, with the help of fast electronics, detector support, and Hall-B engineering groups, completed the construction, installation, and commissioning of the second Ring Imaging Cherenkov (RICH-II) counter.

## Slide 3: Electronic Panel: 391 H12700 MaPMTs

## Slide 4
Installation and alignment of the spherical mirrors

## Slide 5: Photomatrix installation

## Slide 6: Inside the RICH detector

## Slide 7: RICH from inside
7

## Slide 8: Italian team

## Slide 9: Still open from bottom side

## Slide 10: 2x3 cm Aerogel wall
10

## Slide 11: 3 cm Aerogel wall installed
11

## Slide 12: Aerogel Wall – 2 cm tiles
12

## Slide 13: Last View Inside RICH

## Slide 14: Load on Track

## Slide 15: Go to Hall-B

## Slide 16: Tough Fit

## Slide 17: In Hall-B

## Slide 18: Final installation moment

## Slide 19: RICH-I and RICH-II are in place

## Slide 20: Two RICH Detectors: temperature
RICH1 – 138 tiles
20
RICH1I – 138 tiles

## Slide 21: Two RICH Detectors – 50,048 channels
RICH1 - 391 H12700 MaPMTs: 25,024 channels
21
RICH1I - 391 H12700 MaPMTs: 25,024 channels