## Slide 1: INFN Milano LASA Product Acceptance
L. Monaco & the INFN PIP-II group
30 June 2022

## Slide 2: Strategy of Product Acceptance for PIP-II
FNAL and the INFN-LASA will collaboratively establish methods for evaluating the acceptance of components or services from vendors throughout the supply chain.
The PIP-II LB650 Jacketed Cavities Acceptance Plan and PIP-II LB650 Jacketed Cavities Acceptance Criteria documents will fully describe:
The division of responsibilities
Non-conformance handling
Criteria by which the cavities may be accepted by Fermilab
Dual Site Acceptance scheme in place:
Site Acceptance Review 1 (SAR1): to occur on the premises of INFN-LASA cavity qualification partner after cold-testing.
  Once the cavity arrive safely to the qualification lab the activity on the production jacketed cavities by the vendor is completed.
  SAR1 is overcome only if the cavity performs at specification
Site Acceptance Review 2 (SAR2): to occur at the string assembly site under Fermilab responsibility.
  INFN-LASA has to finalize and submit to Fermilab the full document set describing cavity status and performance, including final inspection data (RF, vacuum and shock-loggers) confirming safe transport and delivery.
  This step will then lead to the final acceptance and to the transfer of ownership and associated technical risks.

## Slide 3: The 5 Acceptance Levels (ESS)
Level | Cavity status | Needed documents | If Level reached
Al1 | Cavity after mechanical fabrication | Mechanical, RF, vacuum, visual documents | Proceed to Level Two
Al2 | Cavity before He-tank integration | Mechanical, RF, vacuum, Treatment documents (bulk BCP, annealing) | Proceed to Level Three
Al3 | Cavity jacketing, Final BCP and surface treatments, assembly of accessories for the cold RF test | Cavity jacketing and pressure tests (mechanical, RF, vacuum, visual documents, transfer measurements), final surface treatments, final vacuum and RF checks, outgoing inspection | Jacketed cavity ready to be cold RF tested
Al4 | Cavity cold RF tested | Documents of the cold RF test, incoming/outgoing checks | Cavity can be sent to CEA for string assembly
Al5 | Cavity accepted for string assembly | Documents with incoming inspection at CEA | Cavity final approval (ESS)
SAR1
SAR2

## Slide 4: Documents for Al5 (ESS example)
Template name | Description | Acceptance Level | Issued by
X_M02a | Mechanical check after tuning | Al2 | EZ
Y_M01 | Mechanical check of Dressed Cavity | Al3 | EZ
Y_TM01 | Transfer measurements | Al3 | EZ
Y_P01 | Pressure Test after He-Tank integration | Al3 | EZ
Y_L01 | Leak check of volume (I) between the inner He-tank and the outer cavity | Al3 | EZ
Y_L02 | leak check of volume (II) inner cavity | Al3 | EZ
Y_F07 | FF and RF spectrum after all He-Tank checks (w/o brackets) | Al3 | EZ
Y_ESS27 | Final Leak Check after Final 12h HPR | Al3 | EZ
Y_C01 | Certificate of Conformity (Zanon) | Al3 | EZ
Y_INC01 | Incoming inspection at DESY at the arrival | Al4 | DESY
Y_F17 | DESY Cold Measurements (VT, RF spectrum, HOM) | Al4 | DESY
Y_F18 | Final RF spectrum before shipping to CEA (in vacuum) | Al4 | DESY
Y_OUT02 | Outgoing inspection at DESY before delivery to CEA | Al4 | DESY
Y_L03* | Leak check of volume (I) between the inner He-tank and the outer cavity after VT | Al4 | DESY
Y_REF | Reference frequency (HOR, air, no brack, no frame) | Al5 | INFN
Y_PC | List of Parts in Circulation | Al5 | INFN
Y_DoI | Declaration of Incorporation | Al5 | INFN
Y_INC02 | Incoming inspection at CEA at the arrival | Al5 | CEA
Y_F19 | RF spectrum at CEA at the arrival | Al5 | CEA
Y_HO | HandOver document | Al5 | ESS
* Introduced during the production, initially performed by DESY and then by CEA
About 200 documents overall are generated for each cavity, 20 of which (listed in the table) are made readily available to the project (ESS + CEA) by INFN
Plus two raw text files containing selected numerical data (TM, RF spectrum)
Only few of these are strictly required by CEA to perform string installation

## Slide 5: Documents for Al5 (ESS example)