## Slide 1: Financial Board meeting
Sep. 9th, 2022

## Slide 2: Items to be discussed (not all today)
Tracking of out of scope expenses
Common funds
Gd loaded acrylic procurement
Forti meeting preparation: cost baseline
Forti meeting preparation: EVM
List and see the status, approve next urgent procurement procedures
LNGS-DarkSide sharing of responsibilities & related funding issues (annex to the MoU)
List & track the deadline of all the temporary contracts of people to anticipate strategies

## Slide 3: 1) Track and compensate expenses not fitting the scope of an Institution
Raised by Cristian in August
  2 bridge contracts at that time (2 people for 3 months) (Lucia C. & Antonio I)
  + 2 additional similar contracts asked by Roberto Tartaglia last week (Davide S. and V. Camillo)
Amount: ≈40 k€ in total during the year 2022
Track& compensate expenses (not necessarily contracts) on items beyond the goal of an Institution
    Are there similar situations for other Institutions? yes
      two of them are in the cost book
          1.08.01.01.25 Loan to UCLA for prototyping work 85 k€ spent in 2019 by Naples
          1.01.01.15 DS-20k UAr cryogenics test operations support 91 k€ spent in 2018 by Naples
      one is not listed, funds partly spent and partly still available
  36 k€ contribution to the mockup with money in CERN team account (INFN Roma)
  more?
How is this related to Common Funds?
  Common funds do not exist yet
  The RRB will have a strong voice in the approval of the common funds expenses
  If approved, the common funds mechanism will start in 2023
  Here we are talking about previous expenses..

## Slide 4: 2) Common funds during the construction period
Sharing rule: the IB should elaborate & approve the rule
Giuliana?
Which items are included?
  If each Institution should be responsible for his construction item, then what is left ?
  Can we include contracts?
  Should we include consumables during the construction in CR2, CR3, in Hall C?
  Should we include some of the unfunded items? We need attention

## Slide 5: 3) Gd loaded acrylic procurement
We left before holidays expecting that updates will be given in the first half of Sept
The TPC group strongly push for having the mockup in Gd loaded acrylic
(different from the MB discussion at the end of July)
We urgently need a draft of the contract with DonChamp: Yi is very worried that Donchamp is going to book
time & infrastructures for other jobs
Updates about the strategy?

## Slide 6: Funding items for the Sept. 28th Forti meeting
Request
4) Provide the baseline of the cost (and schedule)
some updates of the INFN costs since June (PCB tender, ASIC packaging, renting of a storage place for material,
3 ladders for the cryostat, additional items for the cryostat...)
Some change in the cost book entries (done in my local copy)
We still miss several details
actual estimation of the cost of the cryostat & cryogenics
are the money included in the CERN-LNGS MoU suff. , do we have contingency, do we miss money?
full list of items with their costs not included in the CERN contract
installation costs in CR2
5) Template for build EVM plots distribuited by Cat
Cost integrated over activity: OK
My comment: the panel wants to see also more details
For each entry they want to see the expected cost (baseline) and then the actual money spent or the updated cost

## Slide 7: Time slot for the FB meeting
Friday 5 PM CET ?