## INFN CSN2
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.0 Management Coordination
DS.0.01 Management Support
DS.0.01.03 Management Support INFN
0.01.03.15 | Construction period travel | 04-Jan-2022 A | 2025-12-30 | 12.5% | INFN CSN2 | Genoa | 960000 | 0
DS.1 Detector
DS.1.05 Veto
DS.1.05.01 Inner Veto Development
1.05.01.01.45 | Determination of cryo-mechanical properties of Gd-loaded PMMA | 29-Apr-2022 A | 26-May-2022 A | 100% | INFN CSN2 | Genoa | 2000 | 0
1.05.01.01.50 | Gd compounds lab tests & industrial samples [2022] | 2022-06-30 | 2022-12-14 | 0% | INFN CSN2 | Genoa | 35000 | 0
DS.1.08 Prototypes
DS.1.08.01 Prototype TPC - Proto-0
1.08.01.01.50 | Commissioning of Proto-0 @ Naples | 17-Sep-2021 A | 30-Jun-2022 A | 100% | INFN CSN2 | Naples | 50000 | 0
1.08.01.01.55 | Consumables for Proto operation procurement | 11-Jan-2022 A | 2024-01-31 | 20% | INFN CSN2 | Naples | 50000 | 0
1.08.01.01.80 | Proto calibration system fabrication | 25-Jun-2021 A | 2022-08-31 | 85% | INFN CSN2 | Naples | 55000 | 0
DS.1.08.02 ReD
1.08.02.01.01.40 | ReD TPC & cryogenics [2022] | 2022-06-30 | 2022-10-31 |  | INFN CSN2 | Naples | 10000 | 0
1.08.02.02.40 | ReD Commissioning & ops. [2022] | 2022-11-30 | 2023-01-16 |  | INFN CSN2 | LNS | 5000 | 0
DS.2 Photodetectors
DS.2.01 Development
DS.2.01.03 Optical Transmission R&D
2.01.03.85 | Completion of optical link development | 19-Jan-2022 A | 27-May-2022 A | 100% | INFN CSN2 | Bologna | 2000 | 0
DS.2.01.04 Integrated Electronics Development
2.01.04.55 | ASIC active substrate prototyping [2022] | 31-Mar-2022 A | 27-Apr-2022 A |  | INFN CSN2 | Torino | 36000 | 0
DS.2.02 TPC Photodetectors Production
DS.2.02.02 Tiles & PDU Production
2.02.02.040 | Production TPC tiles electronics components procurement | 03-May-2022 A | 2022-10-17 |  | INFN CSN2 | LNGS | 140000 | 0
2.02.02.045 | Production veto tiles electronics components procurement | 03-May-2022 A | 2022-10-17 |  | INFN CSN2 | LNGS | 20000 | 0
2.02.02.050 | Production TPC MB electronics components lot 0 procurement | 03-May-2022 A | 2023-01-12 |  | INFN CSN2 | LNGS | 100000 | 0
2.02.02.060 | Production veto MB electronics components (ASIC excluded) procurement | 02-Jun-2022 A | 2022-10-17 |  | INFN CSN2 | LNGS | 40000 | 0
DS.2.02.08 Connections & Power
2.02.08.02.10 | MB connectors production [2022] | 2022-06-30 | 2022-12-14 |  | INFN CSN2 | Milan | 34000 | 0
DS.2.04 PDU Test Facility
DS.2.04.01.02 Setup - Readout System
2.04.01.02.090 | Fibers for light distribution | 30-Mar-2021 A | 25-May-2022 A | 100% | INFN CSN2 | Naples | 68000 | 0
2.04.01.02.100 | Signal transmission lines | 22-Jun-2021 A | 25-May-2022 A | 100% | INFN CSN2 | Naples | 85000 | 0
DS.2.04.03 Production Testing
2.04.03.15 | Assembly machine procurement | 08-Feb-2022 A | 2022-12-14 |  | INFN CSN2 | Naples | 150000 | 0
2.04.03.30 | Cryogenic liquids for PDU test facility procurement | 2022-06-30 | 2026-05-25 |  | INFN CSN2 | Naples | 25000 | 0

## INFN CIPE
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.2 Photodetectors
DS.2.02 TPC Photodetectors Production
DS.2.02.01 SiPM Wafer Production
2.02.01.15 | SiPM wafer production at LFoundry procurement integration | 11-Jan-2022 A | 2022-08-22 | 75% | INFN CIPE | LNGS | 103080 | 0
DS.2.02.02 Tiles & PDU Production
2.02.02.055 | Production TPC MB electronics components lot 1 procurement | 03-May-2022 A | 2022-10-17 |  | INFN CIPE | LNGS | 30000 | 0
2.02.02.065 | Solder for TPC PDU production procurement | 27-Jun-2022 A | 2022-08-26 |  | INFN CIPE | LNGS | 30000 | 0
2.02.02.070 | Extra electronics components for 2 channels sum procurement | 2022-06-30 | 2022-12-14 |  | INFN CIPE | LNGS | 27000 | 0
2.02.02.075 | Pillars for PDU mounting | 02-Jun-2022 A | 2022-11-18 |  | INFN CIPE | LNGS | 20000 | 0
2.02.02.080 | TPC tile PCBs production | 03-May-2022 A | 2023-01-12 |  | INFN CIPE | LNGS | 480000 | 0
2.02.02.085 | Veto tile PCBs production | 03-May-2022 A | 2022-10-17 |  | INFN CIPE | LNGS | 110000 | 0
2.02.02.100 | Radio-pure indium for TPC tiles production | 2022-06-30 | 2022-10-19 |  | INFN CIPE | LNGS | 111000 | 0
DS.2.03 Veto Photodetectors Production
DS.2.03.02 vFEBs Production
2.03.02.05 | ASIC production | 2022-06-30 | 2022-12-29 |  | INFN CIPE | Torino | 50000 | 0
2.03.02.10 | ASIC packaging costs | 2022-06-30 | 2022-12-28 |  | INFN CIPE | LNGS | 160000 | 0
DS.2.05 NOA
DS.2.05.01 NOA Facility
2.05.01.01.65 | NOA structure & furnitures procurement | 01-Oct-2021 A | 2022-09-05 |  | INFN CIPE | LNGS | 1706822 | 0
2.05.01.02.145 | Carriers for flip-chip bonder procurement | 2022-06-30 | 2022-07-27 |  | INFN CIPE | LNGS | 36600 | 0
2.05.01.02.150 | Automated tray for flip-chip bonder procurement | 2022-06-30 | 2022-09-05 |  | INFN CIPE | LNGS | 61000 | 0
2.05.02.25 | Clean room dresses (12 operatos x 24 mos.) and other consumables | 03-May-2022 A | 2022-08-29 |  | INFN CIPE | LNGS | 60000 | 0
DS.3 Infrastructure and Installation
DS.3.02 Hall C Infrastructure Preparation
DS.3.02.01 Mechanical Infrastructure
3.02.01.10 | Hall C concrete basement floor construction | 2022-07-15 | 2022-09-15 |  | INFN CIPE | LNGS | 60000 | 0
DS.3.03 Cryostat
DS.3.03.01 Cryostat Installation Support
3.03.01.02.10 | Storage rental for materials (1,000 m2, 18 mos.) | 2022-07-01 | 2023-09-26 |  | INFN CIPE | LNGS | 132000 | 0
3.03.01.02.35 | Professional services (CSP, DL) for warm structure construction support | 2022-07-01 | 2023-02-03 |  | INFN CIPE | LNGS | 130000 | 0
3.03.01.02.40 | Surveyors supporting cryostat installation | 2022-07-01 | 2023-04-11 |  | INFN CIPE | LNGS | 10000 | 0
3.03.01.02.45 | Additional tools & materials during cryostat installation | 2022-07-01 | 2023-09-26 |  | INFN CIPE | LNGS | 75000 | 0
DS.3.05 DS-20k Installation
DS.3.05.01 Installation Preparation
3.05.01.185 | Additional funds for for Hall C installation activities | 01-Jul-2022* | 2024-06-28 |  | INFN CIPE | LNGS | 727865 | 0

## INFN PON
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.2 Photodetectors
DS.2.02 TPC Photodetectors Production
DS.2.02.01 SiPM Wafer Production
2.02.01.10 | SiPM wafer production at LFoundry procurement | 11-Jan-2022 A | 2022-08-22 | 75% | INFN PON | LNGS | 5435000 | 0
DS.3 Infrastructure and Installation
DS.3.03 Cryostat
DS.3.03.01 Cryostat Installation Support
3.03.01.02.60 | Extra costs of cryostat and cryogenics (ref. MoU INFN-CERN) | 2022-10-03 | 2023-07-26 |  | INFN PON | Roma1 | 727000 | 0
DS.3.03.02 Warm Structure
3.03.02.01.25 | Steel I-beams procurement, manufacture & delivery | 01-Mar-2022 A | 2022-09-22 | 50% | INFN PON | LNGS | 195000 | 0
3.03.02.01.30 | Steel plates procurement, manufacture & delivery | 02-May-2022 A | 2022-09-30 | 35% | INFN PON | LNGS | 56000 | 0
3.03.02.01.35 | Procure Miscellaneous material (incl. seismic brackets) | 25-May-2022 A | 2022-10-12 | 16% | INFN PON | LNGS | 146000 | 0
3.03.02.01.40 | Custom tools construction | 14-Apr-2022 A | 2022-08-03 | 65% | INFN PON | LNGS | 138000 | 0
3.03.02.01.45 | Procure consumables for installation | 14-Apr-2022 A | 2022-08-03 | 65% | INFN PON | LNGS | 417000 | 0
DS.3.03.03 Cold Structure
3.03.03.01.10 | Engineering fees (GTT Contract) | 01-Mar-2022 A | 2022-07-15 | 85% | INFN PON | LNGS | 1024000 | 0

## INFN MIUR (Urania)
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.4 Urania
DS.4.01 Construction
DS.4.01.01 Plant Development & Fabrication
4.01.01.01.35 | Polaris procurement, fabrication, testing | 08-Jul-2020 A | 06-Apr-2022 A | 100% | INFN MIUR | Naples | 6578000 | 0
4.01.01.01.45 | Polaris delivery of plant components | 2022-09-08 | 2022-12-29 |  | INFN MIUR | Naples | 411125 | 0

## INFN RAS (Aria)
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.5 Aria
DS.5.01 Aria Construction
5.01.03.02.35 | Funds for Seruci-0 argon commissioning and run | 01-Jul-2021 A | 2022-10-07 | 78% | INFN RAS | Cagliari | 300000 | 0
5.01.04.045 | In-shaft columns fine adjustment procurement & installation | 01-Jul-2021 A | 2023-03-29 | 55% | INFN RAS | Cagliari | 300000 | 0
DS.5.03 DArT Project at LSC
5.03.03.15 | Travel for integration | 20-Jul-2021 A | 2022-07-20 |  | INFN RAS | Cagliari | 10000 | 0

## NSF
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.1 Detector
DS.1.01 UAr Cryogenics
DS.1.01.01 Development
1.01.01.85 | Install UAr cryogenics in Hall C test area | 2022-09-01 | 2022-10-05 |  | NSF Construction | UCLA | 20000 | 0
DS.4 Urania
DS.4.01 Construction
DS.4.01.03 Site Preparation
4.01.03.01.30 | Warehouse & staging space rental | 2022-09-08 | 2023-07-17 |  | NSF Construction | Houston | 144000 | 0
4.01.03.01.35 | Oversight construction coordinator hire | 2022-09-29 | 2024-03-20 |  | NSF Urania | Houston | 238000 | 0

## CFI
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.1 Detector
DS.1.02 Inner Detector
DS.1.02.02 Proto / Mock TPC
1.02.02.75 | Fabrication of proto / mock TPC anode, cathode | 2022-06-30 | 2022-11-30 |  | CFI DarkSide | Alberta | 346500 | 0
DS.1.02.03 Tools for TPC Assembly & Fabrication
1.02.03.01.20 | Glovebox, transfer system & monitoring (for coating panels) procurement, assembly & development | 29-Oct-2021 A | 2022-12-21 |  | CFI DarkSide | Carleton | 63339 | 0
1.02.03.01.35 | TPC manipulator design, fabrication & shipping | 2022-08-01 | 2023-05-24 |  | CFI DarkSide | Alberta | 417458 | 0
1.02.03.01.50 | Clevios coating system fabrication & assembly | 03-Sep-2021 A | 2023-02-20 |  | CFI DarkSide | Carleton | 71500 | 0
DS.1.06 Electronics and DAQ
DS.1.06.01 Readout
1.06.01.01.25 | Readout boards firmware and software for development and production | 01-Oct-2021 A | 2023-03-23 |  | CFI DarkSide | TRIUMF | 240826 | 0
1.06.01.03.10 | Signal cable assembly | 2022-06-30 | 2023-07-03 |  | CFI DarkSide | TRIUMF | 10975
DS.1.06.02 DAQ
1.06.02.01.05 | Clock & trigger distribution system procurement | 22-Feb-2022 A | 2023-03-23 |  | CFI DarkSide | TRIUMF | 92943 | 0
1.06.02.01.10 | Clock & Trigger system design and firmware development | 22-Feb-2022 A | 2023-09-07 |  | CFI DarkSide | TRIUMF | 533325 | 0
1.06.02.02.25 | Front-End DAQ processing software development | 21-Sep-2021 A | 2024-04-03 |  | CFI DarkSide | Queen's | 355555 | 0
1.06.02.02.30 | Trigger and data processing code development | 21-Sep-2021 A | 2024-04-03 |  | CFI DarkSide | TRIUMF | 156268 | 0
1.06.02.02.35 | Control and data transfer software development | 21-Sep-2021 A | 2024-04-03 |  | CFI DarkSide | TRIUMF | 456565 | 0
1.06.03.10 | Readout coordinator support | 30-Nov-2020 A | 2024-03-05 |  | CFI DarkSide | TRIUMF | 293040 | 0
1.06.03.15 | Readout coordination travel support | 15-Jan-2021 A | 2023-09-28 |  | CFI DarkSide | TRIUMF | 155799 | 0
DS.4 Urania
DS.4.01 Construction
DS.4.01.01 Plant Development & Fabrication
4.01.01.03.10 | Development and fabrication of gas sampling & analysis system | 2022-08-11 | 2023-05-01 |  | CFI DarkSide | Carleton | 340000 | 0

## STFC
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.2 Photodetectors
DS.2.03 Veto Photodetectors Production
DS.2.03.01 vTiles Production
2.03.01.05 | Packaging technician (1 FTE) UK | 2019-12-02 | 2024-11-01 |  | STFC | RHUL | 135000 | 0
2.03.01.15 | Veto tiles production line training engineering support | 01-Sep-2021 A | 30-Jun-2022 A |  | STFC | RHUL | 197654 | 0
2.03.01.20 | Veto tiles production line training consumables procurement | 01-Sep-2021 A | 30-Jun-2022 A |  | STFC | RHUL | 20000 | 0
2.03.01.25 | Veto tiles production and characterization (in UK) engineering and technical support | 2022-06-30 | 2023-04-28 |  | STFC | Liverpool | 133298 | 0
2.03.01.30 | Veto tiles production consumables procurement | 2022-06-30 | 2023-04-28 |  | STFC | Liverpool | 81250 | 0
DS.2.03.02 vFEBs Production
2.03.02.20 | vFEB packaging consumables procurement | 03-Jan-2022 A | 2023-03-01 |  | STFC | Birmingham | 20956 | 0
2.03.02.25 | vFEB assembly engineering and technical support | 03-Jan-2022 A | 2023-03-01 |  | STFC | Birmingham | 91176 | 0
DS.2.03.03 vPDMs Production
2.03.03.10 | vPDM warm test stand construction engineering support | 01-Sep-2021 A | 2022-07-01 |  | STFC | Warwick | 23082 | 0
2.03.03.15 | vPDM warm test stand construction consumables procurement | 01-Sep-2021 A | 2022-08-31 |  | STFC | Warwick | 21933 | 0
2.03.03.25 | vPDM cold test stand construction engineering support | 01-Sep-2021 A | 2022-10-31 |  | STFC | Liverpool | 75594 | 0
2.03.03.30 | vPDM cold test stand construction consumables procurement | 01-Sep-2021 A | 2022-10-31 |  | STFC | Liverpool | 97100 | 0
2.03.03.40 | vPDM production engineering support | 01-Sep-2021 A | 2022-07-29 |  | STFC | Manchester | 47343 | 0
2.03.03.45 | vPDM production consumables procurement | 01-Sep-2021 A | 02-May-2022 A |  | STFC | Manchester | 23034 | 0
2.03.03.50 | vPDM assembly engineering and technical support | 2022-09-01 | 2023-06-01 |  | STFC | Manchester | 43599 | 0
2.03.03.55 | vPDM production & assembly | 01-Sep-2021 A | 2023-03-09 |  | STFC | Manchester | 23034 | 0
2.03.03.60 | vPDM warm testing technician support | 2022-09-01 | 2023-06-01 |  | STFC | Warwick | 154891 | 0

## DOE
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.0 Management Coordination
DS.0.01 Management Support
DS.0.01.01 Management Support DOE
0.01.01.15 | Mgmt advisor & personnel, Fermilab FY22 | 01-Oct-2021 A | 2022-09-30 | 75% | OHEP | FNAL | 311000 | 264531

## All Others
The Activities listed are only those which Start or Finish within a specified time window. At regular intervals (approximately monthly) the time window will advance; completed Activities drop off and upcoming Activities are added. Some Activities will accumulate a fraction of their estimated total each interval while others will accumulate all their cost at once when completed. Therefore, not every "in progress" Activity is expected to have a non-zero Actual Cost. Enter the Actual Cost for your Activities as provided by your Institution's accounting processes.
| You are not asked to update Start, Finish or % complete. The WBS managers update these using the Schedule Status Update sheet. The information is included just to show the planned timeframe when costs might come due. | [6 empty] | UPDATE THIS COLUMN | Optional - provide any comment relevant to the costs for activities. For example "full cost is paid only after completion and all items delivered"
WBS / Activity ID | WBS Name / Activity Name | Planned Start | Planned Finish | Estimated % Complete | Grant / Funds | Institution | Planned Budget aka Estimated Cost | Actual Cost to date | Comments
DS.1 Detector
DS.1.03 Materials
DS.1.03.02 QA Services
1.03.02.05 | Assay and tracking of overall background budget oversight | 08-Apr-2019 A | 2024-04-19 | 64% | AEI | CIEMAT | 87250 | 0
1.03.02.10 | Develop framework for cosmogenic & intrinsic background budget determination | 07-Apr-2021 A | 2022-09-22 | 84% | AEI | Zaragoza | 48000 | 0
DS.1.04 Calibrations
DS.1.04.02 Europe contributons
1.04.02.05 | Calibration guide tube mockup fabrication and testing (warm, cold, long term at CERN) | 11-Jan-2022 A | 2023-07-27 | 30% | IN2P3 | IN2P3 | 25000 | 0
1.04.02.15 | Procure Gas sources - 220Rn source | 2022-07-26 | 2023-05-04 | 20% | NCNP | Krakow | 10000 | 0
DS.1.05 Veto
DS.1.05.01 Inner Veto Development
1.05.01.01.55 | Industrial-scale production development - China vendor | 2022-06-30 | 2022-10-05 |  | CAS | IHEP | 30000 | 0