## Slide 1: Budget updates

## Slide 2
Work toward the cost baselining
NSF funds approved and available (beginning of Sep 2022)
Additional Canadian funds requested, waiting for answer
Definition of some major costs (all agencies) in advanced stage, but still in progress
Few selected examples are in the next table: it does not include all the items
its goal is to explain the work in progress
Some compensation between extra-cost and under-cost
Updated cost book will be shared with the panel at the end of 2022
Financial board activity with regular meetings

## Slide 3
Item | Status | Cost book estimation | Present estimation | Reason for change or updates
Gd loaded acrylic | In discussion | 409 +716 k$ | ≈1200 k$ | Contact with Princeton administration, definition of the contract, funding source in definition
PCB procurement | Tender opening | 1120 k€ | 800 k€ | Radiopurity data showed that use of standard PCB fabrication is ok
Rn abatement | Tender in preparation | 730 | 780 + ?? | Needs of external infrastructures + cost increase of the base system
CR2 modifications for TPC assembly | Design in progress | - | - | Work is in progress, missing estimation
TPC vessel | Contact with companies in progress | 1100 k€ | 1100? k€ | Waiting for a realistic quotation
Coating facilities | Design in progress |  |  | Doing all coating in Canada may be cost effective, decision in progress
Rent of a storage place for cryostat material & transportation | Not necessary | 182 k€ | - | Material stored directly in the underground lab.
Control Room in Hall C | Design in progress | 50 k€ | >> 50 k€ | Construction of a new building, Request of the LNGS director, cost evaluation in progress
Cryogenic slow control | In progress | - |  | Not explicitely included in the June cost book
Ladders for the cryostat + rails, brackets | cost evaluation in progress | - | ≈250 k€ | New items
Cost of the cryostat & AAr cryogenics | Tenders and orders in progress, AAr specs defined and project ready | 7930 k€ (VAT included) In the MoU INFN-CERN + 989 k€ | To be updated | We just reported the PON available funds, based on very old quotations without details, VAT are partially saved with deposito doganale underground,
Cryogenic support structure | Design almost ready | 205 | To be updated | Quotation based on the design is needed

## Slide 4
Institution deliverables and their budget for the MoU
MoU for the CONSTRUCTION, OPERATION and DECOMMISSIONING of the DARKSIDE-20k EXPERIMENT
not including ARIA and Urania
in preparation
draft with Agency deliverables delivered to INFN at the end of July (as requested)
Definition of 21 main deliverables (parts of the detector, work) with some sub-items
Budget obtained from the cost book of June 2022
Entries of the cost book grouped according to the new defined deliverables
Contributions of each Institute identified and individually listed
RRB: Resource and Review Board
Mandate will be fully defined in the MoU
A temporary RRB is in place since Sept 14°, 2022
Chaired by INFN
  NSF - Denise Caldwell (Darren Grant proxy when needed/appropriate)
  DOE - Kathy Turner INFN - Chiara Meroni and Marco Pallavicini
  STFC - Justin O'Byrne
  CFI - to be defined
  IN2P3 - to be defined
  ASTROCENT - Marcin Kuźniak
  CIEMAT - Roberto Santorelli
  IHEP or CAS - to be defined
Members of the collab. will be invited
See the draft of the MoU
document shared with the panel

## Slide 5
EVM light
Process for setting up a EVM light mechanism is starting
Lead by Cat James