## Slide 1
Alessandro Gallo
06/10/2022
WA 4 – RF POWER PLANTS
On going actions
Outcome closed actions & Decisions
To Do
X-band klystron procurement is still the most important ongoing activity;
Two separate tenders are progressing, for high power, high efficiency (CPI, Falone RUP) and high rep rate (Scandinova/Canon, Pioli RUP) tubes, conceived as direct orders;
The interest of the international X-band community (CERN, ST Trieste) for both developments (actually each of tender is in fact a technological devolpment in the field) is confirmed to be very high.
The procurement tender for the HE klystron is almost completed, CPI signature of the contract is imminent. Price: around 1200k€, Timeline: to be agreed at 1st critical design and in any case <24months.
The approach to the guaranteed performance of the first HE tube resulted to be prudent, 50 Hz at full specs, while 100 Hz could be reached at a reduced peak power ≤45 MW or reduced pulse duration ≤1.5 µs. Next tubes will likely reach full specs at 100 Hz.
For the high rep-rate tube we could not place the order directly to CANON. The devised workaround consisted in purchasing a full station to Scandinova, that is anyway only a partial and temporary remedy.
CANON declared the feasibility of a 400 Hz, 20 MW, 2.5 µs klystron (E37217 model, 260 k€). It can be procured through other funds (PNRR).
First contact with THALES as a possible alternative X-band tube provider resulted interlocutory, CERN has proposed a 24 months road map supporting the production of a 1st tube, THALES is evaluating.
Concluding the CPI tender and organization of a kick-off meting;
Finalizing the Scandinova tender for a full station incorporating the CANON X-band tube.
In parallel continuing dialogue with CANON to overcome the “ban” against italian public institution. A new Canon-Europe corporate should be presented soon, hope this will change the relationship.
Start contacts for the C-band high rep rate station procurement (not included in the Eupraxia R&D program, but inserted in the Rome Technopole project - PNRR).

## Slide 2
Upcoming milestones
Achievable, but delay is accumulating because of the mentioned difficulties
Potential risks
General Status
Business as usual
But some issues leaning to the critical side
CPI tender conclusion;
Scandinova tender progress;
First operation of TEX facility (waiting for authorization from regulation agencies)
Alessandro Gallo
05/04/2022
WA 4 – RF POWER PLANTS
DELAYS
INCREASING COSTS