## Slide 1: WP2 status
introduction

## Slide 2
WP2 is the Work Package dedicated to T2K detector upgrade and Neutrino Physics
Recall of the main objectives:
  Design, build, test and commission the upgrades for the T2K near detector (ND280), consisting of two TPCs and a scintillator based 3D Fine Grained Detector (Super-FGD).
  Perfect the measurements of neutrino cross-sections, in particular to pin down nuclear effects and improve modelling.
  Perform oscillation measurements with neutrinos and anti-neutrinos, both in appearance and disappearance, to maximize the sensitivity to leptonic CP violation.

## Slide 3: Tasks
WP2 is organized in 4 tasks, 2 related to T2K upgrades, and 2 to analysis
  Task 2.1: Construction and commissioning of the ND280 TPC [with participating institutes: INFN,CNRS,CEA,NCBJ,IFJ-PAN,IFAE,KEK]
  Task 2.2: Construction and commissioning of the Super FGD [UGE,KEK,U-Tokyo]
  Task 2.3: Neutrinos cross section measurement
  Task 2.4: Neutrino oscillation analysis [INFN,CNRS,CEA,NCBJ,IFJ-PAN,IFAE,UGE,QMUL,KEK,U-Tokyo]

## Slide 4: Deliverables & Milestones
Task 2.1 and 2.2
  Deliverable: Technical Design Report of the upgraded ND280; EMD: 12
  Milestone: production and test of first prototypes with front-end electronics; EMD: 24
  Deliverable: report paper on the new detectors; EMD: 48
Task 2.3
  Milestones: improved selection acceptance for cross-section measurements, EMD 24; neutrino energy reconstruction using detectors at different off-axis angles, EMD 36
  Deliverables: report on cross-sections on C and O and reduction of uncertainties, EMD 48; report on electron neutrino cross-section and reduction of uncertainties, EMD 48
Task 2.4
  Milestone: inclusion of multi-ring topologies in the event selection; EMD: 24
  Deliverable: report on CP sensitivity; EMD: 48

## Slide 5: Status of secondments
Institution | WP2 done (months) | WP2 planned | WP2 % done
INFN | 6,9 | 49,0 | 14,1%
DESY |  | 0,0 | 
OEAW-HEPHY |  | 0,0 | 
IFJ-PAN | 0,7 | 7,0 | 10,5%
UKP |  | 0,0 | 
JSI |  | 0,0 | 
METU |  | 0,0 | 
TAU |  | 0,0 | 
LAL-CNRS | 1,2 | 9,0 | 13,7%
CEA | 2,4 | 16,0 | 15,0%
IFAE | 1,0 | 12,0 | 8,1%
UNIGE | 1,6 | 18,0 | 9,1%
NCBJ | 2,8 | 17,0 | 16,3%
KCL (Qmul) | 0,0 | 3,0 | 0,0%
UKRI | 0,7 | 6,0 | 12,2%
CAEN |  | 0,0 | 
FBK |  | 0,0 | 
Total | 17,4 | 137,0 | 12,7%

## Slide 6: Comments
WP2 secondments stopped ~ Feb 2020, less than one year after the start of the project
Average usage of secondments was ~ 13% at the Jennifer2 suspension date, approx uniform across beneficiaries
After a 2-year stop, it is expected that secondments for T2K upgrades will now ramp up quite rapidly during the next > 2 years
We are now approching the installation and commissining phase
Milestones and deliverables foreseen at his phase of the project are met  see next presentations for more details