## Foglio1
CR 2 upgrade
item | Capital/Labor | Cost | Funding agency | status | Comments
docking area | capital |  |  |  | including the floor, the metal structure and the plastic walls
updgrade of the CR2 air circulation system to serve the docking area | capital
Dust measurment equipment for docking area and for CR2 | capital |  | ?
Nine extra HEPA filters | capital
Soft-wall curtain and support structure | capital |  |  |  | inside CR2, for TPC assembly
Make docking door on CR2 east side | labor
Install the nine HEPA filters | labor
Open the south side of CR2 to extract the TPC | labor
Upgrade of CR2 crane? |  |  |  |  | need to check with Hanguo
Mockup
item | Capital/Labor | Cost | Funding agency | status | Comments
Anode and cathode | capital | 131 k Euro | CFI | spent | ready, machining and coating done
Gd-PMMA barrel | capital |  | ? |  | ready, machining and coating done
Wire grid (frame+wires) | capital | 89.6 k Euro | NSF- Houston | available
Resistor chain | capital
HHV cables, feedthrough, PS | capital | 107 k Euro | NSF-UC Davis | spent | spent (57k +50k in the cost book)
Optical plane structures | capital |  | NSF- L. Grandi? / CIEMAT ?
Rods, springs,brackets, hanging system | capital |  | NSF- A. Pocar?
Reflector panels TPC | capital |  | NSF-UC Davis |  | ESR foils, PMMA panels, spacers, pins
TPB coating of ESR | labor |  | CFI
Reflectors for veto | capital |  | Astrocent |  | ESR, PEN, pins
Capacitive sensors for gas pocket | capital
Tool to clean small pieces (grid frame, resistor chain), Ultra sonic bath? | capital |  |  |  | maybe already exists - the one shown by Hanguo/the one in CR1
Tool to mount the grid | capital |  |  |  | check with Andrew, not sure we need
Tool for assembly / dry fit | capital |  |  |  | Need to be designed and detailed
Protective bags and tool to place the bags | capital
Tools to measure dust | capital |  |  |  | to be used for DS20k also
argon for operation | capital
nitrogen for operation | capital
People to assemble and run the mockup?
Transportation to hall C mockup and ID
item | Capital/Labor | Cost | Funding agency |  | Comments
Truck for mockup | labor
Tooling to move TPC from CR2 to outside |  |  |  |  | inclined planes and air bearings ?
Special lowered truck for TPC |  |  |  |  | check dimensions of all the doors
Crane truck |  |  |  |  | check if we can use one single truck
Truck for optical planes
Infrastructures in hall C