## Slide 1: EuPRAXIA@SPARC_LAB General Introduction and Project Overview
M. Ferrario, INFN
at SPARC_LAB
IV EuPRAXIA@SPARC_LAB Review Committee Meeting, LNF November 30, 2022

## Slide 2: AGENDA
30/11 Wednesday
14:30 General introduction and project overview - M.Ferrario
15:15 Scientific Case – F. Stellato
16:00 Layout & Infrastructure – A.Ghigo
16:45 Coffee Break
17:15 Sparc_Lab latest results – R.Pompili / V.Shpakov
18:00 Closed Session
01/12 Thursday
9:00 Beam dynamics S2E simulations – C.Vaccarezza
9:45 Plasma module development – A.Biagioni
10:30 FEL & Undulators – L.Giannessi
11:15 Coffee Break
11:45 RF sections & RF Power – D.Alesini
12:30 Electron beam Diagnostics – A.Cianchi
13:15 Lunch Break
14:30 Photon Beam-lines and Diagnostics – F. Villa
15:15 TDR structure and Performance Baseline Structure
16:00 Coffee Break
16:30 Closed Session
02/12 Friday
9:00 Q&A and Outlook of the next meeting
10:00 Closed Session
12:00 Report back

## Slide 3: TDR Draft Index

## Slide 4: EuPRAXIA_PP Kickoff meeting, LNF, November 24-25, 2022 116 participants = > 63 attendance + 53 remote

## Slide 5: EuPRAXIA-Preparatory Phase Consortium 34 Institutes from 12 Countries  to be merged with ESFRI Consortium
Complemented by institutes in EuPRAXIA ESFRI consortium: additional 17 institutes from France, Germany, Poland, Sweden, United Kingdom, China, Japan, United States. Russian institutes presently suspended.
Preparatory Phase

## Slide 6: EuPRAXIA-PP (Preparatory Phase) Key Facts
Prepares the implementation of the full RI in Europe
Total project volume (including in-kind): 8.3 M€
  EU funding: 2.49 M€ (EU without in-kind)
  Outside EU 0.69 M€ (Switzerland) 0.51 M€ (UK)
Work organized in 16 Work Packages
Project dates: 1 Nov 2022 – 31 Oct 2026
Coordinator and location of headquarters: INFN
34 participating organizations from 12 countries
Will establish a “Board of Financial Sponsors“ with representatives of funding agencies.
So far ~ 25% of total M&P funding (569 M€) secured. Site 1 is essentially financed.

## Slide 7: Preparatory Phase Main Goals
Managerial WP`s
  Outreach to public, users, EU decision makers and industry
  Define legal model (how is EuPRAXIA governed?), financial model, rules, user services and membership extension for full implementation
  Works with project bodies and funding agencies  Board of Financial Sponsors
Technical WP‘s (correspond to Project Clusters):
  Update of CDR concepts and parameters, towards technical design (full technical design requires more funding)
  Specify in detail Excellence Centers and their required funding: TDR related R&D, prototyping, contributions to construction
  Help in defining funding applications for various agencies
Output defined in milestones & deliverables with dates

## Slide 8: EuPRAXIA Advanced Photon Sources
Project Starting Date : December 1rst

## Slide 9
EXIN / EuPRAXIA / EuAPS
Compressor
EuAPS source
Photon line
COMB/EXIN
EuAPS
user area

## Slide 10: Recruitment strategy
Several position will be opened soon due essentially thanks to the Next-Generation EU related projects.
There will be:
Plasma Scientists
Laser engineer
Senior scientists in plasma accelerator based as EuAPS infrastructure manager.
Additional positions covering other areas will have to be opened in 2023  Difficulties in finding candidates.
Welcome 2 new Beam Dynamics Staff members:
Stefano Romeo
Alessio Del Dotto

## Slide 11: Progress on the EuPRAXIA@SPARC_LAB TDR
Significant progress for ALL working areas and working packages:
Intermediate layout basically frozen (few minor issues to be further studied)
Realization of X-Band accelerating section mechanical prototype full scale – in house
Injector layout – Completed
RF power source strategy concluded and procurement in progress  delay in the administrative procedure. CPI klystron kickoff in few weeks. Canon klystron expected begin 2023.
Ondulator strategy concluded -> 2 Beamlines in the baseline prototyping activities are ongoing
In general the TDR work is advancing according to the schedule.
Additional Manpower is about to be hired (thanks also to the PNRR Funding).

## Slide 12
Milestones Delivered

## Slide 13: R&D Cost Baseline follow up.
The spending rate for R&D has increased as expected since the definition and the design have reached a more mature level.
In particular the procurement of the most significant items are highlighted below:
X-Band high efficiency tube
X-Band high repetition rate RF station (modulator + canon klystron).
Prototype of X-Band accelerating section
Chart: R&D Cost per Working Area
| S2E Simulations | Injector | Linac | High Power RF | Plasma | FEL | User | Infrastructures | Diagnostics
Actual R&D Cost | 273.28 | 85.84 | 393.7 | 4257.7 | 128.8 | 0 | 48.5 | 54.9 | 33.7
Planned R&D Cost | 250 | 1550 | 1170 | 4080 | 970 | 360 | 225 | 100 | 230
Chart: 
| II-2020 | I-2021 | II-2021 | I-2022 | II-2022 | I-2023 | II-2023 | I-2024 | II-2024
Planned Cost | 0 | 275 | 1825 | 3575 | 6725 | 7975 | 8535 | 8835 | 8935
Actual Cost | 0 | 251.32 | 481.745 | 2102.525 | 5279.005

## Slide 14: TDR – Beam Dynamics | Machine Layout

## Slide 15: EuPRAXIA@SPARC_LAB Parameter List update 2
Electron Beam parameters from CDR
Electron Beam Parameters Nov 22
Parameter | Unit | PWFA | Full X-band
Electron Energy | GeV | 1 | 1
Bunch Charge | pC | 30 | 200
Peak Current | kA | 1-2 | 1-2
RMS Energy Spread | % | 1.1 | 0.1
RMS Bunch Length | 𝜇m | 6-4 | 24-20
RMS norm. Emittance | 𝜇m | 1 | 1
Slice Energy Spread | % | 0.03 | 0.02
Slice norm Emittance | mm-mrad | 0.5 | 0.3
Parameter | Unit | PWFA | Full X-band
Electron Energy | GeV | 1-1.2 | 1
Bunch Charge | pC | 30-50 | 200-500
Peak Current | kA | 1-2 | 1-2
RMS Energy Spread | % | 0.1 | 0.1
RMS Bunch Length | 𝜇m | 6-3 | 24-20
RMS norm. Emittance | 𝜇m | 1 | 1
Slice Energy Spread | % | ≤0.05 | ≤0.05
Slice norm Emittance | mm-mrad | 0.5 | 0.5

## Slide 16: EuPRAXIA@SPARC_LAB Parameter List update 1
Nominal FEL parameters from CDR
Parameter | Unit | PWFA | Full X-band
Radiation Wavelength | nm | 3 | 3
Photons per Pulse |  | 0.1 | 1
Photon Bandwith | % | 0.9 | 0.5
Undulator Area Length | m | 30 | 30
𝜌(1D/3D) |  | 1 | 2
Photon Brilliance per shot |  |  | 1
Parameter | Unit | PWFA | Full X-band
Radiation Wavelength | nm | 3 | 3
Photons per Pulse |  | 0.1 | 1
Photon Bandwith | % | 0.9 | 0.5
Undulator Area Length | m | 30 | 30
𝜌(1D/3D) |  | 1 | 2
Photon Brilliance per shot |  |  | 1
FEL Parameters Nov 2022
Parameter | Unit | PWFA | Full X-band
Radiation Wavelength | nm | 3-4 | 4
Photons per Pulse |  | 0.1- 0.25 | 1
Photon Bandwith | % | 0.1 | 0.5
Undulator Area Length | m | 30 | 30
𝜌(1D/3D) |  | 2 | 2
Photon Brilliance per shot |  | 1 | 
Parameter | Unit | PWFA | Full X-band
Radiation Wavelength | nm | 3-4 | 4
Photons per Pulse |  | 0.1- 0.25 | 1
Photon Bandwith | % | 0.1 | 0.5
Undulator Area Length | m | 30 | 30
𝜌(1D/3D) |  | 2 | 2
Photon Brilliance per shot |  |  | 

## Slide 17: Machine Layout
Courtesy F.Cioeta & E.Di Pasquale , A.Ghigo

## Slide 18: Injector

## Slide 19: Linac

## Slide 20: RF Power Sources

## Slide 21: Plasma Module

## Slide 22: Plasma Module

## Slide 23: Plasma Module

## Slide 24: FEL and Undulators

## Slide 25: Users and Beam Lines

## Slide 26: Diagnostics
Courtesy Cianchi, Biagioni, Stella, Shpakov, Franzini

## Slide 27: Building Status

## Slide 28: Building Rendering

## Slide 29: Schedule Update

## Slide 30: Milestones work in progress

## Slide 31: Project Office Status
The Project Management activities has been carried out as expected. A lot of effort has been put in defining parallel projects devoted to the consolidation of EuPRAXIA iniative in particular EuAPS, EuPRAXIA Preparatory Phase.
The project office of the whole EuPRAXIA iniative is increasing its momentum. One additional resource has been hired specifically for the management of the EuPRAXIA Preparatory Phase Project. A scientific secretary is about to be hired beginning of 2023.
A comprehensive project management plan has been set up for EuAPS project which is quite demanding from management perspective (bimestral monitoring and a remarkable amount of tender to be issued in a very short time frame).
In the next semester the major effort will be put in the definition of a comprehensive configuration and project breakdown structure. This will help in the estimation of the implementation cost.
By the end of 2023 we expect to start the activities for the planning of the Implementation phase and to start the redaction of the TDR itself.

## Slide 32: Conclusions