## Slide 1
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Outline

## Slide 2
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
EuPRAXIA -
Beam Driven Pillar
Eu- Research Infrastructure
EuPRAXIA@SPARC_LAB
EuPRAXIA - PP
EuPRAXIA - DN
EuAPS
EuPRAXIA Building
SPARC_LAB
TEX
FLAME
Existing Facilites @LNF supporting EuPRAXIA R&D

## Slide 3
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Short History
First Idea discussed for the application
Jan/2022
Application upload
22/02/2022
Application outcome
Ranking 1st
30/05/2022
Official Start of the project
01/12/2022
End of the project (not later than 31/12/2025)
30/05/2025
(+6months)
31/12/2023
All tenders closed

## Slide 4
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 5
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Project Description - WBS

## Slide 6
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Budget baseline
Costs included in the request for funding (€) |  |  | 
 | To be located within the eight southern regions | To be located outside the eight southern Regions | Total requested grant
Fixed term personnel specifically hired for the project | 270.000,00 | 1.258.000,00 | 1.528.000,00
Scientific instrumentation and technological equipment,software licenses and patent | 6.917.812,47 | 10.865.386,00 | 17.783.198,47
Open Access,Trans National Access, FAIR principle implementation | 0,00 | 0,00 | 0,00
Civil infrastructures and related systems | 1.300.006,38 | 280.000,00 | 1.580.006,38
Indirect costs, including running costs | 575.081,15 | 869.302,00 | 1.444.383,15
Training activities | 0,00 | 15.000,00 | 15.000,00
Total | 9.062.900,00 | 13.287.688,00 | 22.350.588,00

## Slide 7
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Budget baseline
Distribution per item
Distribution per institution
Distribution per WP

## Slide 8
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Geographical distribution
CNR-INO, Pisa
CNR-ISM, Potenza
Milan
INFN-MI
Catania
INFN-LNS
Rome
INFN – LNF, Frascati
UniTOV, Roma
CNR – ISM,Montelibretti

## Slide 9
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 10
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
EuAPS Website
EuAPS website is available now www.euaps.infn.it
Special thanks to Sara Reda & Susanna Bertelli
It will be linked to the main eupraxia project website: https://www.eupraxia-facility.org

## Slide 11
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 12
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 13
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 14
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Time Schedule Overall EuPRAXIA

## Slide 15
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Time Schedule EuAPS

## Slide 16
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Detailed time schedule must be properly fine tuned using the template provided by Intellera.
To be done in the next week.

## Slide 17
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
WP.1 | Project Management & Dissemination |  |  |  | 
Activity ID | Activity name | Milestone ID | Milestone Name | Deliverable | Due Bimester
1.1 | Project & Financial Management |  |  |  | 
1.1.1 | Project Management Plan | M1.1.1 | Approval of the Project Management plan | PMP | 1
1.1.2 | Hiring of Infrastructure Manager | M1.1.2 | Hiring of Infrastructure Manager | Hiring | 6
1.2 | Dissemination & Communication |  |  |  | 
1.2.1 | Website publication | M1.2.1 | Website pubblication | Website | 4
1.3 | Data Management |  |  |  | 
1.3.1 | Meeting EuAPS Data Policy | M1.3.1 | EuAPS Data Policy | Meeting Data policy | 3
1.3.2 | Meeting EuAPS Data Management Experience | M1.3.2 | EuAPS Data experience | Meeting Data experience | 14
1.4 | Integration with EuPRAXIA ESFRI Project |  |  |  | 
1.4.1 | Draft Report on EuAPS for EuPRAXIA TDR | M1.4.1 | Report EuPRAXIA TDR | Report EuAPS -Eupraxia TDR | 12

## Slide 18
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
WP.2 | Betatron Radiation Source |  |  |  | 
Activity ID | Activity name | Milestone ID | Milestone Name | Deliverable | Due Bimester
2.1 | Start to End simulation |  |  |  | 
2.1.1 | Hardware procurement and commissioning | M2.1.1 | Hardware Procurement and commissioning Milestone 2.1.1 M8 | A detailed scan of the betatron radiation source parameter space in the internal injection scheme, by means of numerical simulations, in order to optimize its yield and guide the design and operation. | 4
2.1.2 | Data analysis tools for betatron source characterization | M2.1.2 | Data analysis tools for betatron source characterization (report) M30 | D2.1.3 Data analysis tools for betatron source characterization (report) M30 | 15
2.2 | Plasma Source |  |  |  | 
2.2.1 | Plasma source design | M2.2.1 | Deliverable D.2.2.1 Plasma source design M12 | Deliverable D.2.2.1 Plasma source design | 6
2.2.2 | Gas jet test report | M2.2.2 | Gas jet test report M24 | D2.2.2 Plasma SourceCommissioning M30 Commissioning of the plasma source, including test of the plasma diagnostics to measure the plasma density. | 12
2.2.3 | Laser Transport | M2.2.3 | Laser Transport | D2.2.2 Plasma source Commissioning | 13
2.2.4 | Plasma Source Commissioning | M2.2.4 | Plasma Source Commissioning | D2.2.2 Plasma SourceCommissioning M30 | 15
2.3 | Timing & Synchronization |  |  |  | 
2.3.1 | Procurement of phase noise analyzer | M2.3.1 | Procurement of phase noise analyzer | D2.3.1 Commissioning timing & synchronization system M26 | 6
2.3.2 | Procurement of laser oscillator | M2.3.2 | Procurement of laser oscillator | D2.3.1 Commissioning timing & synchronization system | 10
2.4 | Online Photon Diagnostics |  |  |  | 
2.4.1 | Specs for test chamber and electron and ion spectrometers; call for tenders | M2.4.1 | Specs for test chamber and electron and ion spectrometers; call for tenders | Deliverable 2.4.1 | 3
2.4.2 | Report on Design of gas monitor | M2.4.2 | Deliverable 2.4.1 Report on Design of gas monitor M8 | D2.4.2 Report on commissioning of the gas monitor M22 | 4
2.4.3 | Installation of electron and ion spectrometers in the test chamber | M2.4.3 | Installation of electron and ion spectrometers in the test chamber | D2.4.2 | 8
2.4.4 | Commissioning of the electron and ion spectrometers | M2.4.4 | Commissioning of the electron and ion spectrometers | D2.4.3 Report on pilot experiments with the electron and ion spectrometers M30 | 14
2.4.5 | Report on pilot experiments with the electron and ion spectrometers | M2.4.5 | Deliverable - Report on pilot experiments with the electron and ion spectrometers | 2.4.5 - Deliverable - Report on pilot experiments with the electron and ion spectrometers | 15
2.5 | Users end station |  |  |  | 
2.5.1 | Design User end station | M2.5.1 | Design User end station | D2.5.1 Hardware procurement M16 Acquisition of the principal hardware to assemble the user end station, including vacuum components and mechanical actuator. | 6
2.5.2 | Assembly of the chamber with instrumentation | M2.5.2 | Assembly of the chamber with instrumentation | D2.5.2 | 13
2.5.3 | Test end station report | M2.5.3 | Deliverable - Test end station report | 2.5.3 Deliverable - Test end station report | 15
2.6 | Offline advanved Photon Diagnostics |  |  |  | 
2.6.1 | Design of cross-correlation method | M2.6.1 | Design of cross-correlation method | D2.6.1 Report on cross correlation methods M12 | 4
2.6.2 | Advanced photon diagnostics commissioning | M2.6.2 | Advanced photon diagnostics commissioning | D2.6.2 Report on Advanced Photon Diagnostics activities M30 | 12

## Slide 19
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
WP.3 | High Power Laser Beamline |  |  |  | 
Activity ID | Activity name | Milestone ID | Milestone Name | Deliverable | Due Bimester
3.1 | Clean Room Realization |  |  |  | 
3.1.1 | Clean room design | M3.1.1 | Clean room design | Infrastructure realization | 2
3.1.2 | Procurement and first payment | M3.1.2 | Procurement and first payment | Infrastructure realization | 5
3.1.3 | Second payment | M3.1.3 | Second payment | Infrastructure realization | 7
3.1.4 | Third payment | M3.1.4 | Third payment | Infrastructure realization | 10
3.1.5 | Assembling, commissioning and fourth payment | M3.1.5 | Assembling, commissioning and fourth payment | Infrastructure realization | 12
3.2 | Laser design and realization |  |  |  | 
3.2.1 | Design | M3.2.1 | Design | Laser design procurement and installation | 3
3.2.2 | Procurement and first payment | M3.2.2 | Procurement and first payment | Laser design procurement and installation | 5
3.2.3 | Second payment | M3.2.3 | Second payment | Laser design procurement and installation | 8
3.2.4 | Third payment | M3.2.4 | Third payment | Laser design procurement and installation | 12
3.2.5 | Assembling and commissioning and fourth payment | M3.2.5 | Assembling and commissioning and fourth payment | Laser design procurement and installation | 15
3.3 | Target system for High Rep.ate |  |  |  | 
3.3.1 | Design and procurement | M3.3.1 | Design and procurement | Design and realization of the target system | 12
3.3.2 | Realization and tests | M3.3.2 | Realization and tests | Design and realization of the target system | 15
3.4 | Plasma Diagnostics |  |  |  | 
3.4.1 | Design and procurement | M3.4.1 | Design and procurement | Plasma diagnostic: acquisition and installation | 5
3.5 | Secondary beam diagnostics |  |  |  | 
3.5.1 | Design, procurement and mechanical procurement and mechanical realization of diagnostic | M3.5.1 | Design, procurement and mechanical procurement and mechanical realization of diagnostic | Secondary beam diagnostic: acquisition and installation | 9
3.5.2 | Calibration under conventional beams | M3.5.2 | Calibration under conventional beams | Secondary beam diagnostic: acquisition and installation | 15

## Slide 20
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
WP.4 | High Repetition Rate Laser Beamline |  |  |  | 
Activity ID | Activity name | Milestone ID | Milestone Name | Deliverable | Due Bimester
4.1 | High rep.rate laser system |  |  |  | 
4.1.1 | Laser system design - 1 | M4.1.1 | Laser system tender and advanced payment (20%) | Laser system design (report) | 3
4.1.2 | Laser system design - 2 | M4.1.2 | Laser second payment (40%) | D4.1.1 Laser system design (report) M6 | 8
4.1.3 | Laser system specifications | M4.1.3 | Laser third (final) payment (40%) | D 4.1.2 Laser system specifications (report) M20 | 10
4.2 | High rep.rate laser system diagnostics transport and beam conditionin |  |  |  | 
4.2.1 | Laser transport and manipulation full-scale modelling | M4.2.1 | Laser transport and manipulation full-scale modelling | D4.2.1 Laser beam transport (report) M12 Design of the laser beam transport to the user’s end station, including expected performances regarding pulse duration, pointing diagnostics and so on D4.2.2 User’s beam specs and available operation modes (report) M22 Report on the expected laser figures at the user’s end station, which includes the possibility of beam longitudinal/transverse functions tailoring according to the user’s needs | 2
4.2.2 | Definition and procurement of components for laser beam transport | M4.2.2 | Definition and procurement of optics, optomechanics, etc. for laser beam transport | D4.2.1 Laser beam transport (report) M12 Design of the laser beam transport to the user’s end station, including expected performances regarding pulse duration, pointing diagnostics and so on D4.2.2 User’s beam specs and available operation modes (report) M22 | 11
4.2.3 | Definition and procurement of laser beam temporal diagnostics | M4.2.3 | Definition and procurement of laser beam temporal diagnostics | D 4.1.2 Laser system specifications (report) M20 Report on the final specs of the commissioned laser system; this will include pulse duration, pulse energy, ASE/ps pedestal contrast, short/long term energy stability, pulse spectrum, pointing stability D4.3.2 User’s area capability design (report) M22 Report on the user’s area, including the expected user’s station and related facilities/devices, timing/synchronization capabilities, irradiation station(s) characteristics/footprints D4.3.3 Final infrastructure report, including full beam line specs and available options (report) M30 Final report on the infrastructure, including all beam line specifications, with a user-oriented approach | 11
4.3 | High rep.rae laser infrastructure and users end station |  |  |  | 
4.3.1 | Clean room commissioning | M4.3.1 | Clean room commissioning | D4.3.1 Infrastructure design (report) M8 Preliminary design report of the whole infrastructure | 8
4.3.2 | Procurement of optical tables | M4.3.2 | Procurement of optical tables | D4.2.1 Laser beam transport (report) M12 Design of the laser beam transport to the user’s end station, including expected performances regarding pulse duration, pointing diagnostics and so on D4.3.2 User’s area capability design (report) M22 Report on the user’s area, including the expected user’s station and related facilities/devices, timing/synchronization capabilities, irradiation station(s) characteristics/footprints D4.3.3 Final infrastructure report, including full beam line specs and available options (report) M30 Final report on the infrastructure, including all beam line specifications, with a user-oriented approach | 10
4.3.3 | Procurement of vacuum pipes/pumps/steering chambers for beam transport | M4.3.3 | Procurement of vacuum pipes/pumps/steering chambers for beam transport | D4.2.1 Laser beam transport (report) M12 Design of the laser beam transport to the user’s end station, including expected performances regarding pulse duration, pointing diagnostics and so on D4.3.2 User’s area capability design (report) M22 Report on the user’s area, including the expected user’s station and related facilities/devices, timing/synchronization capabilities, irradiation station(s) characteristics/footprints | 13
4.3.4 | Procurement of vacuum chamber for end station | M4.3.4 | Procurement of vacuum chamber for end station | D4.3.2 User’s area capability design (report) M22 Report on the user’s area, including the expected user’s station and related facilities/devices, timing/synchronization capabilities, irradiation station(s) characteristics/footprints D4.3.3 Final infrastructure report, including full beam line specs and available options (report) M30 Final report on the infrastructure, including all beam line specifications, with a user-oriented approach | 14

## Slide 21
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Earned Value Management

## Slide 22
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 23
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Earned Value Management

## Slide 24
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it

## Slide 25
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Chart: EARNED VALUE MANAGEMENT - INTEGRATED
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8
Planned Value | 543319.0954 | 1094697.4408 | 1961163.7163 | 2995263.6033 | 4018663.4904 | 5079753.2825 | 5983298.0813 | 6860674.725
Earned Value | 831033.2775 | 2152755.9875 | 2240720.2275
Chart: SCHEDULE PERFORMANCE INDICATOR
| M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8
Schedule Performance Indicator | 1.5295 | 1.9665 | 1.1425

## Slide 26
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Follow up procedures

## Slide 27
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Interactions within main stakeholders

## Slide 28
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Interactions within main stakeholders

## Slide 29
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Change request
Change requests can be done (and eventually MUST BE DONE) through the main portal according to specific procedures.
The new baseline must be realistic, deliverable oriented and take into account the boundary conditions imposed by the PNRR rules.
We are forced to assign all the tenders by the end of the year. This imposes a serious constraint that must be treated properly.
During the next month (March2023) we will start a comprehensive survey of the modification of the schedule we have to implement and formalize.

## Slide 30
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Recruitment

## Slide 31
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Document Management System
Sharepoint as main document repository
Project Baseline Document
Templates, procurement instructions…

## Slide 32
EuAPS – Kick Off Meeting 28-02-2023
Antonio Falone
antonio.falone@lnf.infn.it
Conclusions