## Slide 1
FOOT calorimeter
Status Report
Construction

## Slide 2
Missing items:
Mechanical pieces:
- delivery of support table for calibrations in mid May
- vertical module holders being redesigned to mount in a 6x6 configuration
            Detectors:
                - delivery of last batch at the end of May
Overview

## Slide 3
Timeline:
Modules:
  - 22 modules (198 crystals) assembled, 17 of them already calibrated in temperature
  - 40 crystals ready at CERN
  - gluing at CERN (last 82 crystals) to be completed at the beginning of July
Temperature calibration:
  - to be completed by the end of July (beginning of September)
  System assembly:
  - in September, at CNAO or in Torino? (to be decided)
Overview

## Slide 4
Spares:
SiPM tiles:
  - some available from FBK
  - asked for quotation
Front-end boards:
  - quotation for
  30 pieces: 2.5 kE
  50 pieces: 3.7 kE
Overview