## Slide 1: Status of FTK & requests 2012
Paola Giannetti, INFN Pisa, for the FTK Group
ATLAS Italia, May 18, 2011
Next steps, funds in USA and Japan
Old Milestones: we are going to relax the schedule
Status of FTK work
Money requests for 2012

## Slide 2: Next Steps
CERN/ATLAS: Approval at the June CB
TDR with tested prototypes confirming performance
EB/CB approval
LHCC approval
USA funds:
FY11: Engineering funds were delayed because there was no Congressionally approved US budget until a few weeks ago.
  We now have been told to expect ∼0.5 M$ for the remaining 6 months of the fiscal year for engineering and HOLAs.
  ⇒∼6 month delay in some areas
  FY12-16: MRI result expected by late summer.
  NSF officials have suggested another source of (non-HEP) funding if the MRI doesn’t succeed –a new mid-scale instrumentation program being established in the NSF Physics Division.
  US ATLAS, as part of its planning, is looking at how to fund FTK if non-HEP sources are not available
Japan funds: Much smaller amount. Discussions are going well. Increased responsibilities are possible.

## Slide 3
NEXT: DELAY this schedule: TDR ~ at end of 2013

## Slide 4
2013

## Slide 5: New mezzanines (Chicago, LNF)
DUAL OUTPUT HOLA
Annovi, Beretta, Gatta
Clustering Mezzanine:
Under stand-alone tests
Next: to be inserted in the vertical slice
Kapliy, Shochet, Tang
Collaborazione con Bologna: Villa e Pellegrini

## Slide 6: The associative memory system
Lanza, Giannetti, Piendibene
Andreani, Citterio, Giannetti, Piendibene

## Slide 7: AMCHIP04 big Jump in technology! (LNF, Pisa, Milano + ideas from USA)
2010
180
nm
90
nm
65
nm
2011
3.80 mm
3.31 mm
64 patterns= 2 full custum cells
Annovi, Beretta, Crescioli,
Liberali, Sacco, Stabile, Hoff
Consumption & pattern density as expected
13 mm^2 = 8192 Patterns + 228 pads
Variable Resolution: high fake rejection with smaller banks
(Talk G. Volpi Animma 2011)

## Slide 8: Vertical Slice plan (I version – simplified): Bologna (EDRO) - Frascati (pixel clustering) - Milano-Pavia-Pisa (AMboard). Today running @40 MHz
Pixel clust.
Pixel clust.
S-links
Pixels
Fired
channels
Roads
S-link
  Filar board as interface between SLINK and PC
NEXT: WE WILL
USE A TILAR
(A. Negri)

## Slide 9: Vertical slice: 2011 workplan
2011 Development of global test of EDRO+AMBOARD (Villa, Giorgi, Annovi, Crescioli, Cervigni, Piendibene, Magalotti, Negri, Giannetti)
  Transfer CDF tests into TDAQ framework done
  EDRO & AMBOARD working in same crate under unique TDAQ software done
  LNF Mezzanine available: ongoing tests with Filar connections to PCs.
  FULL tests with EDRO & AMBOARD & clustering Mezzanine next
  Use of Tilar to connect to ROS next
  Tests with delivery of FTK data to many L2 CPUs when the CPUS will be in the lab
Setup of a “5kW” test stand” for boards/cooling tests (Giannetti, Lanza, Piendibene):
  PCB boards able to power 128 Amchips done, to be assembled (ordered chips, available in February).
  DELAY OF 1 COMPONENT (the DC-DC CONVERTERS) DUE TO JAPAN DISASTER
  Crate able to provide 5 kW to the boards AVAILABLE IN PISA – WILL BE AT CERN SOON
  Test of new board & production of ~5 of them - to be done
Final crate choice: discussing custom solutions with CAEN and Wiener.
Possibility to use CDF crates under study (A. Lanza, CAEN)

## Slide 10
TEST SETUP used in BOLOGNA
Downloading hits from VME into
input FIFOs
AMBOARD
EDRO
SOFTWARE developed in Pisa
( Run Control application &
Monitoring Software )
integrated in the same partition
with the EDRO one
developed in Bologna
Tested simple
monitoring functions
No high frequency failures
Data (hits & roads) written on disk for analysis and search of low frequency failures

## Slide 11: Vertical Slice plan II version (more complete): + DO (Bologna) & GigaFitter (from CDF) Today running @40 MHz
Pixel clust.
Pixel clust.
S-links
Pixels
Fired
channels
Roads
+
hits
S-link
  Filar board as interface between SLINK and PC
DO
S-link
Tracks
GigaFitter

## Slide 12
WHAT WE NEED IN THE LAB TO INSTALL
THE VERTICAL SLICE (NEXT October Version I) @ CERN
Presented to TDAQ by Negri – The lab now is empty!!
1 CRATE FOR TESTS
1 CRATE FOR STORAGE OF SPARES
A COUPLE OF TABLES.
One should have 1 PC with FILAR
to be used to send pseudo detector data
1 GOOD OSCILLOSCOPE (+ 1LA?)
+
1 ROS WITH TILAR
TO RECEIVE DATA FROM FTK &
DISTRIBUTE THEM TO CPUs
1 RACK
PISA SETUP

## Slide 13
Richieste 2012 – linee guida
Produzione rimandata
2011 si costruiscono pre-prototipi
2012 prototipi finali
chip AM 2012: possibilita’ di fare un’altro prototipo if needed
Richieste 2012
Milano: AMchip II : 60 keuro S.J. al test di AMchip I
Pisa: 15 keuro nuovo prototipo AMBoard
Pavia: 15 keuro LAMB
LNF: 15 keuro mezzanina e scheda test Amchip
Bologna: 3 keuro (spese di laboratorio)
Tot: 48 keuro + 60 keuro S.J.

## Slide 14: Conclusions
Delays compared to the initial schedule due to change of LHC shutdown time:
  2015 installation of the first part of FTK
  ~end of 2013 submission of TDR
  Production delayed to 2014
  Challenging prototypes made into 2 steps
However FTK is very active and has a nice plan to take data with the vertical slice in 2012 and to demonstrate how useful is FTK

## Slide 15
Backup

## Slide 18
FTK: Projects to Institutions
4 DF crates:
cluster finding
split by layer
8 “core” crates:
AMboard
Data Organizer
GigaFitter
S-links
Raw data
ROBs
Track data
ROB
Pisa & Frascati & Fermilab
the AMChip could be 3D
Frascati-Waseda:
Clustering in
Pixels-SCT
mezznines
Pixels
& SCT
RODs
Chicago GigaFitter + Data Organizer + HW
Pisa:
AMBoard
Illinois:
Final board
in core crate
USA-Italy
“2-outHola”
Fermilab:
DF motherboards
USA+Italy: crates + links + backplanes…
1 Readout Crate
Argonne

## Slide 19
LAMB
Standard cell chip
40 MHz clock
FPGA
for
Roads
AMBoard
P3
serial
LVDS
Control
FPGA
FPGA
for
SS
Input
AM0+TSP+DO+TF+HW
CPU vme
AM1+TSP+DO+TF+HW
AM2+TSP+DO+TF+HW
AM3+TSP+DO+TF+HW
AM4+TSP+DO+TF+HW
AM5+TSP+DO+TF+HW
AM6+TSP+DO+TF+HW
AM7+TSP+DO+TF+HW
11LayFit+HW
AM10+…..
AM11+…..
AM12+…..
AM13+……
AM14+…..
AM8+…..
AM9+…...
11LayFit+ HW final
AM15+…..
11LayFit+ HW final
11LayFit+HW
OPTION A
AUX card
Connectors for
Hits LVDS Cables
DO+TF+HW
HW
TF
DO
DO
INPUT
FIFOs
HW
TF
DO
HW
TF
DO
HW
TF
DO
Connectors for
tracks output
Interface
SSMAP
Processing Unit
Pisa +Chicago
ITALIAN DUTIES for
3x10**34
PISA
DATA FORMATTER
FRASCATI
FERMILAB