## Slide 1: 2023 CNAO data taking
Matteo Morrocchi, Francesca Cavanna

## Slide 2: Schedule
Monday | Tuesday | Wednesday | Thursday | Friday | Saturday | Sunday
16 Oct. Accelerator downtime | 17 Oct. | 18 Oct. | 19 Oct. | 20 Oct. | 21 Oct. Night Shift (8h) Beam Tuning | 22 Oct. Night Shift (6h) Beam Tuning
23 Oct. Installation | 24 Oct. Installation | 25 Oct. Installation | 26 Oct. Installation | 27 Oct. Night Shift (8h) Calo Screen Saver Run | 28 Oct. Night Shift (8h) Vertex Calibration Installation | 29 Oct. Night Shift (6h)
30 Oct. | 31 Oct. | 1 Nov. | 2 Nov. | 3 Nov. | 4 Nov. After. Shift (8h) | 5 Nov. After. Shift (8h)
6 Nov. Night Shift (6h) | 7 Nov. Night Shift (6h) Uninstallation Emulsion Run | 8 Nov. Uninstallation | 9 Nov. Uninstallation | 10 Nov. | 11 Nov. Next Exp. In Exp. Room. | 12 Nov.

## Slide 3: Documentation
Need to fill the required safety modules:
- Module for radioprotection, one for each participant (please check the expiration date of your medical certificates and send a copy to me)
- Declaration of possession of requirements for professional and technical suitability, one for each institution
- Safety Approval Form, one for the whole experiment
All modules are available here. The deadline to collect the documentation is September, the 22nd
In addition:
- An online course (0.5 h) needs to be attended, and a form needs to be filled.
- Each Local Coordinator should send to us the participant list specifying (if possible) dates of arrival and departure, radioprotection status, and the means of transportation used by each group (i.e. to optimize the number of vans to be used).

## Slide 4
Measurement Plan
Detector Calibrations (2-3 shifts):
Calorimeter (8h screen saver calibration)
Vertex and Tracker (6h calibration)
Fragmentation measurements (3 shifts):
It would be nice to have a first fragmentation run (also few hours) the 29th of October, so to have some days to analyze the data before the second part of the data taking.
Target?
Emulsion run (1 shift):
2 irradiations with C and C2H4.

## Slide 5: Installation
For the CALO screen saver run, no other detector should be on the beam line, this calibration will be performed at the beginning of the data taking. So it would be nice that:
All the detectors will be installed on the beamline by the 26th to test the whole apparatus (without beam).
Move the detectors out of the beamline, except for the calorimeter, the 27th.
Mount again the morning of the 28th
Remember: Installation dates may change according to the availability of the construction site for the access with the van(s). A meeting with Venchi will be scheduled soon to organize the access. Since the calorimeter will be transported at CNAO fully assembled, it would be easier to access from the construction site also with this detector.
The more the system gets complex, the more the installation needs to be planned and performed in steps…
Let’s avoid having 20 people at the same time in the cave
Space will be reduced compared to last data taking
Step by step plan divided into 2 days to coordinate the activities in the room (4-5 shifts)

## Slide 6: Uninstallation
All the materials have to be removed from the experimental room before November, 11th.
Materials cannot be left at CNAO, some exceptions for limited volumes can be discussed with Marco, but please let us know in advance if this is needed, so to identify a possible solution.
Also the uninstallation needs the coordination with the construction site.

## Slide 7: Detector Geometry
A sketch of the detector geometry in the fragmentation electronic setup should be provided as soon as possible, so to have the right configuration in the simulations.
What should be defined?
position of the TW-Calorimeter with respect to the nominal beam axis
TW-target preferred distance
MSD distance from target
…
Since we have new/larger detectors compared to the last data taking, it would be nice to collect the channel map (including the right orientation and position of each channel) for each detector before the data taking.

## Slide 8: Update from the detectors
Emulsion
Start Counter
Beam Monitoring
Vertex/Tracker
Magnet
MSD
TW
Calorimeter
DAQ

## Slide 9: Emulsion Run
Two bricks, C and C2H4.
Emulsions need to leave CNAO asap after irradiation to go back to Naples. Is a radioprotection survey needed before emulsions leave CNAO? Need to coordinate with Ferrarini
Integration of the Emulsion support in the table needs to be discussed.
Need for a scan spanning an area of 2.4 cm x 2.4 cm with a 15-18 kg brick.
→ Can CNAO magnets be used for this purpose?
Maybe this can be verified the night of October 21-22, but if we are not sure, a backup solution must be found. Does CNAO have something? Otherwise we should study a solution.

## Slide 10
Notes
Documents in preparation:
FOOT Installation documentation
Geometry and detector maps documentation
Safety Approval Form
This presentation is continuously updated and can be found at the following link:
https://docs.google.com/presentation/d/1Z5GhAc4msEjNLL_mqJcTx-BF5PDRneSg/edit#slide=id.p1