## Slide 1: NSF Status: DarkSide-20k and Urania
Cristiano Galbiati | Princeton University | October 5, 2023
Presentation to DarkSide-20k RRB

## Slide 2: Status of DarkSide-20k
From Q2 2023 EVM report (filed July 24, 2023; at work on Q3 2023 report, expected Oct 20):
  CPI~125% & SPI ~140%;
See following slides for summary of financials and schedule from Q2 2023;
Savings for $520k netted through Q2, expected to raise to ~$700k at the end of Q3 2023;
NSF granted all funds for Year 2 of the program (FY2024) on August 15, 2023;
I&I grant (formerly known as “Base”) successfully renewed for 3 years on Augusts 31, 2023;
CR#1 and CR#2 duly examined and vetted but formal process of approval still pending;
CRs in the pipeline:
  Manufacturing of steel optical planes ($300k);
  Contribution to Gd-PMMA (t.b.d.).

## Slide 3: Progress as of July 30, 2023
Award | Award Start | Award End | Total Project Cost (TPC) PMB + contingency
 | 09/01/2022 | 08/31/2025 | $11.711M
Project Budget | PMB Performance Mgmt Budget | ETC Estimate-to-Complete | Remaining Funds
 | $9.035M | $7.495M | $7.826M
Budget Contingency | Awarded | Remaining | 
 | $2.675M | $2.675M | 
Performance Indicators | WC Work Completed | CPI Cost Perf. Index | SPI Schedule Perf. Index
 | 19.2% | 1.27 | 1.42

## Slide 4
Earned Value Metrics Q2-2023 |  | 
BAC | 9.034.829 US$ | 
PV | 1.083.550 US$ | 
EV | 1.540.348 US$ | 
AC | 1.209.153 US$ | 
SPI | 142 % | EV / PV
CPI | 127 % | EV / AC
EAC | 8.703.634 US$ | EAC = AC + (BAC – EV)
EAC-C-PI | 7.092.222 US$ | BAC / CPI
EAC-C/S-PI | 5.437.568 US$ | AC + [(BAC – EV) / (CPI × SPI)]
ETC-Simple | 7.494.481 US$ | EAC - AC
ETC-Trend | 5.883.069 US$ | (EAC - AC) / CPI
SV | 456.798 US$ | EV - PV
CV | 331.195 US$ | EV - AC
VAC | 331.195 US$ | BAC - EAC
WC | 19,2 % | ∑i (WCi × BACi) / BAC
Remaining Funds | 7.825.676 US$ | BAC - AC
Table II.B: Earned value metrics for partial Q2-2023. |  | 

## Slide 5
Chart: Date
| Q4-2022 | Q1-2023 | Q2-2023 | Q3-2023 | Q4-2023 | Q1-2024 | Q2-2024 | Q3-2024 | Q4-2024 | Q1-2025 | Q2-2025 | Q3-2025 | Q4-2025 | Q1-2026
Work Performed (EV) | 0 | 0.205 | 1.54
Actual/Obligated Cost (AC) | 0 | 0.107 | 1.209
Baseline Plan (PV) | 0 | 0.262 | 1.084 | 2.432 | 4.006 | 5.384 | 6.497 | 7.36 | 8.117 | 8.616 | 8.841 | 9.013 | 9.035 | 9.035
Figure II.C: Work performed (EV), actual/obligated cost (AC), and baseline plan (PV) vs. time.

## Slide 6
Chart: Date
| Baseline | 2023-Q1 | 2023-Q2 | 2023-Q3 | 2023-Q4 | 2024-Q1 | 2024-Q2 | 2024-Q3 | 2024-Q4 | 2025-Q1 | 2025-Q2 | 2025-Q3 | 2025-Q4 | Q4-2025
UAr base system procured, fabricated, and delivered to LNGS | 44488 | 44488 | 44488
NSF Key Deliverable: UAr cryogenics system components delivered to LNGS | 44488 | 44488 | 44488
Calibration deployment system delivered to LNGS | 44488 | 44488 | 44488
NSF Key Deliverable: Calibration System delivered to LNGS, ready for installation | 44488 | 44488 | 44488
NSF Key Deliverable: LArTPC detector components, optical planes and installation fixtures delivered to LNGS | 44420 | 44420 | 44420
TPC components (field cage, reflector, wire grid) delivered to assembly locations | 44342 | 44342 | 44342
UAr purification system procured, fabricated, and delivered to LNGS | 44292 | 44292 | 44292
Outer cage assembly and PDU integration completed | 44275 | 44275 | 44275
Detector feed-through flanges and chimneys delivered to LNGS | 44264 | 44264 | 44264
Detector hanger support system delivered to LNGS | 44174 | 44174 | 44174
Calibration guide tube procurements complete | 44119 | 44119 | 44119
Bisector | 43465 | 43555 | 43646 | 43738 | 43830 | 43921 | 44012 | 44104 | 44196 | 44286 | 44377 | 44469 | 44561
Figure III.B: Forecast (and accomplished) date as function of time for the Key Deliverables (a.k.a. KPP, Key Performance Parameters) owned by the U.S. Institutions and within the scope of the NSF Midscale RI-1 DarkSide cooperative agreement.

## Slide 7
Chart: Date
| Baseline | 2023-Q1 | 2023-Q2 | 2023-Q3 | 2023-Q4 | 2024-Q1 | 2024-Q2 | 2024-Q3 | 2024-Q4 | 2025-Q1 | 2025-Q2 | 2025-Q3 | 2025-Q4
Calibration system installed | 44611 | 44611 | 44611
UAr cryogenics delivered to Hall C | 44425 | 44425 | 44425
All Inner Detector components delivered to assembly location | 44342 | 44342 | 44342
Calibration sources delivered to LNGS | 44323 | 44323 | 44323
UAr radon removal system delivered to Hall C | 44292 | 44292 | 44292
Calibration system US components delivered to LNGS | 44274 | 44274 | 44274
Outer cage delivered to LNGS | 44143 | 44143 | 44143
Acrylic components delivered | 44069 | 44069 | 44069
DSS ready for installation onto top cap | 43999 | 43999 | 43999
Mock TPC ready for operation | 43887 | 43901 | 43981
Mockup TPC mechanical assembly test completed | 43873 | 43873 | 43950
Large deposition chamber and monitoring devices delivered to Alberta | 43839 | 43839 | 43839
Figure III.D: Forecast (and accomplished) date as function of time for the Tier 1 milestones owned by the U.S. Institutions and within the scope of the NSF Midscale RI-1 DarkSide cooperative agreement. Legenda: solid lines with black-filled romboids identify Tier 1 milestones already completed; dashed line identify Tier 1 milestones not yet completed, whose monitoring will continue in the next editions of this document.

## Slide 8
Detailed EVM Data |  |  | Budget Profile for Y1, Y2, Y3, and Cumulative Period before and after submitted or approved CRs [k$] |  |  |  |  |  |  |  | 
WBS | Description | Institution | CR# | Y1 w/o CR | Y1 w CR | Y2 w/o CR | Y2 w CR | Y3 w/o CR | Y3 w CR | Y1-3 w/o CR | Y1-3 w CR
0.01.02 | Mgmt. Support NSF | Princeton |  | US$‎ 279 | US$‎ 279 | US$‎ 139 | US$‎ 139 | US$‎ 137 | US$‎ 137 | US$‎ 555 | US$‎ 555
1.01.02.01 | UAr Base System | UCLA |  | US$‎ 130 | US$‎ 130 | US$‎ 121 | US$‎ 121 | US$‎ 103 | US$‎ 103 | US$‎ 354 | US$‎ 354
1.01.02.02 | UAr Pur. System | Columbia |  | US$‎ 591 | US$‎ 591 | US$‎ 372 | US$‎ 372 | US$‎ 265 | US$‎ 265 | US$‎ 1.228 | US$‎ 1.228
1.01.02.03 | UAr Getter | Princeton | 2 | US$‎ 0 | US$‎ 487 | US$‎ 244 | US$‎ 0 | US$‎ 244 | US$‎ 0 | US$‎ 487 | US$‎ 487
1.02.02.02 | ID Assembly Tools US | VTech & Will. |  | US$‎ 1.010 | US$‎ 1.010 | US$‎ 329 | US$‎ 329 | US$‎ 275 | US$‎ 275 | US$‎ 1.614 | US$‎ 1.614
1.02.04.01 | ID Acrylic US | VTech & Will. |  | US$‎ 409 | US$‎ 409 | US$‎ 0 | US$‎ 0 | US$‎ 0 | US$‎ 0 | US$‎ 409 | US$‎ 409
1.02.04.02 | S2 System | UCLA |  | US$‎ 41 | US$‎ 41 | US$‎ 45 | US$‎ 45 | US$‎ 6 | US$‎ 6 | US$‎ 93 | US$‎ 93
1.02.04.03 | Outer Cage | Chicago & UMass | 1 | US$‎ 134 | US$‎ 302 | US$‎ 510 | US$‎ 342 | US$‎ 74 | US$‎ 74 | US$‎ 718 | US$‎ 718
1.02.04.04 | HV System | UC Davis |  | US$‎ 168 | US$‎ 168 | US$‎ 180 | US$‎ 180 | US$‎ 111 | US$‎ 111 | US$‎ 459 | US$‎ 459
1.02.04.05 | Reflectors | UC Davis |  | US$‎ 32 | US$‎ 32 | US$‎ 99 | US$‎ 99 | US$‎ 0 | US$‎ 0 | US$‎ 131 | US$‎ 131
1.02.04.06 | Wire Grid | Houston |  | US$‎ 215 | US$‎ 215 | US$‎ 202 | US$‎ 202 | US$‎ 213 | US$‎ 213 | US$‎ 630 | US$‎ 630
1.02.05.01 | ID Flgs. & Chimneys | UCLA |  | US$‎ 118 | US$‎ 118 | US$‎ 240 | US$‎ 240 | US$‎ 154 | US$‎ 154 | US$‎ 513 | US$‎ 513
1.02.05.02 | ID Adjustable Hangers | UCLA |  | US$‎ 80 | US$‎ 80 | US$‎ 64 | US$‎ 64 | US$‎ 56 | US$‎ 56 | US$‎ 200 | US$‎ 200
1.02.05.03 | ID Integration Support | Princeton |  | US$‎ 294 | US$‎ 294 | US$‎ 450 | US$‎ 450 | US$‎ 306 | US$‎ 306 | US$‎ 1.051 | US$‎ 1.051
1.04 | Calib. Deployment US | Hawaii |  | US$‎ 177 | US$‎ 177 | US$‎ 158 | US$‎ 158 | US$‎ 50 | US$‎ 50 | US$‎ 384 | US$‎ 384
1.09 | Outreach US | Fort Lewis & PU |  | US$‎ 70 | US$‎ 70 | US$‎ 70 | US$‎ 70 | US$‎ 71 | US$‎ 71 | US$‎ 210 | US$‎ 210
All Sub-Systems |  |  |  | US$‎ 3.749 | US$‎ 4.405 | US$‎ 3.223 | US$‎ 2.811 | US$‎ 2.063 | US$‎ 1.819 | US$‎ 9.036 | US$‎ 9.036
Table V.A: Budget profile by WBS, before and after consideration of the CRs submitted and/or approved. Notable changes are highlighted. |  |  |  |  |  |  |  |  |  |  | 

## Slide 9
Detailed EVM Data |  |  | Cumulative [k$] |  |  |  | Cumulative [] |  | 
WBS | Description | Institution | BAC | PV | EV | AC | WC | CPI | SPI
0.01.02 | Mgmt. Support NSF | Princeton | 555,1 US$ | 229,2 US$ | 229,2 US$ | 165,6 US$ | 16555,5 % | 0,41 | 1,38
1.01.02.01 | UAr Base System | UCLA | 353,6 US$ | 0,0 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.01.02.02 | UAr Purification System | Columbia | 1.228,0 US$ | 162,8 US$ | 204,6 US$ | 94,4 US$ | 4408,806 % | 0,17 | 2,17
1.01.02.03 | UAr Getter | Princeton | 487,3 US$ | 0,0 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.02.02 | ID Assembly Tools US | VTech & Will. | 1.613,9 US$ | 197,6 US$ | 661,7 US$ | 558,0 US$ | 0 % | 0,37 | 1,19
1.02.04.01 | ID Acrylic US | VTech & Will. | 409,2 US$ | 141,9 US$ | 245,5 US$ | 205,4 US$ | 0 % | 0,90 | 1,20
1.02.04.02 | S2 System | UCLA | 92,9 US$ | 0,0 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.04.03 | Outer Cage | Chicago & UMass | 717,0 US$ | 61,6 US$ | 56,4 US$ | 51,9 US$ | 3459,5 % | 0,08 | 1,09
1.02.04.04 | HV System | UC Davis | 457,6 US$ | 3,2 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.04.05 | Reflectors | UC Davis | 132,2 US$ | 0,0 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.04.06 | Wire Grid | Houston | 630,5 US$ | 141,6 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.05.01 | ID Flanges & Chimneys | UCLA | 512,5 US$ | 0,0 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.05.02 | ID Adjustable Hangers | UCLA | 200,0 US$ | 0,0 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.02.05.03 | ID Integration Support | Princeton | 1.050,6 US$ | 119,6 US$ | 124,7 US$ | 116,7 US$ | 11669,7 % | 0,12 | 1,07
1.04 | Calib. Deployment US | Hawaii | 384,4 US$ | 1,1 US$ | 0,0 US$ | 0,0 US$ | 0 % |  | 
1.09 | Outreach US | Fort Lewis & PU | 210,1 US$ | 25,0 US$ | 18,1 US$ | 13,1 US$ | 0 % | 8,6 % | 1,39
All Sub-Systems |  |  | 9.034,8 US$ | 1.083,6 US$ | 1.540,3 US$ | 1.209,2 US$ | 36093,5 % | 0,19 | 1,27
Table VI.A: Detailed cost and performance data. |  |  |  |  |  |  |  |  | 

## Slide 10: Status of Urania
KM connection and metering plant ($1.0M) on track for completion Nov 2023;
Design ($0.3M) completed for sitework, on track for completion for PEMB, HHV, and interconnections;
Sitework bids received, contract under way (~$0.9M+10% ctgcy);
Soon to hit the books: storage and transportation (~$0.2M), PEMB (~$0.2M), HHV connection and switchboard (~$0.2M), transformers (~$0.1M; ~70 weeks delivery in US problematic, to be sourced from Italy);
Tight fit into overall $3.0M overall budget;
Electrical and piping interconnections, under discussion with INFN possibility of direct assignment to their contracted plant builder to avoid disputes in commissioning;
Operations confirmed to be carried out by DOE, lead lab changed to from FNAL to PNNL as per communication of Gina Rameika on Sep 25 2023, move exploits expertise of personnel that led DS-50 operations (Back, Alexander);
Final permit hearing scheduled for Monday, October 16, 2023, groundbreaking shortly after if permit granted.

## Slide 11: Status of Urania Permits

## Slide 12
the end