## Slide 1: DS-20k Optical Plane Assembly Sequence
J. Brandt – Dec 2023

## Slide 2: Order of Operations
PDU Installation – OP supported on TPC Plate
  PDU Cables
  PDU Cable Guides
Lift OP into Vertical Position
  Install PMMA Blocks
  Install IV Plate Sections
Rotate OP to rest on IV Plate
Install vPDUs / Cables
  vPDU Cable Guide design pending – Need to identify easiest point for integration

## Slide 3: Frame and PDUs
Base Frame – IV Plate removed
Base Frame – TPC Side
  TPC Plate will rest on assembly table
PDUs installed
  Assume PDUs will be installed from “underneath” OP

## Slide 4: PDU Cables and PMMA Blocks
PDU Cables
  Installed from “top” of OP while TPC Plate is still resting on assembly table OR in vertical configuration
Cable Guides
  Three types:
    Solid
    Split (Vertical Beam transits)
    Split with flat half (OP exit locations)
PMMA Blocks added in vertical configuration
  Channels in PMMA blocks avoid contact with Cable Guides
  Corner and edge blocks not shown still require modification

## Slide 5: IV Plate and vPDUs/Cabling
Single quadrant IV Plate
Full IV Plate
vPDUs Installed on IV Plate
  vPDU Cables and Cable Guides not designed yet

## Slide 6: Unknowns and Questions
What orientation is best for PDU and PDU Cable installation?
  TPC Plate supported on assembly table
  IV side supported on table with accommodations for missing IV Plate
How will PMMA Blocks be retained during assembly in vertical configuration?
How/when will vPDU Cables and Cable Guides be installed?