## Slide 1: ITk Integration Lecce May - 9th – 2024 Emiliano Dané on behalf ITk Frascati collaboration

## Slide 2: General items
The Clean Room is almost complete;
The Nitrogen plant is installed and under pressure test;
The climatic chamber now has a backup plant in case of bad-functional working of the air pressure plant. (some bottle of artificial air are connected to an automatic switch system in order to cover this item);

## Slide 3
Things to do:
Define a detailed procedure for the ITk Assembly (together with UK and the coll.)
Check the compatibility of all the assembly tool (cabling, piping ecc..) with the Assembly tool
  Make a repository for all the Assembly toolings
Find a solution for the Functional test in Climatic Chamber
Solution for the Shipping

## Slide 4: 1° attempt to go in detail for the assembly activities (focusing on weldings – S. Coelli)

## Slide 5
 | Activity | Comment | Estimated Time
1 | HS positioning | Both the empty half shelves will be in position in the trolleys and test the mating in order to do the zero | 
2 | Pipe positioning | In Milan they are testing the insertion in 2 pieces: Inlet (1) and exhaust plus the by-pass (2) in order to make it easier. Pipe holders to define (not clear to me). Pipes goes everywhere.. they are not selfsustaining. | 
3 | by-pass welding | welding of the bypass with the pipes placed inside the HS (Is there enough room for the WH?) | 
4 | Leak or/and Pressure Test | re-working (socket baseline) | 
5 | 1st Manifold welding | Suggested by Simone: socket, Mechanical tool to hold the Welding Head. Procedure has to be tested. | 
6 | Cabling (Harness) insertion |  | 
7 | C-stifness positioning |  | 
8 | Half Ring positioning | in what order do we place the half rings? (could be from high z?) | 
9 | Pipe HR welding Exhaust | 2 weldings: Start with welding the Outlet. The U (exhaust) part is custom on place. First do the welding manifold side, then HR side. Suggested socket welding. Mechanical tool needed to hold the welding head. | 
10 | Leak or/and Pressure test | Not clear | 
11 | Pipe HR welding Inlet | 1 welding. Mechanical tool to hold the Welding Head | 
12 | Leak o Pressure test |  | 
13 | HR electrical connection |  | 
Only the HS part. (with S. Coelli)

## Slide 6
by-pass welding
by-pass
Inlet

## Slide 7
1° exhaust welding
2° exhaust welding
U customized

## Slide 8
Inlet Welding
Swagelok Welding Head used in the model

## Slide 9: 1° welding on manifold and test before the cabling insertion, just after the piping positioning
Maybe more confortable putting the Assembly tool in vertical
Only half Manifold is present at this level
fitting
The recovery could be done cutting, remove the entire piping, rework in workshop and restart the process or we can use another brand new one set of pipings

## Slide 10: 2nd welding after the mating of the layer
Removing this upper part of the trolley. we don't need at this level in order to have more room for the welding head
I don't know the mapping of HV
in order to simulate the rooming available
Here the recovery could be done by sleeves or reworking the pipes

## Slide 11
Action (as mentioned by Simone):
Perform test in order to qulify the procedure assembly on aluminum prototype (in Milan).
Then with the CF prototype perform the test in Frascati. Not only for the welding but also to verify all the assemby steps.

## Slide 12: Functional test in limatic Chamber

## Slide 13
Under Study:
To do a platform and position it over the existing one in order to:
  avoid to leave a big hole in the floor when system is moved to the CC
  avoid 20cm of lifting (only few millimetrs)
  same tool as in Liverpool
Passive and active pillars (only active shown in the pictures) passing through the existing platform
Embedded wheels or external spring wheels (not clear if it fits in CC)
To be checked
Functional Test in Climatic Chamber
Floor
New platform
External spring wheels
Load cells

## Slide 14
2 companies
https://www.cel.eu/
https://www.confimibergamo.it/cospal-compositer-srl.html

## Slide 15
Synchronized electric hydraulic jacks. We used a lot for the lifting of Kloe experiment.
Pivotable wheel
Calculation of center of mass in order to find the best jack's position limiting the stresses
Use of the load cells for the load transfer from the "Assemby position" to the jacks and then on the wheel trolleys
Cylindrical wheel trolleys
Lifting Jacks

## Slide 16: Shipping
The use of the new platform involves the lengthening of the bar and the addition of 2 wheels (one per side), which must be dismantled as soon as the trolley move out from the platform in order to fit in the Climatie Chamber.

## Slide 17
Action:
Check the CAD model be consistent with real object;
in order to have a better knowledge of the assembly trolley we need to "play" with it, by using some fake or real Half Shell, not yet in Frascati
We started to think some solution. We have to converge soon in one direction;

## Slide 18: Shipping

## Slide 19
A trolley easy to move with load on the rails and
compatible with the transport box.
Fixed to the dumped basement, remove the wheels.
Once in CERN and after the test the wheels are mounted back.
Wheels are out of the room of the box, so we have to mount the lateral and upper panel, after the fixing of the trolley on the basement.

## Slide 20
Not real rails – who is the contactfor the final design?
Design of the CF flange in order to include the rails, or think to have another support to holding them
Modification in order to have a system to swicth the load, from the Head to the rails.

## Slide 21
This is the situation after the L4 mating
Once the load is transferred to the rails the heads are removed

## Slide 22
Action (very similar to the previous item):
Check the CAD model be consistent with real object;
in order to have a better knowledge of the assembly trolley we need to "play" with it, by using some fake or real Half Shell, not yet in Frascati
We started to think some solution. We have to converge soon in one direction;