## Slide 1: Project Technical Board meeting
Antonella Sciuto
WP 3 Leader & CNR unit coordinator
SWRIPS PTB Fourth Meeting
Catania, 16 April 2024

## Slide 2
WP3 aim: development of sensing systems and in particular
=>of an in-line test system for continuous monitoring of the physical and chemical parameters of the purified water to be re-used for irrigation.
Few news to be shared after our last Techinal Board Meeting…..

## Slide 3: WP3 report on performed/running activities in the period February/March
Task 3.1=> Development of sensors and electronics: Design of Silicon Carbide photo-detector is completed. Some test will be performed for the innovative electrode fabrication
Task 3.2=> Optically sensible polymeric substrates for heavy metals and pesticide detection : Activity is temporary stopped due to concomitant activity with higher priority
Task 3.3=> Detector assembly and readout software development: LED sources have been delivered and some test are running
Task 3.4 =>Detector test and calibration: will start in Month 12
Task 3.5 => Development of data network and online monitoring software for remote control: will start in the next weeks (Month 6 of the project)

## Slide 4: WP3 technical and scientific meeting calendar (every 3 months )
  coordination meeting 30 January ’24 (Done)
  deliverable meeting 24 April ’24 => D3.1 Design and flow chart preparation for the fabrication of SiC sensors (task 3.1)-M6 (April 2024)
  coordination meeting 21 July ’24
deliverable meeting 22 November ’24=> D3.2 Report on sensors fabrication and on their electro-optical characterization & D3.3 Large area SiC sensors ready and operating in deep-UV and electro-optical characterised (task 3.1)-M14 (December 2024)
deliverable meeting January ‘25=> D3.4 Optically sensible polymeric substrates for pollutant detection made and tested (task 3.2)-M16 (February 2025)
deliverable meeting April ’25 => D3.5 Spectroscopy apparatus assembled and readout software deployed and running (task 3.3) (M18) (April 2025)
  coordination meeting July ’25
  deliverable meeting November ’25=>D3.6 Report on the tests and calibration curves of the spectroscopy apparatus (task 3.4) (M25) (November 2025)
  deliverable meeting June ’25=> D3.7 Data network and remote control software (task 3.5) (M32) (June 2026)
Tasks activity will be discussed and planned during the WP meetings. Further Task meetings will be planned if necessary during the project period.

## Slide 5: Some key points for CNR activities both in the WP2 and WP3: -list of typical/residual contaminant in the water to be removed by nanostructured filters and to be monitored by sensing systems (as today shared by Lofti and by Fabio for starting waste water ….) to prepare artificial waste water in lab will be shared from WP1 and WP2 partners for effluent waste water -water samples to test nanostructured filters on real samples at month 12 and later

## Slide 6
Some other questions
Q:Do we have a template for the report delivery?
Answer: Alessia/Livio will share the template in few days
Q:Task activity report will be prepared by the task leader? Or contributions will be collected by the WP leader?
Answer:the Task Leader is responsible for the report delivery Q:Concerning the Palermo Conference: will be published papers/proceeding or only extended abstract?
Answer: at this moment only abstract but a Special issue will be maybe published