## Foglio1
Month | Day | Date | Activity - Proto-0 | Description/Parallel Activites | Comments
May | Mon | 2024-05-06 | Proto-0 AL300 Commissioning | Preparation of parts, Replacement of grid wire
May | Tue | 2024-05-07 | Proto-0 AL300 Commissioning | Preparation of parts
May | Wed | 2024-05-08 | Proto-0 AL300 Commissioning | Cleaning of parts
May | Thu | 2024-05-09 | Cryostat warming up | Cleaning of parts
May | Fri | 2024-05-10 | Cryostat warming up | All parts in Clean Room
May | Sat | 2024-05-11 | Cryostat warming up
May | Sun | 2024-05-12 | Cryostat warming up
May | Mon | 2024-05-13 | Opening of cryostat, Proto-0 assembly preparation
May | Tue | 2024-05-14 | Proto-0 assembly preparation |  | Test of PDUs in PTF completed
May | Wed | 2024-05-15 | Proto-0 assembly
May | Thu | 2024-05-16 | Proto-0 assembly
May | Fri | 2024-05-17 | Proto-0 assembly completion, closing of cryostat, PDU's warm test, pump & purge cycles, starting pumping
May | Sat | 2024-05-18 | Pumping
May | Sun | 2024-05-19 | Pumping
May | Mon | 2024-05-20 | Pumping
May | Tue | 2024-05-21 | Pumping
May | Wed | 2024-05-22 | Pumping
May | Thu | 2024-05-23 | Pumping
May | Fri | 2024-05-24 | Pumping
May | Sat | 2024-05-25 | Pumping
May | Sun | 2024-05-26 | Pumping
May | Mon | 2024-05-27 | Filling process | Start filling
May | Tue | 2024-05-28 | Filling process
May | Wed | 2024-05-29 | Filling process
May | Thu | 2024-05-30 | Filling process
May | Fri | 2024-05-31 | Filling process
June | Sat | 2024-06-01
June | Sun | 2024-06-02
June | Mon | 2024-06-03 | Filling process
June | Tue | 2024-06-04 | Filling completion, recirculation started, PDU's cold test | End of filling
June | Wed | 2024-06-05 | Single phase measurement | Purity and LY measurements
June | Thu | 2024-06-06 | Single phase measurement | Purity and LY measurements
June | Fri | 2024-06-07 | Single phase measurement | Purity and LY measurements
June | Sat | 2024-06-08 | Single phase measurement | Purity and LY measurements
June | Sun | 2024-06-09 | Single phase measurement | Purity and LY measurements
June | Mon | 2024-06-10 | Gas pocket ON, fields ON, Std dual phase measurement |  | DS General Collaboration Meeting
June | Tue | 2024-06-11 | Std dual phase measurement |  | DS General Collaboration Meeting
June | Wed | 2024-06-12 | Std dual phase measurement |  | DS General Collaboration Meeting
June | Thu | 2024-06-13 | Std dual phase measurement |  | DS General Collaboration Meeting
June | Fri | 2024-06-14 | Std dual phase measurement |  | DS General Collaboration Meeting
June | Sat | 2024-06-15 | Std dual phase measurement
June | Sun | 2024-06-16 | Std dual phase measurement
June | Mon | 2024-06-17 | Std dual phase measurement, fields raised
June | Tue | 2024-06-18 | Std dual phase measurement, fields raised
June | Wed | 2024-06-19 | Std dual phase measurement, fields raised
June | Thu | 2024-06-20 | Std dual phase measurement, fields raised
June | Fri | 2024-06-21 | Std dual phase measurement, fields raised
June | Sat | 2024-06-22 | Std dual phase measurement, fields raised
June | Sun | 2024-06-23 | Std dual phase measurement, fields raised
June | Mon | 2024-06-24 | Gas pocket increased 1
June | Tue | 2024-06-25 | Gas pocket increased 1
June | Wed | 2024-06-26 | Gas pocket increased 1
June | Thu | 2024-06-27 | Gas pocket increased 1
June | Fri | 2024-06-28 | Gas pocket increased 1
June | Sat | 2024-06-29 | Gas pocket increased 1
June | Sun | 2024-06-30 | Gas pocket increased 1
July | Mon | 2024-07-01 | Gas pocket increased 2
July | Tue | 2024-07-02 | Gas pocket increased 2
July | Wed | 2024-07-03 | Gas pocket increased 2
July | Thu | 2024-07-04 | Gas pocket increased 2
July | Fri | 2024-07-05 | Gas pocket increased 2
July | Sat | 2024-07-06 | Gas pocket increased 2
July | Sun | 2024-07-07 | Gas pocket increased 2
July | Mon | 2024-07-08 | Liquid level increased
July | Tue | 2024-07-09 | Liquid level increased
July | Wed | 2024-07-10 | Liquid level increased
July | Thu | 2024-07-11 | Liquid level increased
July | Fri | 2024-07-12 | Liquid level increased
July | Sat | 2024-07-13 | Liquid level increased
July | Sun | 2024-07-14 | Liquid level increased