## Slide 1: ME0 Module Production
Piet Verwilligen
GEM Coordination – December 19th, 2024
INFN – sezione di Bari

## Slide 2: GEM Bari & Coordination GEM
Italian institutes in GEM: Ba, Bo, LNF, Na, Pv
  29 FTE M&Ob (28%) – 52 persons on authorlist (28%)
  Core contribution: 2.6M (20%)
INFN Bari between founding institutes of CMS GEM
  Design & Responsibility for Front-End (VFAT3)
  Responsibility for Chamber Production
  CMS Italia GEM coordination P.V.
  GEM Bari: 5 staff, 3 Post-doc, 6 PhD students
Currently 4 Level-2 coordinators in GEM organigram
  Upgrade, Run-Coordination, Production, Electronics

## Slide 3: The ME0 project: challenges
ME0
Original Requirements*:
  97% module efficiency
  rad resolution
  8-10 ns time resolution
  gain uniformity
  Efficient operation at average hit rates up to 150kHz/cm2*
  Accumulate charge up to 7.9C/cm2*
  Discharge rate that does not impede performance or operation
  * updated w.r.t. TP & Muon TDR
6-Layer stack of Triple-GEM
  Install behind HGCAL (complex environment)
  stacks (20) for each endcap
  Coverage:

## Slide 4: ME0 Design: Overview
Design Inherited from GE1/1
  = 85 cm x b 29-52 cm (A=2700cm2)
  = 0.8 (8 -partitions)
  = 20.22 - 386 strips
  600um – 1200um => 920 urad
  3mm PCBs (reduced thickness)
  Gap dimensions ensured by Inner Frame
  GEMs tensionned with pull-out screws
  Gas tightness ensured by outer frame and O-rings

## Slide 5: ME0 Simplified Schedule
Procurement & QA
Module Production Q2 2024 – Q2 2026
Stack Production 2025 - 2026
today
24 months
Installation
Jan ‘27

## Slide 6: ME0 Schedule for Bari
Recap of 2024
  Started production at CERN
  1st round of Production July – September ‘24
    Reduced from 10 to 5 chambers b/c August holidays
    5 high quality chambers produced and tested up to QC5
  2nd round of Production December – February ’25
    1st chamber constructed and brought through QC5
    2nd chamber needs repair in clean room
Forecast 2025
  Finish 2nd round (8 chambers) in Jan-Feb ‘25
  Expect 2 more rounds May-July & Oct-Dec ‘25
  Total expected: 28
2025 will mark the start of Stack Assembly @ CERN
  Construction sites need to send manpower (Bari: D.Troiano)
  CERN constructionsite will move from Modules -> Stacks
    Need performand Module Production sites (IT: Ba, LNF)
    Indian sites joining, but they never build & tested GE11 A-to-Z
    This might result in a higher load on Bari construction site as it was the most performant construction site outside CERN

## Slide 7: Achievements 2024
Module Production
  Total:
    75 constructed - Expected 80 by Dec 31st 94% done
    41 validated - Expected 50 by Dec 31st 82% done

## Slide 8: ME0 Construction in CP3

## Slide 9: ME0 Construction in CP3

## Slide 10: Organization
For each ME0 Module
  ½ day of Pre-Assembly in GEM Laboratory
  ½ day of Assembly in Clean Room
    Eventually other ½ day to go back to solve problems
  ½ day for QC3 (gas leak test) and QC4 (HV test)
  1 day of flushing with dry gas
  ½ day for QC5 (Gain calibration)
  ½ day for QC5 (Gain uniformity)
  1 day back-up in case tests need to be repeated
Total: 1 module / week (in regime)
We have pool of people (Staff / Post-doc / PhD)
  “shifts” for construction in Camera Pulita
  Organization of QC3 – QC4 – QC5-I – QC5-II tests

## Slide 11: Sharing CP3 Clean Room
Since couple of years we share the CP3 clean room with ALICE (bended ALPIDE tracker)
To improve efficiency in clean room we have constructed a new foil box
  Foil capacity 7 foils -> 21 foils

## Slide 12: VFAT3 Testing @ Bari
Equally important for the construction of Stacks
  Test of Packaged VFAT3 in Bari
  10,000 chips packaged
    8000 for ME0 – 2000 for GE21
    Packaging yield: 96% (9868 good according to IMEC)
  Need to test these chips in house before mounting
    chip yield expected: 85% - need 7000 good ME0 plugin cards
    First batch of 1600 sent to plugin-card production company
    Efficiency of test-stands is decreasing – labor intensive
    New sockets needed. Expect testing January – March