## Slide 1
WP2 Activities - Project Update
Project Technical Board Meeting - 21/01

## Slide 2: UNIPA Activities
Reactivation of two granular sludge reactors after the summer holidays.
Conditions: one in anaerobic feeding, the other in fully aerobic conditions.
Steady-state achieved; complete granulation in anaerobic reactor; aerobic reactor at 50%.
Testing maximum organic load to evaluate system response in COD removal.
Upcoming: Alginate extraction and boosting experiments.
Prototype assembly for Agrumaria Corleone facility: aiming for startup by early March.
Preparation of Deliverable 2.2 report, due end of January.

## Slide 3: Montpellier Activities
Focus on granular sludge system equipped with membrane.
Research on zeolite's role in reducing membrane fouling.
Results: COD removal improved up to 98%, significant reduction in fouling.
Zeolite addition reduces cleaning frequency.

## Slide 4: CNR Activities
Development of nanocomposite coating layers based on sulfonated pentablock copolymer.
Goal: Increase contaminant removal efficiency and add antimicrobial/antibiofouling properties.
Planned experiments on biological aspects with Sebania Libertino to start soon.

## Slide 5: CERTE Activities
Characterization of wastewater from the tomato industry (COMOCAP).
Phase 1: Bioreactor with granular sludge operating in continuous mode since July.
Current focus: Enhancing granule size with chemical additives.
Future activities will aim to improve granulation.