## Sheet1
WP/Task/Deliverable |  |  |  | Schedule information |  | Progress
ID | Task | Subtask | Type | Duration | Predecessors | %done | Name1 | Name2 | Name3 | Name4 | Name5 | Name6 | Name7 | Name8 | Name9 | Name10
E1 | Mandate |  | E | 0 d | 17/12/2024
E2 | Team ready |  | E | 0 d | E1
E3 | Software package for science case |  | E | 0 d | E2
E4 | Reference triangle optical layout |  | E | 0 d | E1
E5 | Reference 2L opitcal layout |  | E | 0 d | E1
E6 | Reference triangle detector layout |  | E | 0 d | 20/12/2024, E3
E7 | Reference 2L detector layout |  | E | 0 d | 12/1/2024, E4
E8 | GWINC package for noise budget computation |  | E | 0 d | E2
E9 | Preliminary suspension system classification |  | E | 0 d | E2
E10 | Preliminary tower classification |  | E | 0 d | E2
E11 | Reference ET sensitivity curve |  | E | 0 d | E2
1 | Online meetings
1.1 |  | kick-off meeting | M | 1 d | 18/12/2024 | 100% | Name1: all
1.2 |  | 1st weekly meeting | M | 1 d | 8/1/2025, 1.1 E6, E7 | 0% | Name1: all
1.3 |  | 2nd weekly meeting | M | 1 d | 13/1/2025, 1.2 | 0% | Name1: all
1.4 |  | 3rd weekly meeting | M | 1 d | 20/1/2025, 1.3 | 0% | Name1: all
1.5 |  | 4th weekly meeting | M | 1 d | 27/1/2025, 1.4, 3.3 | 0% | Name1: all
1.6 |  | 5th weekly meeting | M | 1 d | 3/2/2025, 1.5 | 0% | Name1: all
1.7 |  | 6th weekly meeting | M | 1 d | 10/2/2025, 1.6 | 0% | Name1: all
1.8 |  | 7th weekly meeting | M | 1 d | 24/2/2025, 1.7 | 0% | Name1: all
1.9 |  | 8th weekly meeting | M | 1 d | 3/3/2025, 1.8 | 0% | Name1: all
1.10 |  | 9th weekly meeting | M | 1 d | 10/3/2025, 1.9 | 0% | Name1: all
1.11 |  | 10th weekly meeting | M | 1 d | 24/3/2025, 1.10 | 0% | Name1: all
1.12 |  | 11th weekly meeting | M | 1 d | 31/3/2025, 1.11 | 0% | Name1: all
1.13 |  | 12th weekly meeting | M | 1 d | 7/4/2025, 1.13 | 0% | Name1: all
1.14 |  | 13th weekly meeting | M | 1 d | 28/4/2025, 1.14 | 0% | Name1: all
100 |  | preliminary list of configuration concepts | D | 0 d | 1.4 | 0%
110 |  | set of criteria for flexibility evaluation | D | 0 d | 1.5 | 0%
2 | In-person meetings
2.1 |  | 1st in-person meeting | M | 3 d | 17/2/2025, 1.7, 3.4 | 0% | Name1: all
2.2 |  | 2nd in-person meeting | M | 3 d | 17/3/2025, 1.10, 3.5 | 0% | Name1: all
2.3 |  | 3rd in-person meeting | M | 3 d | 14/4/2025, 1.13, 3.8 | 0% | Name1: all
200 |  | 1st set of 2L detector layouts | P | 0 d | 2.1 | 0%
210 |  | 2nd set of 2L detector layouts | P | 0 d | 2.2 | 0%
220 |  | Set of triangle detector layouts | P | 0 d | 2.3 | 0%
3 | Science case
3.1 |  | Science case for baseline triangle layout | S | 2 w | E3, 4.1 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.2 |  | Science case for baseline 2L layout | S | 2 w | E3, 4.2 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.3 |  | Metrics for performance risk evaluation | W | 2 w | E3, 1.3 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.4 |  | Coarse performance risk evaluation for optional 2L optical layouts | S | 1 w | 3.3, 4.3 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.5 |  | Coarse performance risk evaluation for optional technologies and 2L layout | S | 1 w | 3.3, 4.4 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.6 |  | Science case for optional 2L optical layout | S | 3 w | 3.4, 2.1 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.7 |  | Science case for optional technologies and 2L layout | S | 2 w | 3.5. 2.2 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.8 |  | Coarse performance risk evaluation for optional triangle layouts | S | 1 w | 3.3, 4.2 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
3.9 |  | Science case for optional triangle layouts | S | 3 w | 3.8, 2.3 | 0% | Name1: Ulyana Dupletsa; Name2: Francesco Iacovelli; Name3: Archisman Ghosh
300 |  | Performance risk full assessment for 2L | P | 0 d | 3.6, 3.7 | 0%
310 |  | Performance risk full assessment for triangle | P | 0 d | 3.8 | 0%
4 | Noise budget
4.1 |  | Noise budget for baseline triangle layout | S | 1 w | E6, E8 | 0% | Name1: Mikhail Korobko
4.2 |  | Noise budget for baseline 2L layout | S | 1 w | E7, E8 | 0% | Name1: Mikhail Korobko
4.3 |  | Noise budget update with optional 2L optical layout | S | 1 w | E8, 500, 7.1, 6.1, 6.2, 6.3, 6.4 | 0% | Name1: Mikhail Korobko
4.4 |  | Noise budget update with optional technologies and 2L layout | S | 1 w | E8, 510, 7.4, 6.5, 6.6, 6.7, 6.8 | 0% | Name1: Mikhail Korobko
4.5 |  | Noise budget update with optional triangle layout | S | 1 w | E8, 520, 7.1, 6.1, 6.2, 6.3, 6.4 | 0% | Name1: Mikhail Korobko
400 |  | Updated noise budget for 2L | P | 0 d |  | 0%
410 |  | Updated noise budget for triangle | P | 0 d |  | 0%
5 | Optical layout
5.1 |  | Technical requirements on optical layout from instrument technologies | S | 1 w | 2.1 | 0% | Name1: Anna Green; Name2: Antonio Perreca; Name3: Leonardo Lucchesi; Name4: Julien Gargiulo; Name5: Steffen Grohman
5.2 |  | Optical layout system decomposition and scientific requirements derivation | S | 2 w | E3, E4, E8, E11 |  | Name1: Romano Meijer; Name2: Anna Green; Name3: Mikhail Korobko; Name4: Ulyana Dupletsa; Name5: Francesco Iacovelli
5.3 |  | 2L flexibility envelope for arm cavities with baseline technologies | S | 2 wk | 5.1, 5.2, 6.1, 6.2, 6.3, 6.4, 7.1, 8.1, 8.2 | 0% | Name1: Antonio Perreca; Name2: Anna Green; Name3: Jerome Degallaix; Name4: Daniel Brown; Name5: Antonino Chiummo
5.4 |  | 2L flexibility envelope for central interferometer with baseline technologies | S | 2 wk | 5.1, 5.2, 6.1, 6.2, 6.3, 6.4, 7.1, 8.1, 8.2 | 0% | Name1: Julia Casanueva
5.5 |  | 2L flexibility envelope for input mode cleaners with baseline technologies | S | 2 wk | 5.1, 5.2, 6.1, 6.2, 6.3, 6.4, 7.1, 8.1, 8.2 | 0% | Name1: Antonino Chiummo
5.6 |  | 2L flexibility envelope for filter cavities with baseline technologies | S | 2 wk | 5.1, 5.2, 6.1, 6.2, 6.3, 6.4, 7.1, 8.1, 8.2 | 0% | Name1: Marco Vardaro; Name2: Giacomo Ciani
5.7 |  | 2L flexibility envelope for arm cavities with optional technologies | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.3, 8.4 | 0% | Name1: Anna Green; Name2: Antonio Perreca
5.8 |  | 2L flexibility envelope for central interferometer with optional technologies | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.3, 8.4 | 0% | Name1: Julia Casanueva
5.9 |  | 2L flexibility envelope for input mode cleaners with optional technologies | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.3, 8.4 | 0% | Name1: Antonino Chiummo
5.10 |  | 2L flexibility envelope for filter cavities with optional technologies | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.3, 8.4 | 0% | Name1: Marco Vardaro; Name2: Giacomo Ciani
5.11 |  | triangle flexibility envelope for arm cavities | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.5, 8.6 | 0% | Name1: Antonio Perreca; Name2: Anna Green
5.12 |  | triangle flexibility envelope for central interferometer | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.5, 8.6 | 0% | Name1: Julia Casanueva
5.13 |  | triangle flexibility envelope for input mode cleaners | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.5, 8.6 | 0% | Name1: Antonino Chiummo
5.14 |  | triangle flexibility envelope for filter cavities | S | 3 w | 5.1, 5.2, 6.5, 6.6, 6.7, 6.8, 7.4, 8.5, 8.6 | 0% | Name1: Marco Vardaro; Name2: Giacomo Ciani
5.15 |  | Update 2L optical layout with baseline technologies | W | 1 w | 5.3, 5.4, 5.5, 5.6 | 0% | Anna Green | Antonio Perreca | Jerome Degallaix | Julia Casanueva | Antonino Chiummo | Marco Vardaro | Giacomo Ciani | Daniel Brown
5.16 |  | Update 2L optical layout with optional technologies | W | 1 w | 5.7, 5.8, 5.9, 5.10 | 0% | Anna Green | Antonio Perreca | Jerome Degallaix | Julia Casanueva | Antonino Chiummo | Marco Vardaro | Giacomo Ciani | Daniel Brown
5.17 |  | Update triangle optical layout | W | 1 w | 5.11, 5.12, 5.13, 5.14 | 0% | Anna Green | Antonio Perreca | Jerome Degallaix | Julia Casanueva | Antonino Chiummo | Marco Vardaro | Giacomo Ciani | Daniel Brown
500 |  | 2L optical layout with baseline technologies updated | P | 0 d | 5.15 | 0%
510 |  | 2L optical layout with optional technologies updated | P | 0 d | 5.16 | 0%
520 |  | triangle optical layout updated | P | 0 d | 5.17 | 0%
6 | Seismic isolation
6.1 |  | Categorization of suspensions | W | 2 w | 16/01/2025 | 0% | Romano Meijer | Nathan Holland | Francesca Spada | Paolo Ruggi | Leonardo Lucchesi | Conor Mow-Lowry
6.2 |  | Identification of baseline and optional suspension design | S | 3 w | 6.1 | 0% | Name1: Nathan Holland; Name2: Paolo Ruggi; Name3: Leonardo Lucchesi; Name4: Francesca Spada; Name5: Conor Mow-Lowry
6.3 |  | Preliminary assessment of impact of baseline and optional suspension design on science case | S | 2 w | 6.2 | 0% | Paolo Ruggi | Nathan Holland | Francesca Spada | Conor Mow-Lowry | Mikhail Korobko | Ulyana Dupletsa | Francesco Iacovelli
6.4 |  | Update on suspension categories | S | 3 w | 6.1 | 0% | Name1: Nathan Holland; Name2: Paolo Ruggi; Name3: Francesca Spada
6.5 |  | Design of baseline suspension types and identification of geometrical constraints | S | 3 w | 6.2, 6.3 | 0% | Name1: Leonardo Lucchesi; Name2: Conor Mow-Lowry
6.6 |  | Design of optional suspension types and identification of geometrical constraints | S | 3 w | 6.2, 6.3 | 0% | Name1: Nathan Holland; Name2: Paolo Ruggi
6.7 |  | Requirements tree for suspensions | S | 3 w | 6.8 | 0% | Name1: Romano Meijer
6.8 |  | Final assessment of impact of baseline and optional suspension design on science case | S | 3 w | 6.5, 6.6 | 0% | Paolo Ruggi | Nathan Holland | Francesca Spada | Conor Mow-Lowry | Mikhail Korobko | Ulyana Dupletsa | Francesco Iacovelli
600 |  | seismic isolation configurations updated | P | 0 d |  | 0%
7 | Cryogenics
7.1 |  | Requirements tree for cryogenics | S | 2 w |  | 0% | Name1: Fulvio Ricci; Name2: Steffen Grohmann; Name3: Henk Jan Bulten
7.2 |  | LF TM cryostat and payload baseline system decomposition | W | 2 w | 1.4 | 0% | Name1: Fulvio Ricci; Name2: Steffen Grohmann; Name3: Angelo Cruciani; Name4: Piero Rapagnani; Name5: Ettore Majorana
7.3 |  | cryopumps baseline system decomposition | W | 3 w | 1.4 | 0% | Name1: Steffen Grohmann; Name2: Angelo Cruciani; Name3: Julien Gargiulo
7.4 |  | cryogenic infrastructure baseline system decomposition | W | 2 w | 1.4 | 0% | Name1: Steffen Grohmann; Name2: Angelo Cruciani; Name3: Fulvio Ricci
7.5 |  | LF TM cryostat and payload options technology concept | W | 3 w | 1.4 | 0% | Name1: Henk Jan Bulten; Name2: Ettore Majorana; Name3: Steffen Grohmann; Name4: Piero Rapagnani
7.6 |  | cryopumps options technology concept | W | 3 w | 1.4 | 0% | Name1: Henk Jan Bulten; Name2: Angelo Cruciani; Name3: Steffen Grohmann; Name4: Julien Gargiulo
7.7 |  | cryogenic infrastructure options technology concept | W | 3 w | 1.4 | 0% | Name1: Henk Jan Bulten; Name2: Angelo Cruciani; Name3: Fulvio Ricci; Name4: Steffen Grohmann
700 |  | cryogenic system configurations available | P | 0 d |  | 0%
8 | Vacuum
8.1 |  | vacuum pipes and support baseline configuration for 2L | W | 2 w | 1.2 | 0% | Name1: Patrik Werneke; Name2: Antonio Pasqualetti; Name3: Julien Gargiulo; Name4: Maria Marsella
8.2 |  | tower vacuum baseline configuration for 2 L | W | 2 w | 1.2 | 0% | Name1: Julien Gargiulo; Name2: Antonio Pasqualetti; Name3: Ettore Majorana; Name4: Piero Rapagnani
8.3 |  | vacuum pipes and support optional configuration for 2L | W | 3 w | 1.2 | 0% | Name1: Patrik Werneke; Name2: Antonio Pasqualetti; Name3: Julien Gargiulo; Name4: Maria Marsella
8.4 |  | tower vacuum optional configuration for 2 L | W | 3 w | 1.3 | 0% | Name1: Julien Gargiulo; Name2: Antonio Pasqualetti; Name3: Ettore Majorana; Name4: Piero Rapagnani
8.5 |  | vacuum pipes and support configuration for triangle | W | 3 w | 1.3 | 0% | Name1: Patrik Werneke; Name2: Antonio Pasqualetti; Name3: Julien Gargiulo; Name4: Maria Marsella
8.6 |  | tower vacuum configuration for triangle | W | 3 w | 2.2 | 0% | Name1: Julien Gargiulo; Name2: Antonio Pasqualetti; Name3: Ettore Majorana; Name4: Piero Rapagnani
800 |  | Vacuum system configurations updated | P | 0 d |  | 0%
9 | Tower integration
6.1 |  | LF TM tower baseline design | S | 3 w | 6.1, 8.2, 8.5 | 0% | Leonardo Lucchesi | Julien Gargiulo | Angelo Cruciani | Steffen Grohmann | Ettore Majorana | Piero Rapagnani
6.2 |  | HF TM tower baseline design | S | 3 w | 6.2, 8.2, 8.5 | 0% | Name1: Leonardo Lucchesi; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti; Name4: Ettore Majorana; Name5: Piero Rapagnani
6.3 |  | other core optics baseline design | S | 3 w | 6.3, 8.2, 8.5 | 0% | Name1: Leonardo Lucchesi; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti; Name4: Ettore Majorana
6.4 |  | suspended benches baseline design | S | 3 w | 6.4, 8.2, 8.5 | 0% | Name1: Francesca Spada; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti; Name4: Francesca Spada; Name5: Antonino Chiummo
6.5 |  | LF TM optional design | S | 3 w | 6.5, 8.4, 8.5 | 0% | Name1: Nathan Holland; Name2: Julien Gargiulo; Name3: Henk Jan Bulten; Name4: Ettore Majorana; Name5: Piero Rapagnani
6.6 |  | HF TM optional design | S | 3 w | 6.6 | 0% | Name1: Nathan Holland; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti; Name4: Ettore Majorana; Name5: Piero Rapagnani
6.7 |  | other core options optional design | S | 3 w | 6.7 | 0% | Name1: Nathan Holland; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti; Name4: Ettore Majorana; Name5: Piero Rapagnani
6.8 |  | suspended benches optional design | S | 3 w | 6.8 | 0% | Name1: Francesca Spada; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti; Name4: Francesca Spada; Name5: Antonino Chiummo
900 |  | Tower configuration concepts updated | P | 0 d |  | 0%
10 | Technical infrastructure
10.1 |  | technical infrastructure baseline system decomposition for 2L | W | 3 w | 1.2 | 0% | Name1: Patrik Werneke; Name2: Max Majoor; Name3: Steffen Grohmann; Name4: Antonio Pasqualetti; Name5: Julien Gargiulo
10.2 |  | technical infrastructure options technology concept for 2L | W | 3 w | 1.3 | 0% | Patrik Werneke | Max Majoor | Henk Jan Bulten | Angelo Cruciani | Julien Gargiulo | Antonio Pasqualetti
10.3 |  | technical infrastructure for triangle | W | 3 w | 2.2 | 0% | Patrik Werneke | Max Majoor | Steffen Grohmann | Angelo Cruciani | Julien Gargiulo | Antonio Pasqualetti
1000 |  | Technical infrastructure configurations updated | P | 0 d |  | 0%
11 | Detector layout
11.1 |  | preliminary brainstorming | W | 3 w | E6, E7, 1.1 | 0% | Name1: all
11.2 |  | review of criteria | W | 1 w | 11.1, 1.4 | 0% | Name1: Max Majoor; Name2: Patrik Werneke
11.3 |  | 2L detector layout update for baseline technologies | S | 1 w | 10.1, 11.2, 5.2, 5.3, 5.4, 5.5 | 0% | Name1: Max Majoor; Name2: Patrik Werneke
11.4 |  | 2L detector layout update for optional technologies | S | 1 w | 10.2, 11.2, 5.6, 5.7, 5.8, 5.9 | 0% | Name1: Max Majoor; Name2: Patrik Werneke
11.5 |  | triangle detector layout update | S | 1 w | 10.3, 11.2, 5.11, 5.11, 5.12, 5.13, 6.5, 6.6, 6.7, 6.8 | 0% | Name1: Max Majoor; Name2: Patrik Werneke
1100 |  | 2L detector layout | D | 0 d |  | 0%
1110 |  | triangle detector layout | D | 0 d |  | 0%
12 | Civil infrastructure
12.1 |  | criteria and tools for civil infrastructure layout | W | 2 w | 1.2 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Max Majoor
12.2 |  | criteria and tools for civil infrastructure costing | W | 2 w | 12.2 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.3 |  | 2L baseline civil infrastructure | S | 1 w | E7, 12.1 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.4 |  | identification of most critical elements for costing in baseline 2L layout | S | 1 w | 12.2, 12.3 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.5 |  | civil infrastructure for updated 2L detector layout with baseline technologies | S | 3 w | 11.3, 12.1 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.6 |  | cost breakdown for updated 2L detector layout with baseline technologies | S | 1 w | 12.2, 12.5 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.7 |  | criteria update | W | 3 w | 12.1, 12.2, 2.1 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.8 |  | identification of most critical elements for costing in optional 2L detector layout | S | 1 w | 11.4, 12.2 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.9 |  | civil infrastructure for updated triangle detector layout with optional technologies | S | 3 w | 11.5, 12.1 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
12.1 0 |  | cost breakdown for updated triangle detector layout with optional technologies | S | 1 w | 12.2, 12.9 | 0% | Name1: Jonathan Bratanata; Name2: Wissam Wahbeh; Name3: Maria Marsella
1200 |  | summary of 2L civil infrastructure | D | 0 d |  | 0%
1210 |  | summary of triangle civil infrastructure | D | 0 d |  | 0%
13 | Risk analysis
13.1 |  | Risk management plan and tools | W | 1 w | 1.1 | 20% | Name1: Ghada Mahmoud
13.2 |  | Risk assessment and evaluation for baseline seismic isolation | M | 3 w | 6.1, 6.2, 6.3, 6.4, 13.1 | 0% | Name1: Ghada Mahmoud; Name2: Leonardo Lucchesi; Name3: Paolo Ruggi
13.3 |  | Risk assessment and evaluation for optional seismic isolation | M | 3 w | 6.5, 6.6, 6.7, 6.8, 13.1 | 0% | Name1: Ghada Mahmoud; Name2: Nathan Holland; Name3: Conor Mow-Lowry
13.4 |  | Risk assessment and evaluation for baseline cryogenics | W | 3 w | 7.1, 7.2, 7.3, 13.1 | 0% | Name1: Ghada Mahmoud; Name2: Angelo Cruciani; Name3: Steffen Grohman; Name4: Piero Rapagnani
13.5 |  | Risk assessment and evaluation for optional cryogenics | W | 3 w | 7.4, 7.5, 7.6, 13.1 | 0% | Name1: Ghada Mahmoud; Name2: Henk Jan Bulten; Name3: Ettore Majorana
13.6 |  | Risk assessment and evaluation for baseline vacuum system | W | 3 w | 8.1, 8.2, 13.1 | 0% | Name1: Ghada Mahmoud; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti
13.7 |  | Risk assessment and evaluation for optional vacuum system | W | 3 w | 8.3, 8.4, 13.1 | 0% | Name1: Ghada Mahmoud; Name2: Julien Gargiulo; Name3: Antonio Pasqualetti
13.8 |  | Risk assessment and evaluation for 2L optical layouts | W | 3 w | 5.6, 5.7, 5.8, 5.9, 13.1 | 0% | Ghada Mahmoud | Anna Green | Antonio Perreca | Antonino Chiummo | Jerome Degallaix | Daniel Brown | Julia Casanueva
13.9 |  | Risk assessment and evaluation for triangle optical layouts | W | 3 w | 5.10, 5.11, 5.12, 5.13, 13.1 | 0% | Ghada Mahmoud | Anna Green | Antonio Perreca | Antonino Chiummo | Jerome Degallaix | Daniel Brown | Julia Casanueva
1300 |  | Risk analysis report | D | 0 d |  | 0%
Note on A2: Give a number for the task/subtask for referencing in "predecessor"; use a dot for creating subtask numbers: 1, 1.1, 1.2 … 2, 2.1, 2.1.1, …. Use D1,D2,… for external dependencies.
Note on B2: Name of task (=level 2 of WBS)
Note on C2: Name of Subtask (=level 3 or more of WBS)
Note on D2: Type of task. Empty = normal task S = modeling or simulation W = writing M = meeting P = project milestone (duration 0) D = deliverable (duration 0) E = external dependency (duration 0)
Note on E2: Duration in days, weeks or months Possible abbreviations: d = day(s) wk = week(s) mon = month(s) 1 week = 5 working days 1 month = 20 working days (because of holidays)
Note on F2: Enter the number of the predecessor task(s) or subtask(s). If no predecessor, enter the earliest starting date. Both are possible. Separate with commas (,).
Note on G2: Indicate which percentage of the task is done. Cannot be 0% the task has started already. Must be 100% if the task is finished. Otherwise modify earliest starting date or duration.

## Sheet2
Anna Green
Antonio Perreca
Jerome Degallaix
Daniel Brown
Marco Vardaro
Giacomo Ciani
Julia Casanueva
Nathan Holland
Leonardo Lucchesi
Antonino Chiummo
Francesca Spada
Sebastian Steinlechner
Paolo Ruggi
Conor Mow-Lowry
Julien Gargiulo
Antonio Pasqualetti
Henk Jan Bulten
Steffen Grohmann
Fulvio Ricci
Ettore Majorana
Piero Rapagnani
Angelo Cruciani
Jonathan Bratanata
Wissam Wahbeh
Maria Marsella
Max Majoor
Patrik Werneke
Mikhail Korobko
Elena Licciardello
Romano Meijer
Ghada Mahmoud
Andreas Freise
Riccardo de Salvo
Marco Galimberti
Lucia Lilli
Benoit Tuybens
Fiodor Sorrentino
TBD
Ulyana Dupletsa
Francesco Iacovelli
Archisman Ghosh
all