## Slide 1: Solenoids Report
Andy Hocker
Mu2e Level 2 Manager for Solenoids
June 13, 2025

## Slide 2: Mu2e Solenoid Project Scope
DS
PS
TSu
TSd
Production Solenoid (PS)
Transport Solenoid (TSu,TSd)
Detector Solenoid (DS)
Cryogenic Distribution
Quench Protection/Slow Monitoring
Power Supplies
Field Mapping
Ancillary Equipment
Installation/Commissioning
DONE
DONE
DONE
DONE

## Slide 3: Production Solenoid

## Slide 4: Production Solenoid (PS)
Completed studies of leak in inner thermal shield nitrogen circuit
DocDB 52243 (and following slides)
Since last collaboration meeting
Authorized vendor to ship
Delivery date TBD
Reviewed our conclusions with an external panel of SMEs
Concurred that getting the PS here ASAP was the best course of action

## Slide 5: Anatomy of the PS
Inner bore and inner thermal shield
PS1
PS2
PS3
Cold mass
Outer thermal shield
Muon Beamline vacuum space
Insulating vacuum space

## Slide 6: PS leak conclusions
Had vendor measure leak rate three different ways, all resulted in an expected nitrogen accumulation of a few tens of grams per year
Independent calculations by vendor agreed with ours
This nitrogen will likely freeze out on nearby 4.5 K surfaces (aka cryopumping)
  An accumulation of a 50 micron thick layer over 1 m2 in a year, negligible effect on heat load
Released as ~1.5 ft3 of gas and easily pumped out during annual PS warm-ups
  This is how g-2 dealt with a similar (but 6x larger) leak --- warmed up every three months
Bottom line: this is a manageable leak.

## Slide 7: But what if it gets worse
How much worse? Assuming no help from cryopumping, leak starts to overwhelm vacuum pumps when 100-150x larger
Vendor thermal-cycled the inner thermal shield 5 times, saw no evidence of the leak getting worse
Mitigations we can pursue if needed:
  More frequent mini-warm-ups (like g-2): costs a couple days of data-taking, coordinate with other sources of down-time
  Reduce the nitrogen operating pressure (and hence leak rate)
The failsafe: turn off flow to the inner thermal shield completely
  We require the coil to run 1.5 K less than quench temperature (“thermal margin”)
  No shield -> coil runs hotter -> eats margin -> need to reduce current by 10% to recover margin
  10% less current = 10% less field = 10% less muons
  Complication: the transfer line uses this N2 flow too. Currently working this problem
R. Coleman, DocDB 652

## Slide 8: PS shipping
Leave vendor in morning
Arrive FNAL next morning to allow plenty of time for unloading
Dummy test last year validated rigging and isolation scheme
See SEP-2024 collab meeting report (DocDB 50536)

## Slide 9: Shipping route
Chase car 1: FNAL
Chase car 2: Vendor engineer
To Mu2e

## Slide 10: PS incoming inspection
Verify vessel, LHe circuit, outer thermal shield circuit leak-tight
Check that inner thermal shield circuit leak not worse
Electrical checks including hi-pot
Prep for moving downstairs

## Slide 11: Detector Solenoid
02

## Slide 12: DS progress (1)
Inner bore/thermal shield inserted into cold mass
Laser survey of cold mass: total length (~10 m) within 0.1 mm of design value

## Slide 13: DS progress (2)
“Global” leak check performed on outer thermal shield
  Evacuate pipes, flood volume with helium and look for helium in pipes
  Supplements targeted leak checks of individual welds

## Slide 14: DS progress (3)
Laser survey showed LHe manifolds stick out too far
LHe manifold
Modify inner thermal shield LN2 transport tubes in chimney region to clear manifolds
This was not easy

## Slide 15: Current state of DS
Cold mass/vacuum vessel insertion “dry run” (no MLI)
Can jockey vessel around to temporarily clear features as the insertion progresses
Reached a limitation at about the halfway point
  Will need to shave a few mm from corner of a siphon tube elbow
  Could introduce a leak but it would be repairable
These are the things that cause schedule slips
Cold mass
Outer thermal shield

## Slide 16: Transport Solenoid
03

## Slide 17: TS status
Currently all about the TSu/TSd interconnect region

## Slide 18: Antiproton window housing issue
When welding the interconnect shells to the AP window housing, the diameter of the housing shrank and bowed out in the middle
  COL3d ring gear can’t rotate
  AP window blade (divides US/DS muon beamline vacuum) can’t fit in its slot
New brace system created to fix this
  Thanks to Greg Rakness and Jeff Brandt for the following slides
Slot for blade

## Slide 19: Brace system parts

## Slide 20: Expand the housing diameter

## Slide 21: Lock in

## Slide 22: Cool off

## Slide 23: It’s working
You’ll either have to trust me, or do some zooming and panning of these images offline
housing
Tsu gear
TSd gear
No braces: housing disappears behind TSd gear
With braces: housing clears TSd gear
Rotated COL3d about 1/3, felt resistance, work a little more on straightness

## Slide 24: Infrastructure etc.
04

## Slide 25: Cryogenic distribution
TSu and TSd cryogenic interconnects are done (magnet-to-transfer line)
Each contains
  2x2 LN2 pipes (inner/outer thermal shield, sup/ret)
  2x2 LHe pipes (cold mass and bus cooling, sup/ret)
  2x2 superconducting leads (main and trim, +/-)
Vacuum instrumentation lines also installed
  Glorified conduit for monitoring instrumentation wires (temperatures, strain gauges, etc.)
  Wires not yet pulled

## Slide 26: Insulating vacuum pumping line installation
The last piece of TS-specific cryo infrastructure
Preliminary system leak-checking to follow
TSd
TSu

## Slide 27: Power supply systems highlights (1)
Dump resistors installed at Mu2e
TSu
TSd
DS
PS

## Slide 28: Power supply systems highlights (2)
Two pairs of 20 V, 1000 A Ametek power supplies donated by g-2
Original plan for repurposed Tevatron electron lens supplies abandoned due to attrition of expertise
About one month away from being technically ready to run power to a shorted bus
TS main supply racks complete
front
back

## Slide 29: Quench protection system integration
Cabling between QP system and v-tap trees done
Cables pulled from QP system to power supply controls racks
Next: signal injection and simulated quench testing

## Slide 30: Schedule considerations
One driver of TS cooldown date is that it must be connected to PS/DS while warm
  So it waits for PS/DS to be installed and aligned
We could advance the TS by 5-6 months at the cost of a thermal cycle
  Cool down TS
  Commission TS
  Warm up
  Connect to PS/DS when ready
  Cool back down
The prospect of debugging cryo operations early is extremely attractive
Project baseline as of end-May
 | TSu | TSd | PS | DS | All
Deliver | Delivered | Delivered | 1-AUG-2025 | 15-JAN-2026 | 
Cooldown | MAY-2026 | JUN-2026 | OCT-2026 | JAN-2027 | 
Energize | JUN-JUL-2026 | JUL-2026 | NOV-2026 | FEB-2027 | MAR-2027

## Slide 31: Operations
Active areas of effort
  Re-starting the MC-1 refrigerator (new full-flow purifier)
  Establishing magnetic field hazard mitigations and controls
  Further development of field mapping system (see talk by Dittmer, this session)
  Finalizing design of field monitoring system (see talk by Kawall, FMS session Tuesday)

## Slide 32: Summary
Vendor is ready to ship PS, and we’re ready to receive it
  However there remains some contractual wrangling related to the leak
All 3 top-level components of the DS are done
  Inner bore and cold mass are integrated
  Outer vessel integration in process
Technical challenges continue to delay DS delivery
  Current project end date includes float to the DS delivery, that float is down to 2.5 months
Several important campaigns have completed
  Installation of the AP window housing restraint system
  TS cryogenic interconnects
  Remediation and installation of the dump resistors
Looking forward to installing two more magnets and commissioning!