## Slide 1: Concluding remarks
E. Migneco
KM3NeT general meeting, Catania, february 23 2012

## Slide 2: The (near)-future of KM3NeT
This is not a summary of the summaries
  A complete and exhaustive overview of the status of the activities has been given yesterday and today by the WP coordinators
Not a long range programme on the full KM3NeT
  Leave this to the future management
Just concentrates on a few hot topics relevant for the near future of KM3NeT
  Development plan (from the presentations of E. de Wolf and E. Heine)
  MoU (from the presentation of P. Coyle)
Boundary conditions: recommendations from SSC and ASC

## Slide 3: Technology development plan
The validation of KM3NeT components, started within the Preparatory Phase, will extend beyond the end of the PP
Factorized and staged in order to get the important answers as soon as possible
TDR for the main components to start pre-ordering
Answer to the technical recommendation of the SSC

## Slide 4: PPM test programme (timeline and responsibilities)
‘mini-DOM’ in ANTARES
  Singles rate and coincidence measurements with 3” PMTs
‘full’ DOM in ANTARES
  Long term benchmark of the optical module
  Test of KM3NeT readout electronics
DU mechanical tests in shallow waters
  Test of the design and integration of the detection unit (DU)
  Test of deployment method
Deployment of mechanical tower in deep waters
  Test of reliability of backbone and DOM penetrators
Deployment and connection of ‘mini-tower’
  Test of KM3NeT fibre optics and data transmission network
  Test of detector operation
DOM validated
DU structure and deployment valid.
Responsibility Nikhef/CPPM
Responsibility INFN (design) / CPPM (sea op.)
Responsibility INFN
Responsibility INFN
Jun 2012
Aug 2012
Oct 2012
Dec 2012

## Slide 5
Development plan for DOM and DU mechanics on track
Two major items are on the critical path of the project
  Electronics
  Backbone
Need to take soon decisions on how to proceed
Need to clearly define the decision process to get to the procurement phase
My personal impression is that the situation is rather delicate and has to be handled carefully to avoid it to evolve in a direction different from the one we have in mind

## Slide 6
Agreement on an MOU to define the Collaboration organisation and commitments for the future
Agreement to proceed towards an ERIC
Anticipates recommendation from SSC

## Slide 7: MoU (a work in progress)
Presented this morning by Paschal Coyle on behalf of WPC
MOU drafting committee:
P. Coyle, E. de Wolf, P. Piattelli, I.Siotis (E. Migneco)
Scope:
How to organise ourselves to spend coherently and efficiently
the funds currently available i.e. does not go beyond the 40 M€
(but clearly there is the intention to do so the a future)
Signed by:
at a first step- the institutes involved in the project
at a second step (ERIC) the ministries/funding agencies
Commitments:
funds, deliverables

## Slide 8: MoU- Milestones
Two stages:
  Preparation (2012-2013)
    Simulations  detector geometry  Review
    Evaluation PPM PM description  Technical Proposal  Review
    Seafloor networks at C-P and Toulon available
    2DUs connected  production readiness review
  Construction (2014-2015)
    27 DUs in C-P
    2 DUs in Toulon
    9 to increase science performance for Gal. Sources
    More DUs if costs reductions realised or additional funding forthcoming
Date | TDR
3Q2012 | Optical module
 | Detection unit mechanics
 | Calibration system
4Q2012 | Backbone cable system
 | Readout/DAQ system
 | Shore station infrastructure
?? | Seafloor network system
Staged Technical Proposals

## Slide 9
Science and Technology Advisory Committee
QA/QC Manager
Physics Coordinator
(elected)
Technical coordinator
(elected)
Earth & Sea
Sciences
(appointed)
Logistics
Manager
(appointed)
Install. Site
Managers
(appointed)
Deputy spokesperson
(elected)
Spokesperson (chair)
(elected)
Institute Board (chair elected)
Executive Management Team
Coordinators of Software and Physics activities
Publication Committee
Conference and Outreach Committee
Safety Manager
Resource Manager
Coordinators DOM assembly sites
Coordinators DU integration sites
Coordinator readout/DAQ
Technical Steering Committee
Physics and Software Steering Committee
Management local infrastructures
Local shore station
Local seafloor network
Local sea operations
Coordinators R&D projects
International Resource Board
Local Seabed Infrastructure coordinators

## Slide 10: Management Elections
Search committee nominated:
P. Coyle, E. de Wolf, I Siotis, M. Taiuti
Define the members of the IB which vote
Define the election rules
Consult with the Collaboration, encourage candidates to put themselves forward
Date for candidates to be declared - 1st April
Date of the election - 15th April

## Slide 11: Conclusions
These have been very interesting days
The conditions to proceed in a effective way are there (fundings, technology, …)
Some critical aspects are present and the solutions are not clear at the moment and have to be cleared before the installation of the new management