## Slide 1
1
EuAPS, Status update.
CLAUDIO BORTOLIN (INFN-LNF)
EuAPS 1st Annual Meeting LNS 4/5 June 2025

## Slide 2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
The technical team (12+9 FTE)
INFN-Mi 2 Fixed term contracts +2 FTE
CNR-INO 2 Fixed Term Contracts +1FTE
CNR-ISM 2 Fixed Term Contracts +1FTE
INFN-LNS 2 Fixed term contracts +0,5 FTE
INFN-LNF 3 Fixed term contracts +3,5 FTE
UniToV 1 Fixed term contract +1 FTE
63%
37%
2

## Slide 3
INFN-LNF ->Tiziano Ferro (FO), Sara Silvi, Marco Traini
EuAPS 1st Annual Meeting LNS 4/5 June 2025
The Administrative/Financial team
CNR -> Chiara Mustarelli, Paola Bolognesi
UniToV -> Alice Aldi
3
…and numerous calls, Teams meetings, and training sessions with the PMO and AC (V. Valsecchi, U. Dosselli, S. Bartocci)

## Slide 4
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
5
PNRR documentation preparation and tracking
Expert-led video sessions

## Slide 5
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
4
PNRR documentation and audits
INFN has implemented a tagging system for purchase documentation

## Slide 6
EuAPS 1st Annual Meeting LNS 4/5 June 2025
EuAPS: 3 facilities (LNF, LNS, CNR Pisa), 4WPs, 46 IO
Tot. 22,3 MEur
7

## Slide 7
Bim1
Bim2
Bim3
Bim4
Bim5
Bim6
Bim7
Bim8
Bim9
Bim10
Bim11
Bim12
Bim13
Bim14
Bim15
+
Bim16
Bim17
Bim18
EuAPS 1st Annual Meeting LNS 4/5 June 2025
The ambitious plan
Proposed timeline (30+6 months)
Design
Procurement
Installation
Commissioning
Test report
Budget
Project completion
6

## Slide 8
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
Some “Relativistic” effects in contracts signatures…
Dec 22
Dec 23
Dec 24
Today
Tomorrow
8
Design + component selection
+tender processes
13 months
Controls, document requests
10 months
Delivery, installation, commissioning, tests
13 months

## Slide 9
EuAPS 1st Annual Meeting LNS 4/5 June 2025
…even harder than my previous experiences…
20

## Slide 10
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
PNRR reporting process
Dec 22
Dec 23
Dec 24
Today
Tomorrow
9

## Slide 11
2
WPs Activities&IO status
EuAPS 1st Annual Meeting LNS 4/5 June 2025
10
Bimester 15 was closed on 31st May
See presentations by A. Falone (WP1) and A. Cianchi (WP2)

## Slide 12
2
WPs Activities&IO status
EuAPS 1st Annual Meeting LNS 4/5 June 2025
11
See presentations by P. Cirrone (WP3) and L. Labate (WP4)

## Slide 13
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
Reporting on GEA (MUR platform)
New feature
12

## Slide 14
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
13
Reporting activities advancement (on schedule)

## Slide 15
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
14
Financial reporting (on schedule)
Details on committed budget and expenses in next talk (S. Silvi)

## Slide 16
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
15
Procedures reporting -> 87% closed
83 procedures closed
11 in the finalization phase (mostly recent orders)

## Slide 17
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
16
Variation requests: preparing the next one
Approval process involves ETS (Pantaleo Raimondi) + MUR experts

## Slide 18
2
Bimester 16 just started, fewer than 6 months until the deadline
EuAPS 1st Annual Meeting LNS 4/5 June 2025
17
Personnel contracts extension to 30/11 are ongoing (but then?)
Intense schedule of activities for all WPs
Significant number of stakeholders to be coordinated (see talk of A. Falone)
Laser systems production timeline very tight with risks of delays

## Slide 19
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
18
The mid- to long-term perspective of EuAPS is not as follows…
…the facilities must run for 10 years (at least) after project completion.

## Slide 20
2
EuAPS 1st Annual Meeting LNS 4/5 June 2025
19
KPI and sustainability
Some preliminary numbers provided to
INFN Management
Discussions with MUR for the operation financial support will take place

## Slide 21
EuAPS 1st Annual Meeting LNS 4/5 June 2025
EuAPS looks a complicated journey but..
20
... to succeed, we also need less “them” and more “us,” because in the end, there is only us.
Thank you!