## Riassunto Economico
Progetto | 2025 |  |  | 2026 |  |  | 2027 | 2028 | 2029 | Contributi esterni fino al 2025 incluso
| FTE | Consumi [keur] | Missioni [keur] | FTE | Consumi [keur] | Missioni [keur] | Consumi [keur] | Consumi [keur] | Consumi [keur]
CryDBDCal | 2 | 0 | 0 | 2 | 55 | 0 | 50 | 20 | 20 | PRIN 3dSpark
MPGD_HCAL | 2.9 | 20.5 | 27 | 2.9 | 55 | 20 | 25 | 25 | 25 | PRIN Calorinho
SpaCal | [6 empty] | 20 | 20 | 20
MAXICC | 4.3 | 33 | 21 | 4.8 | 30 | 26 | 20 | 20 | 20 | Prin Maxicc
ScintCal | 0.3 | 0 | 0 | 0.8 | 5 | 3 | 10 | 10 | 10
DRDCAL | 5.9 | 33 | 41 | 5.9 | 35 | 41 | 20 | 20 | 20 | Call gr5 HIDRA2
CRILIN | 5 | 15.5 | 26 | 6.5 | 50 | 42 | 20 | 20 | 20 | PRIN Calorinho
OREO | 5.7 | 4.5 | 36 | 5.7 | 60 | 39 | 20 | 20 | 20
| FTE | Consumi [keur] | Missioni [keur] | FTE | Consumi [keur] | Missioni [keur] | Consumi [keur] | Consumi [keur] | Consumi [keur]
Gran Totale | 26.1 | 106.5 | 151 | 28.6 | 290 | 171 | 185 | 155 | 155

## Deliverables and Milestones
Start And End Date, Milestones and Deliverables and Time Scale
Task 1.3: Hadronic section with gaseous readout
D Number | M Number | Title | Description | Start date | End date
D1.13 |  |  | Completion of 8-layer 20x20 cm^2 prototype with a total interaction length of 1.2 𝛌 | 2023 | 2024
| M1.14 |  | Specifications for 50x50 cm^2 prototype | 2024 | 2025
D1.14 |  |  | Completion of 12-layer prototype (8L 20x20 cm^2 + 4L 50x50 cm^2) | 2025 | 2026
| M1.15 |  | Design of 50x100 cm^2 layers | 2026 | 2027
| M1.16 |  | Production of 50x100cm^2 layers to be included in the prototype | 2028 | 2028
| M1.17 |  | Design of 100x100cm^2 layer | 2030 | 2030
D1.15 |  |  | Production of 2 100x100 cm^2 layers to be included in the prototype | 2030 | 2031
Task 3.1: Homogeneous and quasi-homogeneous EM calorimeters
MAXICC
D Number | M Number | Title | Description | Start date | End date
| M3.5 |  | Completion of qualification tests on components and selection of crystal, filter and SiPM candidates for prototype | 2024 | 2025
| M3.6 |  | Report on the characterisation of crystal, SiPM and optical filter candidates and their combined performance for Cherenkov readout | 2024 | 2025
D3.3 |  |  | Full containment dual-readout crystal EM calorimeter prototype and testbeam characterisation | 2025 | 2026
| M3.7 |  | Joint testbeam of EM module prototype with dual-readout fibre calorimeter prototype (DRCAL) |  | >2026
CRILIN
D Number | M Number | Title | Description | Start date | End date
D3.4 |  |  | Acquisition and tests of crystals and SiPMs; design and production of electronics boards; design and production of the mechanical components | 2024 | 2025
D3.5 |  |  | Calorimeter fully assembled | 2025 | 2025
| M3.8 |  | Beam test characterisation of a full containment EM calorimeter prototype |  | 2026
| M3.9 |  | Report on testbeam results | 2025 | 2026
OREO
D Number | M Number | Title | Description | Start date | End date
D3.18 |  |  | Two layer PWO-UF prototype fully assembled | 2024 | 2024
| M3.22 |  | First experimental tests at CERN PS&SPS and data analysis | 2024 | 2024
| M3.23 |  | Report on beam test results | 2024 | 2025
| M3.24 |  | Report on MC simulation of the first prototype in Geant4 | 2024 | 2025
D3.19 |  |  | Final MC package in Geant4 | 2024 | 2026
| M3.25 |  | Implementation of the OREO technology in realistic experimental scenarios | 2025 | 2026
Task 3.2: Innovative Sampling EM calorimeters
SpaCal
D Number | M Number | Title | Description | Start date | End date
D3.7 |  |  | Tungsten and lead absorbers for module-size prototypes | 2024 | 2024
| M3.11 |  | Design of optimised light guides | 2024 | 2025
D3.8 |  |  | Set of crystal samples, SPIDER ASIC prototype | 2024 | 2026
| M3.12 |  | Specification of photon detector and improved simulation framework available | 2024 | 2026
D3.9 |  |  | Module-size prototypes (significantly larger than EM showers) built and validated in beam tests | 2024 | >2026
DRCal
D Number | M Number | Title | Description | Start date | End date
D3.12 |  | Full scale prototype | Construction of fullscale dual-readout module with hadronic shower cointainment | 2021 | 2025
| M3.15 | Testbeam campaign | Testbeam campaign to assess module performance: result paper | 2024 | 2026
| M3.16 | Testbeam campaign | Continue beam testing with alternative readout elx | 2026 | 2029
Task 3.4: Materials
ScintCal
D Number | M Number | Title | Description | Start date | End date
| M3.19 |  | Dataset of scintillation and radiation hardness properties of various scintillation materials studied | 2024 | 2026
D3.15 |  |  | Samples of a set of scintillators produced and characterised | 2025 | 2026
D3.16 |  |  | Samples of most promising glasses produced and characterised |  | >2026
| M3.20 |  | Material selected for future detectors |  | >2029
CryoDBD Cal
D Number | M Number | Title | Description | Start date | End date
| M3.21 |  | Report crystals in terms of optimisation of growing/doping procedures | 2024 | 2024
D3.17 |  |  | Scintillating polymer for 3D-printing, with optimal mechanical and light-production properties, produced and tested | 2024 | 2025

## CryoDBDCal
Referente | Matteo Biassoni - INFN MIB |  |  | Matteo Biassoni - INFN MIB
| 2025 |  |  | 2026 |  |  | Note
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | - su commissione 2. Spaccato della cifra per sezione piuttosto difficile. Metterei tutto su Bicocca
GSSI
INFN and Uni MIB | 2 | 0 | 0 | 2 | 55 | 0
INFN-RM1
LNGS
LNL
Totale | 2 | 0 | 0 | 2 | 55 | 0

## MPGD_HCAL
Referente | Luigi Longo - INFN Bari |  |  | Luigi Longo - INFN Bari
| 2025 |  |  | 2026 |  |  | Note
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | - missioni per test beam a PS e SPS (sia per il 2025 che il 2026) - consumi piu' inventariabili 2026 per nuovo catodo per avere una drift gap quanto piu' sottile possibile ed il costo della nuova elettronica per leggere le 8 camere 20x20cm2
INFN and Uni Bari | 2.9 | 20.5 | 27 | 2.9 | 55 | 20
...
Totale | 2.9 | 20.5 | 27 | 2.9 | 55 | 20
>2027
150

## SpaCal
Referente | Marco Pizzichemi - INFN MIB |  |  | Marco Pizzichemi - INFN MIB
| 2025 |  |  | 2026 |  |  | Note
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | SpaCal è inserito nell'Upgrade del calorimetro di LHCb. Richieste all'INFN per il 2025 (così come per il 2026) sono come core money nella sigla per acquistare componenti del calorimetro stesso.
INFN and Uni MIB

## MAXICC
Referente | Marco Lucchini - INFN MIB |  |  | Marco Lucchini - INFN MIB
| 2025 |  |  | 2026
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur]
INFN and UNI MIB | 0.4 | 3.5 | 0.5 + 2.5 (SJ) | 0.4 | 2 | 3
INFN-NA | 3.6 | 16 (SJ) | 14+ 4 (SJ) | 3.6 | 24 | 14+ 4 (SJ)
INFN-PG | 0.3 | 13.5 | 0 | 0.8 | 4 | 5
Totale | 4.3 | 33 | 21 | 4.8 | 30 | 26

## ScintCal
Referente | Claudia Cecchi - INFN Perugia |  |  | Claudia Cecchi - INFN Perugia
| 2025 |  |  | 2026 |  |  | Note
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | - campioni di BGSO e GAGG per capire come questi cristalli possano essere eventualmente compatibili con calorimetria dual readout. - missioni per viaggio verso ditte produttrici + misure enea casaccia
INFN and Uni MIB
UNIVPM
INFN-PG | 0.3 |  |  | 0.8 | 5 | 3
Totale | 0.3 |  |  | 0.8 | 5 | 3
> 2027
30

## DRCal
Referente | Romualdo Santoro - INFN Mi | [5 empty] | Romualdo Santoro - INFN Mi
| 2025 | [5 empty] | 2026
| HiDRa 2025 (GR5) |  |  | RD_FCC 2025 -> DRCal
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur]
INFN-BO | 0.5 | 10 | 2 (SJ) | 0.8 | 2.5 | 8 (SJ) |  | spare pcb (2k)
INFN CT | 0.6 |  | 4 |  |  | 2 (SJ) |  | tecniche alternative per inserimento fibre in tubetti (10k)
INFN-MI + Uni Insubria | 1 |  | 2 (SJ) | 0.3 | 7.5 | 6(SJ) |  | Radioroc (timing 2 boards): 14k + sistema raffreddamento readout: 2k
INFN-PI | 0.2 |  | 4 (SJ) |  |  | 1(SJ) |  | sistema di calibrazione e monitoraggio dei guadagni (5k)
INFN-PV | 1.4 | 10 | 6 (SJ) | 1 | 3 (SJ) | 6(SJ) |  | trigger board (2k)
INFN-RM1 | 0.1
TIFP
Sub-totale | 3.8 | 20 | 18 | 2.1 | 13 | 23
Totale | 5.9 | 33 | 41 |  |  |  | 5.9 | 35 | 41
>2027
270

## CRILIN
Referente | Ivano Sarra - INFN LNF |  |  | Ivano Sarra - INFN LNF
| 2025 |  |  | 2026
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur]
INFN-LNF | 2.2 | 3+ 10 (SJ) | 10 (SJ) | 3 | 40 | 20
INFN-PD | 1.2 | 2.5 (SJ) | 6 | 1.5 | 10 | 10
INFN-TO | 1 |  | 10 (SJ) | 1 |  | 10
INFN-TS | 0.6 |  |  | 0.6
INFN-FI |  |  |  | 0.4 |  | 2
Totale | 5 | 15.5 | 26 | 6.5 | 50 | 42

## OREO
Referente | Laura Bandiera - INFN Ferrara |  |  | Laura Bandiera - INFN Ferrara
| 2025 |  |  | 2026 |  |  | Note
| FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | FTE | Consumo + inventariabile [KEur] | Missioni [kEur] | - missioni per 2 settimane di test beam a SPS (sia per il 2025 che il 2026) - 60 keuro nel 2026 for large prototype and automatization of alignment
INFN-FE | 1.6 | 4.5 | 16 | 1.6 | 60 | 16
INFN-MI + Uni Insubria | 2.1 |  | 12 | 2.1 |  | 12
INFN-LNL | 2 |  | 8 | 2 |  | 8
INFN-LNF | [5 empty] | 3
Totale | 5.7 | 4.5 | 36 | 5.7 | 60 | 39