## Slide 1
News
News from the ET management meeting. Set up a WorkPlan. In our perspective:
Discussion on a system oriented TDR
Risk report
Cost estimate (preliminary, PBS based)
For this
New slot for the meeting: MONDAY MORNING @10.00h. Start next Monday
For presentations templates are available in TEAMS: go to the ET_ALL team, then go to files / Documents / Logos and Templates
Meeting with directors in Rome is cancelled. It will be held remotely during one Monday slots.

## Slide 2: ET-PP document validated (the PO structure) https://edms.cern.ch/document/3161421/4. The Operative PO is submitted (same link). For this we set up a preliminary internal delivery plan (see next slide). This is not graved on stone…but should indicate the way
Deliverable | Expected Result/Outcome | Date | Deliverable - Milestone
ET Roadmap - document | Document describing the roadmap of the ET project in Phase 1 | Q1 2025 | Deliverable
ET Roadmap Methodology - document | Document describing the methodology followed to establish the ET roadmap | Q1 2025 | Deliverable
ET Nomenclature - document | Document describing the project nomenclature | Q3 2025 | Deliverable
ET PBS update provided | ET PO coordinate the establishment of the new PBS version after the review phase | Q4 2025 | MIlestone
ET WBS validated | The final version of the WBS, and consequently of the project OBS is approves by the stakeholders. | Q4 2025 | MIlestone
ET Change process validated | The procedure for the generic change request for PBS and parameters in the | Q4 2025 | MIlestone
ET scheduling Management Plan - document | Document describing the procedures, the methodologies and the roles associated to the scheduling management in ET | Q2 2026 | Deliverable
Risk management plan - document | Document describing the procedures, the methodologies and the roles associated to the risk management in ET | Q2 2026 | Deliverable
Requirements Management plan - document | Document describing the procedures, the methodologies and the roles associated to the requirement management in ET | Q2 2026 | Deliverable
Quality Assurance Plan – document | Document describing the procedures, the methodologies and the roles associated to the quality management in ET | Q2 2026 | Deliverable
ET configuration Management plan - document | Document describing the procedures, the methodologies and the roles associated to the configuration management in ET | Q2 2026 | Deliverable
Project management plan. 1st release - document | Document describing all the processes defined to ensure the successful realization of the Project Office Mandate | Q4 2026 | Deliverable
Preliminary Cost Book - document | Document describing the costing guidelines and providing an approximate cost estimate | Q3 2027 | Deliverable

## Slide 3
For this I need:
1) Management plans updated. I distributed the template. I provide a WBS for the OBS skeleton. I need your feedbacks. After the Symposium we will start to work with these structures and provide the documents.
2) Dedicated Meetings:
risk meeting in Rome discussing: plan, register content, strategy for extending the risks domains. I said that the main deliverable is a report and asked for a template. If not proposed I will do it.
Nomenclature meeting to close. Need the nomenclature document, at least the one indicating the methodology

## Slide 4
CERN contract is signed:
Impact for us:
Structure the configuration collaboration with them
EDMS:
We will start to work on EDMS. Instructions and guidelines will be provided. In the meanwhile, please get self trained:
introduction training material at:
https://edms.cern.ch/project/CERN-0000180042
the local administrators training material at:
https://edms.cern.ch/project/CERN-0000011138
the FAQs:
https://edms-service.web.cern.ch/faq/EDMS/pages/faqs.html
and tutorials:
https://edms-service.web.cern.ch/faq/EDMS/pages/tutorials.html