## Slide 1
B. Di Girolamo, on behalf of the HL-LHC Project
Lessons from HL-LHC to realise further big projects
Arcetri – July 28th 2025
Physics At The Highest Energies With Colliders

## Slide 2
Outline
Very short introduction LHC
HL-LHC  key project goals and challenges
Specific points of attention
Lessons learned for future projects

## Slide 3
LHC in the Geneva Basin and its Experiments
LHC ring:
27 km circumference
CMS
ALICE
LHCb
ATLAS
22 km arcs with
Super Conducting Magnets
Features proton-proton and Lead-Lead and Lead-proton collisions!
[plus other ion species]

## Slide 4: LHC Performance Goals
p collisions Ebeam > 5 TeV LHC: E = 7 TeV
Collision energy: Higgs discovery requires ECM > 1 TeV
Instantaneous luminosity: rate of events in detector
Integrated luminosity: total number of events L
depends on the beam lifetime, the LHC cycle and
‘turn around’ time and overall accelerator efficiency
rare events L > 1033cm-2sec-1 L = 1034cm-2sec-1
300 fb-1 with 1barn = 10-28m2 and femto = 10-15
[3.5/4TeV; 6.5TeV; 6.8TeV]
[2×1034cm-2sec-1]
[389 fb-1] -> [500 fb-1]

## Slide 5
We found a new particle

## Slide 6: LHC Performance
 Over 389fb-1 at 13 TeV so far during first 10 years of operation with
Higgs Discovery in 2012!
> 100fb-1 / year at hand!!!
over 500fb-1 by the end of LHC Run3 by mid 2026!!!
So Why do we need an Upgrade?
Doubling the statistical accuracy for the experiments implies 4 times the data volume!!!
over 20 Years of operation with current peak performance
Operation until 2055 with long shutdowns every 4 years!!!
Higgs discovery in 2012!  But many questions remain and the search continues!!!
Higgs properties [coupling]
More than one Higgs?
BSM Physics? Dark Matter & Dark Energy?
Need for more Data and Statistics!!
HL-LHC goal: 10 times the LHC data Volume within 10 years
 operation from mid 2030 until 2041

## Slide 7: LHC Lifetime Limitation: Debris from the IP & Radiation damage to magnets!
Q2
27 MGy
MCBX3 20 MGy
Cold bore insulation
≈ 35 MGy
7
HL-LHC goal: 10 times the LHC data Volume  requires radiation hard magnets
that can tolerate over 3ab-1!!!
End of the LHC triplet lifetime by End Run3 in 2026
[over 500fb-1]
Need to replace triplets in the LHC after 2026 to keep the machine operational
 replace with design for higher performance!!!
Implies overcoming several limitations in the existing LHC!!!
Cryo cooling of triplet magnets & radiation damage in triplet magnets & machine efficiency!
But also for the experiments!!
 Need for an Upgrade!

## Slide 8
Increase bunch population
Higher Intensity
Smaller
Reduced emittance
Smaller beam size at IP
Crossing angle reduction factor
Shorter bunches, smaller crossing angle, crab cavities
Increase F

## Slide 9: HL-LHC Design Parameters
LHC Magnet system
LHC injector complex
LHC injector complex
HL-LHC triplet magnets
HL-LHC crab cavities
Machine operation &
availability

## Slide 10: Scope
Interaction region HL layout
LHC TODAY
Peak luminosity Lpeak = 2×1034 cm-2s-1
Integrated luminosity in 10 years 300-350 fb-1
LHC TOMORROW
Ultimate peak luminosity 7.5×1034 cm-2s-1
Integrated luminosity in 12 years Lint = 4000 fb-1
HL-LHC
Corrector package (orbit and multipole)
TAXN, TAXS target absorbers
Inner triplet Nb3Sn focusing Quadrupoles, handle more intense beam, withstand higher radiation, are longer to improve beam stability
Q1/Q3, Q2
Recombination dipole
D1
Separation dipole with correctors, for smooth transition btw arc dipoles and final focusing
crab cavities
Collimators
D2

## Slide 11: HL-LHC technical bottleneck: Radiation damage to triplet magnets
Requires larger aperture!
70mm at 210 T/m 150mm diameter 140 T/m
8T peak field at coils  12T field at coils (Nb3Sn)!!!
Need to replace existing triplet magnets with radiation hard system such that the new magnet coils receive a similar radiation dose @ 10 times higher integrated luminosity!!!!!  Shielding!
Tungsten blocks
Capillaries
US-LARP MQXF magnet design
Based on Nb3Sn
technology
 Longer magnets
 New, brittle superconductor!
 New magnet technology!
 New Superconductor

## Slide 12: WP3 Magnet Scope
Design, engineering, construction, test and installation the Insertion Region (IR) magnets of IR1 and IR5 for the HL-LHC upgrade.
  Q1/Q3 cryomagnets: from AUP (US)
  Q2: from CERN
  MCBXF nested corrector magnets: from CIEMAT (Spain)
  HO corrector magnets: from INFN-LASA (Italy) [completed]
  D1 cold masses: from KEK (Japan)
  D2 magnets: from INFN-Ge (Italy)
  D2 corrector magnets: from IHEP (China)
  DCM: from CERN

## Slide 13: Q2 – Overall status
MQXFBP2: being prepared for the HL-LHC string
MQXFB03: test ongoing
MQXFBP3: in the HL-LHC string
MQXFB08: magnet assembled
MQXFB06: cryostating ongoing
MQXFB07: cold mass finishing
3 more magnets to build (B10-B12)
At full production speed! Ca. 50% of Cold-Mass-Assemblies done
MQXFB04: fully qualified for HL-LHC ✓
MQXFB05: fully qualified for HL-LHC ✓

## Slide 14: The IT STRING Scope
The IT STRING will deliver the first complete experience of installing and operating the IT zone
The scope of the IT STRING is to represent, as best as reasonably achievable in a surface building, the various operation modes to STUDY and VALIDATE the COLLECTIVE BEHAVIOUR of the different systems of the HL-LHC’s IT zone (magnets, magnet protection, cryogenics of the magnets and of the superconducting link, magnet powering, vacuum, alignment, interconnections between magnets, and the superconducting link itself).
Installation of IT-String is now completed.
Cooldown expected after summer, Hardware Commissioning to start in October 2025
To reality!

## Slide 15: Magnet Validation for IT-String

## Slide 16: Cold Powering System
D2
DSHM
DFHM
Q1
Q2A
Q2B
Q3
CP
D1
DCM
DFM
DFX
DSHX
DFHX
140 m
89.5 m
Power converters: (18, 7, 2) kA
Power converters: (18, 0.6) kA
Power converters: (60, 120, 200) A
Superconducting link to minimize thermal losses when transporting over 100kA over 100m!
High Temperature Superconductor, MgB2 operating at ca. 20K to 30K
Cooling with gaseous He from liquid He boil off

## Slide 17: Sc Link INSTALLATION IN THE IT STRING

## Slide 18: HL-LHC Upgrade Ingredients: Crab Cavities
Geometric Luminosity
Reduction Factor:
Reduces the effect of geometrical reduction factor
Independent for each IP
Noise from cavities to beam
 Beam size; losses and
phase control!!!
Challenging space constraints:
 requires novel compact
cavity design
Crab Cavities:
effective cross section
nom LHC
nom HL-LHC
early LHC

## Slide 19: HL-LHC cavity designs
RF Dipole: Waveguide or
waveguide-coax couplers
Double ¼-wave: Coaxial couplers with
hook-type antenna
2 Designs with
Different Coupler concepts and
for crossings in the vertical and
horizontal planes
Present baseline: 4 cavities / IP / side  16 total
Present baseline: 2 cavities within one common cryostat  need 4 cryo-modules per CC type

## Slide 20
DQW Crab cavity cryo-module for installation in the SPS
20

## Slide 21: First proton crabbing ever!
Study and R&D
has been very useful to obtain this result
Beam TEST in SPS ongoing between 2018-2023

## Slide 22
New underground galleries and surface buildings for technical infrastructure finished!
 Installation of services ongoing

## Slide 23: Completion of CE on January 20th 2023
Notes: To be updated with latest plans for Ceremony

## Slide 24
Technology
Landmarks
Nb-Ti Technology
Separation / Recombination
dipole magnets: D1 & D2
Finished in 2023
Finished in 2023
Successfully deployed in 2023 Pb-Pb run
½ system already installed for Run3
Series production started
in Industry
Complete Prototype System validated in 2024
Fully validated in 2023 and first magnets ready for installation
First series magnets delivered to CERN
Prototype validated by CERN &
Half of series [3/6] completed
New Civil Engineering
~ 1 km of LHC modified

## Slide 25: HL-LHC physics production
Ions physics run recently approved in 2031-2041
Expected target reduced from 3000 fb-1 to 2771 fb-1
How could 3000 fb-1 could be recovered?
Machine could provide higher pile-up to compensate, if requested by experiments
Limit considering engineering margins PU = 200

## Slide 26: Physics opportunities at HL-LHC
Both experiments and theorists are systematically exploring the physics potential of the HL-LHC, identifying new opportunities and achievable goals while assessing potential limitations
The HL-LHC offers several key advantages
  A vastly larger dataset
  Reduced statistical uncertainties
  Lower experimental systematic uncertainties, thanks to larger calibration datasets
  Decreased background uncertainties, achieved through precise high-statistics control measurements
  Enhanced detector capabilities, such as forward tracking and improved timing
A wide program is planned for HL-LHC!
  Precise characterization of the Higgs boson (precise measurements of its properties and search for sign of BSM physics)
  Detailed exploration of electroweak SM and top sectors (precise measurements and rare signature observations)
  Dedicated searches for BSM physics (long-lived particles, DM, heavy resonances)
  QCD (and high-density QCD) measurements
  Flavour Physics program

## Slide 27: Higgs factory (~180 million Higgs)
Gauge boson decays can reach ~3% precision
Fermion decays (bb,ττ) can reach ~3-4%
μμ can be observed with ~8%
ggH can be measured at ~2%
WH can be measured at ~6%
arXiv:1902.00134
In several cases the uncertainties will be dominated by theory
Just an example

## Slide 28: Lessons learned from a 1.2 BCHF CtC project

## Slide 29
The obvious recipe
It takes time and it needs money
It needs a sustained international interest and support of the scope
It needs international collaborations
It needs a careful Project Management, a robust Quality Plan, a rigorous and flexible Budget and Schedule

## Slide 30: TIME MANAGEMENT

## Slide 31
Run3 operation
Approval of
HL-LHC Project
EU funded HiLumi
Design Study
HL-LHC Operation
We are here
~1 year until start of Long Shutdown 3
> 80% of the project budget of ~1.2 BCHF already committed
The project is ready for installation start in mid 2026!

## Slide 32
High Field SC Magnets
Transition from NbTi to Nb3Sn:
HL-LH lead the R&D for 11-15T magnets based on Nb3Sn technology:
15-20 years R&D program
Transition to HTS:
Assume R&D period of similar siz
e  2035?
32
Ca. 30 years of NbTi magnet R&D leading up to the LHC dipole magnets!
Transition from NbTi to Nb3Sn: requires similar length of R&D!
HL-LHC led the R&D for 11-15T magnets based on Nb3Sn technology:
Started in early 2000
15-20 years R&D program
 Ready for installation in 2028
Magnet development requires substantial R&D effort!!!
FCC-hh
HLHL
HL-LHC magnet
Installation from
2028 to 2029

## Slide 33: SCHEDULE Management
We work with 2 different schedules
Equipment readiness schedule
Long shutdown 3 schedule
Float:
Time lag btw READY and NEEDED for installation

## Slide 34: Equipment readiness Schedule: Bottom-up
Each WP manages its In-work schedule
Data are exchanged with Monitoring & Control Office
EVM provides complementary monitoring
The HL-MCO manages:
Schedule baseline
Isochrone line
Schedule change
Interlinked deliverables
Project master schedule
Critical/ sub-critical path
Schedule margins via installation plan

## Slide 35: Master Schedule – LS3 shift
Impact of LS3 shift
Long Term Schedule v.4.1 Engineering Check (ACC-PM-MS-0004)
still 4.5 months to be gain
YETS 2025-26
LS3 LHC start shifted to 2026 and extended
Start delayed to the 29th of June 2026 for the LHC
Duration beam to beam in the LHC: 47 months (+4.5 months wrt long term revision 4.0)
Master Schedule In Work CSR2024
upgrade
specifications
fabrication
assembly
test
installation
commissioning
development

## Slide 36: Long shutdown Installation schedule
Warm-up and related tests
Cabling and CV dismantling
LSS dismantling and transport after cryo lockout
Cabling and CV installation
LSS installation, including transport
Cool-down, related test & HWC
LSS dismantling after cryo lockout
  Beam vacuum, magnets, collimators, QRL dismantling and transport
Cabling and CV dismantling
  Optical fibre duct cut and displaced, de-cabling and EN-EL infrastructure dismantling
  Piping dismantling
Core excavation
  Core excavation and Minor Civil Engineering work
Cabling and CV installation
  Power cable infrastructure installation (from core excavation to QXL installation)
  Piping installation
LSS installation, including transport – QXL and SC link
  QXL installation + Cold test
  SC link(DSHX/M) unspooling (after first QXL installation)
Cabling installation
  Optical fibre installation, re-cabling, pulling/blowing cables and test
LSS installation, including transport –accelerator elements
  Beam vacuum, magnet, Crab cavities, collimators, TAXN, DFX/M, …
zone

## Slide 37: BUDGET MANAGEMENT

## Slide 38: Budget figures
Budget At Completion | 1,178
CERN funds | 1,069
In-kind | 94.4
External funds | 14.5
MCHF
1178.0
108.9
Procurement of the scope financed by cash contribution is managed by CERN
1,069.0+14.5
=1,083.5
~9%

## Slide 39: Resources
Per WP
Per year
Long Shutdown
Industrial support contracts, not appearing as workforce, but as CHF (labour hours)
  1,790
  2,230
= 4,020 FTE

## Slide 40: BAC evolution
Scope reduction compensates infrastructures cost
Infrastructures reevaluation
Russian
in-kinds
Covid & cost changes
Russian
in-sourcing
Cryogenic contracts
kCHF
Indexation, insourcings, LS3 shift cost
CSR | MCHF | Delta
2015 | 1033 | 
2018 | 1041 | +0.9%
2019 | 1088 | +4.5%
2021 | 1102 | +1.3%
2023 | 1141 | +3.4%
2024 | 1157 | +1.4%
2025 | 1178 | +1.8%
TOTAL |  | +14%

## Slide 41: Financing HiLumi
Cumulative Budget Deficit
[MCHF]
LHC
HL-LHC
CERN works with constant annual contribution by its Member States.
To reabsorb the Cumulative Budget Deficit due to HL-LHC, no other major project may be financed before ~2032.
2000 | 2002 | 2004 | 2006 | 2008 | 2010 | 2012 | 2014 | 2016 | 2018 | 2020 | 2022 | 2024 | 2026 | 2028 | 2030 | 2032 | 2034

## Slide 42: PROJECT MANAGEMENT

## Slide 43: Interplay work packages and project management
THE WP’s…
THE Project…
Manage the technical issues and decisions
Manage schedule and budget of the WP
Report to the Project
Request cost/schedule changes
Dictates Templates and Quality
Manages change
Manages interlinking deliverables
Identifies & follows critical path
Manages buffer budget
Manages integration, installation
Manages Make or Buy Plan
Manages Risk
Reports to Management
Strong PM delegation to WPs

## Slide 44: MONITORING

## Slide 45: Earned Value Management
Work is detailed, scheduled, budget estimated, to lowest level of detail
Planned Value
The project engineer reports progress on each task (work-unit), on monthly basis
Earned Value
The accounting system computes the real cost for the activity
Actual Cost
BAC
Time
today
Schedule Variance
Incremental cost increases are understood: →Schedule delays vs overspending
Key to transparent reporting to stakeholders and trust of management
Cost Variance
, via Budget Codes
BUDGET CODE
92261 WP17.3 – Cooling – SF Cooling Towers
94012 WP03 – Q2 – Cold tests
BC used for: Financial planning, purchasing, accounting, EVM
SM18 test bench reconfiguration
SM18 powering
Shuffling modules
Magnet protection
SM18 DAQ
SF Cooling towers point 1
SF Cooling towers point 5

## Slide 46: PROCESSES: Committees and meetings

## Slide 47: organization
CERN Machine Advisory Committee
Cost & Schedule Reviewer’s panel
HL Collaboration board
Technical Coordination Committee
CONFIGURATION
Project-wide Configuration management meeting
WP Project Steering Meetings
WP Monitoring Cost & Schedule
Single WP audit
 next slide
Collaboration Steering Committees
IN-KIND single collaboration agreement management
Director general
CERN Council
Finance Committee
Scientific Policy Committee
advisory
Governance
project
Accelerators director
Links the HLLHC machine and the experiments upgrade
HL-LHC Executive board
HL Project office Mgt Meetings
PL & coordinators
Management
HL-LHC
HL Coordination group
ATS-HL meeting
HLLHC project and ATS resource providers (departm’s)
HL Machine & exp. coordination
All In-kind institutes

## Slide 48: PROCESSES
TCC: Technical Coordination Committee, weekly, all WPs
PSM: Project Steering Meeting, 3mestral, per WP
CONFIGURATION
BUDGET & SCHEDULE
Engineering Change Request
Schedule Change Request
Decision Management Report
Decision Management Report
Decision Management Report
Engineering Change Request
NEW Cost & Schedule BASELINE
HL yearly Cost
& Schedule
Review
CSR Panel recommends strategy
to ATS head
CERN arbitration
ATS presents strategy to DG+ FD
CERN Medium Term Plan
DG presents strategy to Council
Council approves
CSR: HL Cost & Schedule Review
MTP: CERN Medium Term plan, N-1/ N+5
Baseline budget & schedule
CMAC
Configuration review
Chamonix yearly LHC performance workshop
TCC
TCC
TCC
TCC
TCC
PSM-WPx
PSM-WPx
PSM-WPx
Approval by
WPLs, PL, DPL, BSO, DH, GL
Approval by
WPLs, PL, DPL, BSO, DH, GL
Budget CR
Budget CR
9 months
Baseline: Technical Design Report
In-work budget & schedule

## Slide 49: Quality Assurance

## Slide 50: Pragmatic approach to Quality Assurance
External contributors are governed by the quality management plans of their home institute, however all HL-LHC deliverables shall be compatible with the HL-LHC Quality plan
Hardware baseline documentation stored in EDMS (primary tool for documentation at CERN)
Fabrication records in MTF (Asset management tool)
Project technical information accessible to all “Hilumiers”
Corporate image when representing the project

## Slide 51: Points specific to International Collaborations (my specialty)

## Slide 52: International Collaboration: The Insertion Region (up to Q4)
Q1
Q2a
Q2b
Q3
CP
D1
DFX
DFM
Connection to LHC (UL)
Service gallery (UR)
TAXS
Crab cavities
UA Gallery
Q4
Collimators
TAXN
Service cavern
SC Links
D2
HL-LHC Introduction and LHC overview

## Slide 53: Collaborating Institutes
Not anymore valid

## Slide 54: Interleaved in-kind & CERN deliverables The example of the WP4 crab cavities
Components (FPC, beam screen, RF lines, …)
Components
5 DQW cryomodules (Europe) | 5 RFD cryomodules (North America) | 20 RF Systems (Asia, CERN)
Cavities + processing + helium vessels by Research Instruments (DE) & CERN Cold magnetic shields by UK HOM couplers + antennas by CERN 4 CM by UK (STFC) & 1 CM at CERN with some components from CERN All cavities & CM cold validation tests at CERN (and a back up at Uppsala-Sweden) | Bare cavities by Zanon (IT) under US-AUP Processing + cold magnetic shield + helium vessel + HOM couplers + antennas + cold tests by US-AUP/CERN 5 CM by TRIUMF-Canada with some components by CERN CM cold validation tests at CERN | High power amplifiers (IOT) CERN, financed KEK High power RF lines, circulators, loads by CERN, financed KEK TCA platform for LLRF by CERN
5 DQW cryomodules (Europe) | 5 RFD cryomodules (North America) | 20 RF Systems (Asia, CERN)
Cavities + processing + helium vessels by Research Instruments (DE) & CERN Cold magnetic shields by UK HOM couplers + antennas by CERN 4 CM by UK (STFC) & 1 CM at CERN with some components from CERN All cavities & CM cold validation tests at CERN (and a back up at Uppsala-Sweden) | Bare cavities by Zanon (IT) under US-AUP Processing + cold magnetic shield + helium vessel + HOM couplers + antennas + cold tests by US-AUP/CERN 5 CM by TRIUMF-Canada with some components by CERN CM cold validation tests at CERN | 
Multiplication of schedule risk from one collaborating partner to the next
( )

## Slide 55: Core value and In-Kind value
CORE VALUE
=
Equivalent cost for CERN to execute the full extent of the scope
CORE VALUE
=
Equivalent cost for CERN to execute the full extent of the scope
CERN
-funded
part
IN-KIND CORE VALUE
*Proportion for illustration purpose only
General rule
CERN/Member States = 50/50
CERN/Non-Member States = 0/100
This defines in-kind value
In-kind core value is what remains from the core value estimate, when we subtract what CERN funds

## Slide 56: Lessons learned

## Slide 57: Lessons learned from collaborations
Differences betweek CERN accounting and Collaborators accounting
The HL-LHC CORE cost
  The CERN CORE costs includes material and labor for construction, Quality and construction documentation.
  It does not include conceptual design and construction follow-up or supervision, the cost of CERN Staff, the cost of infrastructures that might be needed to execute the work
The effective or declared cost for the Institutes can be significantly higher depending on the effort on infrastructure and on the accounting model that may take into account the full manpower cost and overheads
This can create issues with funding agencies: recognition of value vs. paid value

## Slide 58: Lesson from “It takes time and it needs money”
The timeline of the big projects span decades
  If new projects pop up (FCC, MuonCollider, etc.) the hardware builders get distracted – almost as if “production is boring”
    Effect: less attention to production – non-conformities – crisis – more time to resolve and more money spent
  In a chain of integration, delays happen and this might create clashes
    Example an item produced in Country A and to be integrated with other items by Country B, is delayed by X months and other priorities kick-in and Country B has to reduce manpower to finish the integration
    New projects and national strategies while production not yet finished
  Technical experts in companies changing with small overlap
  Companies love large productions: an upgrade triggers small productions
Some countries value money more than scope and schedule
  Remaining within cost is the main parameter of success

## Slide 59: Lesson from “It takes time and it needs money”
Crises happen
  COVID hit every country: extra costs
  Wars didn’t help: lost a substantial contribution promised earlier
  Detectors or accelerator items not ready: schedule shift, additional manpower needed, contracts for installations moved and penalties
Some institutes, for budget reasons, have split procurement contracts (for example for series and spares)
  Number of items for the project is low and industry, after the first contracts, understands they have little profit and on the second contract they want to recover…bad idea

## Slide 60: Misalignment of fiscal years and rigidity
Expenditures within a fiscal year can be interpreted rigidly
  Item can be ready in advance, but not delivered because its delivery and transfer of liability was foreseen in next fiscal year

## Slide 61: Lessons from consortia of institutes
Funding agencies might favor to have a single institute managing the funds for deliverables of multiple institutes
  Multi-parties agreements or single agreement to be signed by all
  Management of liabilities towards a single end point
  Multiple legal services, each with a different approach or policy
It takes time to go through legal aspects, while the technical aspects are instead very clear and would allow start of work very quickly

## Slide 62: Lesson: The High Cost of Schedule Drift
Challenge: The critical LS3 installation phase has been repeatedly delayed, now at its "hard limit".
The Cost:
  Estimated at ~1 MCHF per month of delay.
Lesson: Schedule delays have significant and compounding financial consequences. Proactive management of the critical path and schedule float is paramount.

## Slide 63: Lesson: Managing Without a Formal Contingency
Challenge: The project budget was approved with no formal contingency for risks.
The Solution: A Dynamic "Buffering Reserve"
  The Project Office maintains a central reserve.
  It's funded by capturing savings and descoped items from Work Packages.
  Funds are re-allocated to cover overruns or new scope.
Lesson: This model offers flexibility and strong central control but makes the budget highly sensitive to risks, leading to an implicit tolerance for cost drift.

## Slide 64: Lesson: In-Kind Collaborations (and Industrial contracts)
Challenge: Managing dozens of international partners providing critical components ("in-kind") is a source of risk.
The Impact:
  Delays from one partner can cascade through the project schedule.
  It may happen that CERN needs to internalise items to minimise delays
Lesson: While essential for funding, the in-kind model requires extremely robust governance, clear interfaces, and proactive risk management to mitigate inevitable delays. CERN can help and this needs an effort in keeping knowledge and strength over decades

## Slide 65: Lesson: A Flexible PM Model in a Matrix Organization
The Model: lightweight, flexible, distributed
  Strong delegation of PM to technical Work Package leaders.
  Relies on a dense network of review meetings (TCC, PSM) for coordination and control.
The Outcome:
  Pros: Adapts well to CERN's scientific and matrix culture.
  Cons: Matrix and top-down management priorities (project vs. operation) can contribute to schedule overruns and recurring cost pressure.
Lesson: A tailored PM approach is necessary, but it must be balanced with strong central oversight to enforce discipline and contain drift.

## Slide 66: Lesson: The Power of Transparent Monitoring
Challenge: How do you track progress and justify costs to stakeholders in a project this complex?
Key Tools:
  Earned Value Management (EVM): Essential for identifying schedule vs. cost variance.
  Schedule Float Analysis: Comparing the "equipment ready" date with the "needed for installation" date provides a clear, forward-looking risk indicator.
Lesson: Consistent, data-driven monitoring builds stakeholder trust and provides the evidence needed for difficult decisions regarding cost, schedule, and scope changes.

## Slide 67: Lesson: Key Takeaways for Future Projects
The HL-LHC experience highlights four pillars for managing similar large scientific projects:
  Adaptability: Be prepared to change scope, schedule, and plans. Rigid, long-term plans are unrealistic.
  Robust Governance: A clear, multi-layered governance and meeting structure is non-negotiable for managing international collaborations and complex interfaces.
  Transparent Monitoring: Use tools like EVM and float analysis to provide clear, honest, and data-driven status reports to all stakeholders.
  Continuous Improvement: Acknowledge weaknesses in the project management model and actively work to strengthen processes, tools, and culture.
AND do not forget to plan for costs for decommissiong and dismantling

## Slide 68
More about HL-LHC
Published in 2024 and available as
Open Access Publication
https://doi.org/10.1142/13487
ISBN: 978-981-127-894-5

## Slide 69: PM workshop at CERN: AcceleratePM
Date (provisional)
Themes
Contact @CERN
Contacted institutes
Cost, Schedule, Risk, Requirements Management, Change Management, Test, Model Based System Engineering.
Early dec 2025
Format
Networking, cross fertilisation, synergies.
Presentations
Round tables
GSI/FAIR, ESS, DESY, PSI, INFN…
Giovanna.Vandoni@cern.ch
Michele.Battistin@cern.ch
Methodologies, implementation strategies, software, return of experience.
Investigation axes

## Slide 70: THANK YOU!
The invaluable sources
O.Brüning, H.Garcia Gavela, G. Vandoni, M.Zerlauth
…and the full HL-LHC Project!
…and thanks to:

## Slide 71: Backup slides

## Slide 72: LHC Challenges: Crossing Angle at Interaction Points
Parasitic bunch encounters:
non-linear fields from long-range beam-beam interaction:
 Operation requires crossing angle
efficient operation requires large beam separation at unwanted collision points  Separation of 10 -12 s  large magnet apertures next to the experiments!!
 at the limit of magnet technology!!!
Insertion Layout:
ca.130m  150m
ca.50m
Operation with ca. 2800 bunches @ 25ns spacing  approximately 30 unwanted collisions per
Interaction Region (IR) in the LHC
 even more for HL-LHC!

## Slide 73: EVM at CSR 24 - baseline 8
 | [MCHF]
Budget At Completion | 1157.0
BAC CERN funds | 1050.1
BAC in-cash | 12.5
BAC CERN + in-cash | 1062.6
BAC In-kind | 94.4
Planned Value | 800
Earned Value | 767
Actual Cost | 749
Uncommitted, CERN + in-cash | 210
All HL-LHC, including in-kind
-94.4M

## Slide 74: Baselines comparison
Expenditure capacity depending on workforce and business model:
250kCHF/(FTE · year)
Heavy in-house procurement via fabrication workshops and service groups
Strong inflection of PV slope pushed forward
PV also determined by labor cost, shows strong labor effort in LS3
Linear EV eats up schedule float

## Slide 75: QA – Mandate
Support the members of the project (CERN and Collaborations) on the fulfillment of the HL Quality plan*.
Definition of requirements (Configuration, Baseline Change Requests)
Control of requirements (Technical reviews, Deviations, Nonconformities)
Traceability of requirements (Documents and records)
Continuous improvement (Corrective & preventive actions and audits)
* Based on the ISO 9001:2015

## Slide 76: The need of a Quality Plan for the Project
HL-LHC is an upgrade of an existing machine (LHC). Therefore, there were existing rules and procedures to be respected
A Quality Plan was prepared for the LHC Project. This document was still in use when the project was approved, but it became obsolete on many aspects. With the advent of the HL-LHC Project, it was necessary that an updated Quality Plan was released to fulfil both the HL-LHC Project and the LHC machine in operation
CERN is not ISO-9001 certified and there is not a common approach in all Departments/Groups concerning quality matters (even within the same Group)
Safety rules at CERN are to be respected (documentation to be approved by HSE for safety compliance) but we are not an INB (no external Control by Authorities)
Requirements (documentation, control, safety aspects, etc) are different than decades ago (continuous improvement on quality aspects)

## Slide 77: Procurement & Risk

## Slide 78: Make or Buy Plan
Bottom-up approach identifies what can be produced with industrial partners, what must be insourced
Breakdown of Contracts included in the HL-LHC Procurement Plan
How much
what
when

## Slide 79: Qualitative risk analysis
HL has no contingency for risk in budget
Risk quantified only in relation to procurement: Cost risk only
Risk qualitatively analysed for all other aspects : RISK Intelligence Map
Risk analysis is used to
  Identify threats & opportunities, decrease uncertainty
  Provide evidence-based information for decision taking
  Increase resilience by anticipating adverse events
  Prioritize risk treatment where impact and vulnerability are highest.
  Risk register, annually renewed, continuously updated via PSMs

## Slide 80: Work packages

## Slide 82: Interleaved in-kind & CERN deliverables The example of the magnets
Design, engineering, construction, test and installation the Insertion Region (IR) magnets of IR1 and IR5 for the HL-LHC upgrade.
  Q1/Q3 cryomagnets: from AUP (US)
  Q2: from CERN
  MCBXF nested corrector magnets: from CIEMAT (Spain)
  HO corrector magnets: from INFN-LASA (Italy) [completed]
  D1 cold masses: from KEK (Japan)
  D2 magnets: from INFN-Ge (Italy)
  D2 corrector magnets: from IHEP (China)
  DCM: from CERN
No chain in-kind in-kind CERN, but several deliverables integrated together at CERN

## Slide 83
Run 3
]