## Foglio1
Year | k€ | Quarter | WP 0 AMCHIP - costs in column G |  |  |  |  | WP 1 Boards - costs in K€ |  |  | WP2 Integration | WP 3 commissioning | WP4 Simulation
2011 | 145 | 1st Q | design Am4 | Annovi, Crescioli, Stabile, Beretta |  |  |  | design AMBFTK/LAMB
|  | 2nd Q | design Am4 |  |  |  |  | design AMBFTK/LAMB
|  | 3rd Q | design Am4 |  |  |  |  | design AMBFTK/LAMB
|  | 4th Q | design Am4-submission |  |  |  | 70 k$ | design AMBFTK/LAMB
2012 | 40 | 1st Q |  |  | test stand setup | Beretta, Annovi,Stabile |  | design AMBFTK/LAMB |  |  |  | VS @ CERN Lab32
|  | 2nd Q |  |  | test stand setup |  |  | design AMBFTK/LAMB |  |  |  | VS @ CERN Lab32
|  | 3rd Q | miniasic/serdesIP/Am5 | Beretta, Stabile, Crescioli | test AMchip4 | Beretta, Annovi, Becherle | 110 k$ | test AMBFTK/LAMB |  |  |  | VS @ CERN Lab4
|  | 4th Q | miniasic/serdesIP/Am5 |  | test AMchip4 |  |  | test AMBFTK/LAMB |  |  |  | VS @ POINT 1
2013 | 260 | 1st Q | sub. miniasic 20/3/13 | Stabile, Crescioli, Becherle |  | Beretta-Becherle | 23 k$+5k euro | designSLP2(AMB+LAMB) | 50 |  | AMBFTK @CAEN
|  | 2nd Q | design Am5 |  | test stand setup adjust. | BerettaStabileBecherle |  | designSLP2(AMB+LAMB) |  |  | AMBFTK @CAEN
|  | 3rd Q | design Am5-submission |  | tests miniasic | Beretta-Becherle | 200+5 keuro | test SLP2 |  |  | AMBFTK @CAEN | AMBFTK @POINT 1
|  | 4th Q |  |  | test stand setup adjust. | BerettaStabileBecherle |  | test SLP2 |  |  | AMBFTK @CAEN | AMBFTK @POINT 1
2014 | 260 | 1st Q | design Am6 | Stabile, Crescioli | test AMchip5 | Becherle Beretta | 93 keuro | prod. 10 SLP2-AMB |  | 32 | SLP2 @CAEN
|  | 2nd Q | design Am6 |  | 1500 AM5 - 8 PUs |  |  | prod. 40 SLP2-LAMB |  |  | SLP2 @CAEN | commissioning Demo
|  | 3rd Q | design Am6 |  | test production |  |  | prod FTK_IM |  | 135 | SLP2 @CAEN | commissioning Demo
|  | 4th Q | design Am6 |  | commissioning | [5 empty] | SLP2 @CAEN | commissioning Demo
2015 | 263.3333 | 1st Q | Full mask submiss. |  |  |  | 244 k$ + 256 k$ |  |  |  |  | commissioning Demo
|  | 2nd Q |  |  | test AM6 | all | [5 empty] | Data taking with Demo
|  | 3rd Q |  |  | 2.7 kAM6 6 wafers-16 PU |  | 44 k$ | prod. 16 SLP2-AMB |  | 50
|  | 4th Q |  |  | test production/comm. | all |  | prod. 64 SLP2-LAMB
2016 | 273.3333 | 1st Q |  |  | prod 24 wafers 64 PU |  | 88 k$ + 88 k$ | prod. 64 SLP2-AMB |  | 200 |  | commissioning FTK
|  | 2nd Q |  |  | test production | all |  | prod. 256 SLP2-LAMB |  |  |  | commissioning FTK
|  | 3rd Q |  |  | commissioning | all | [5 empty] | running FTk
|  | 4th Q | [9 empty] | running FTk
2017 | 350 | 1st Q |  |  | production 64 PU |  | 180 k$ | prod. 64 SLP2-AMB |  | 200 |  | commissioning FTK
|  | 2nd Q |  |  | test production | all |  | prod. 256 SLP2-LAMB |  |  |  | commissioning FTK
|  | 3rd Q |  |  | commissioning | all | [5 empty] | running FTk
|  | 4th Q | [9 empty] | running FTk
2018 |  | 1st Q | DATA TAKING - MAINTANAMCE
2nd Q
3rd Q
4th Q
tot | 1601.6667 |  |  |  |  | TOT not-USA keuro | 303 |  |  | 617
~500 keuro in excess of INFN funds | [5 empty] | TOT not-USA k$ | 827
EXTRA FUNDS | [6 empty] | 992.1667
100 keuros Germany for Amchip
50-100 keuros from Japan for Amchip | [8 empty] | SUPERTOT ITALIA | 1609.1667
University of Geneva: participation to VS, commissioning, simulation… can we add LAMB design and production ~200-300 keuro?
Institutions that could sign the IMOU and bring EXTRA FUNDS
LPHNE: participation to Amchip design/test with Crescioli? Funds?
Tessaloniki: ?? How can Tessaloniki participate?
Academia Sinica: can help to get better quotations for Amchip prototypes and productions?
Extra info:
FTK is selected for negotiation for the IAPP last call (FP7)-> good probability to get EU funds for manpower and collaboration with two CAEN and Prisma electronics. We plan to integrate FTK@CAEN
50
46
16
6.1
7.04
9.5
10
144.64